| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Bob Simmons | Date: March 11, 2004 |
| ECP No: 04-005 | ECP Title: Revised Estimates for Design, R&D, and Tooling |
| Required Reviewers |
| Required Reviewers for this ECP: WBS Managers, Project Engineers, Project Control Manager, Engineering Manager, NCSX Project Manager, & NCSX Federal Project Director |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Update cost and schedule baselines to reflect this ECP. |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: March 11, 2004 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: Update NCSX Cost and Schedule Baselines to reflect updated estimates for Final Design, R&D, and Tooling costs, and corrections to prior year actual costs. Impacted WBS Elements: WBS 12, 14, 18, 25, 65, 74, 74, 81, & 84. Allocations and Contingency also impacted. Impacts of Change (Briefly Describe): In summary, this ECP reflects: WBS 12. Vacuum Vessel: increases in design, weld joint R&D, and oversight of R&D contracts (Approx. +$500k) WBS 14. Modular Coils: reduced estimates for coil fabrication tooling and MCWF R&D. (approx. –$300k). WBS 18. Field Period Assembly: updated estimate reflecting more mature design (approx. +$50k) WBS 8: Management and Integration, increases in FY04 management costs, outside PDR reviewer costs, PPPL allocated indirect costs; (approx. +$210). WBS 2-7: miscellaneous re-estimates (approx. +$100k) NET INCREASE IN BASE ESTIMATE: $560K, to be covered by a reduction in contingency. More detailed breakdown of the changes are found in Attachment 2. Included in these changes are adjustments to the FY2003 costs (approx. +$180K) to reflect the difference between the PDR baseline and actual FY2003 costs. As a result of the above changes, it is proposed to draw down contingency by approximately $560K from $15,910K to $15,350K. Assessment of Other Options: None. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: March 11, 2004 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. Attachment 1 – Detailed Analyses by WBS Level 2 and 3 Attachment 2 – Updated NCSX Project Baseline Description of Change: This ECP updates the cost and schedule baselines to reflect updated estimates for Final Design, R&D, and Tooling costs, and corrections to prior year actual costs. These changes reflect information learned in both the in-house design and R&D efforts and prototype vendor assessments and discoveries as their work proceeded. The largest increases are for additional vacuum vessel design, analyses, and R&D; and for additional project management oversight. These changes are necessary to mitigate down-stream risks. The increases are partly offset by reductions in tooling cost estimates for the modular coil winding activities. |