## Main
NCSX WBS 4 REVISED BASELINE ESTIMATE 8/14/03 ; WITH GFM ESTIMATE 01/19/04 | [12 empty] | M&S | [5 empty] | Design/ Procurement |  | Installation |  |  |  | Commissioning |  |  | Line Total | Contingency |  |  |  | Total Cost
[6 empty] | Start date | Finish date | Multiplier | Qnty | Units | Qnty | Units | Qnty | Units | Unit Cost | Cost | Spare Units | Spare Cost | EEEM | Dm | EEEM | EESM | EETB | SC | EEEM | EESM | EETB |  | Tech | Cost | Schedule | Total
[15 empty] | (k$/unit) | ($K) |  | ($K) | (md) | (md) | (md) | (md) | (md) | ($K) | (md) | (md) | (md) | ($K) | (%) | (%) | (%) | (%) | ($K)
41- AC Power | 519.0815 | 612.5162
| 411 - Auxiliary AC Power | 475.7595 | 561.3962
|  |  | Test Cell AC Power Distribution |  |  | 2004-01-01 | 2007-01-01 | 1 | [6 empty] | 0 | 0 |  | 0 | 20 | 50 | 10 | 10 | 60 |  | 6 | 10 | 20 | 158.384 | 8 | 8 | 2 | 18 | 186.8931 |  | 18
[5 empty] | Iso Transformers |  |  | 1 |  |  |  |  | 3 | unit | 5 | 15 |  | 0 | [9 empty] | 19.95 | 8 | 8 | 2 | 18 | 23.541 |  | 18
[5 empty] | Transformers |  |  | 1 |  |  |  |  | 6 | unit | 3.5 | 21 |  | 0 | [9 empty] | 27.93 | 8 | 8 | 2 | 18 | 32.9574 |  | 18
[5 empty] | Panels |  |  | 1 |  |  |  |  | 6 | unit | 2.5 | 15 |  | 0 | [9 empty] | 19.95 | 8 | 8 | 2 | 18 | 23.541 |  | 18
[5 empty] | Cable |  |  | 1 |  |  |  |  | 800 | feet | 0.0015 | 1.2 |  | 0 | [9 empty] | 1.596 | 8 | 8 | 2 | 18 | 1.8833 |  | 18
[5 empty] | Tray |  |  | 1 |  |  |  |  | 100 | feet | 0.01 | 1 |  | 0 | [9 empty] | 1.33 | 8 | 8 | 2 | 18 | 1.5694 |  | 18
[5 empty] | Conduit |  |  | 1 |  |  |  |  | 150 | feet | 0.001 | 0.15 |  | 0 | [9 empty] | 0.1995 | 8 | 8 | 2 | 18 | 0.23541 |  | 18
|  |  | Ex-Test Cell AC Power Distribution |  | Reactivate/new installation | 2004-01-01 | 2006-01-01 | 1 |  |  |  |  | 3 | xfmr/ panel | 3 | 9 |  | 0 | 10 | 15 | 15 | 20 | 30 |  | 10 | 10 | 20 | 128.81 | 8 | 8 | 2 | 18 | 151.9958 |  | 18
|  |  | Standby Power for Cryo systems |  | UPS Systems | [29 empty] | #DIV/0!
|  |  | Grounding |  | Misc. grounding | 6/104 | 2006-06-30 | 1 |  |  |  |  | 1 | lot | 5 | 5 |  | 0 | 10 | 25 | 5 | 15 | 20 | 20 | 5 | 5 | 10 | 117.61 | 8 | 8 | 2 | 18 | 138.7798 |  | 18
| 412 - Experimental AC Power | 43.322 | 51.12
|  |  | D-site Pulsed AC Power Distribution |  | Lockouts/protection/reactivate | 2005-01-01 | 2006-04-01 | 1 |  |  |  |  | 1 | lot | 5 | 5 |  | 0 | 5 | 5 | 2 | 8 | 10 |  | 3 | 3 | 5 | 43.322 | 8 | 8 | 2 | 18 | 51.12 |  | 18
42 - AC/DC Converters | 0 | 0
| 421 - C-site AC/DC Converters | 0 | 0
|  |  | Trim Coil Power Supplies | Robicon PS Maintenance | Reactivation |  |  | 1 |  |  |  |  | 1 | lot | 5 | 5 |  | 0 | 10 | 15 | 10 | 10 | 15 |  | 3 | 3 | 0 | 0 | 8 | 8 | 2 |  | 0
| 422 - D-site AC/DC Converters | 0 | 0 |  |  |  |  | 1 | [24 empty] | 0
|  |  | Coil Power Supplies | Transrex PS Maintenance | Reactivation | 2000-09-30 | 2001-05-31 | 1 |  |  |  |  | 2 | PSS | 0.25 | 0.5 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 5 | 5 | 4 |  | 8 | 8 | 2 |  | 0 |  | #DIV/0!
43 - DC Systems | 2244.691 | 2729.993
| 431 - C-site DC Systems | 324.926 | 383.4127
|  |  | Coil DC Cabling to Disconnect/Link Box (PCTB) | Design & Supervision |  | 2004-03-01 | 2005-06-01 | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Design/ Procurement Dm: 60; Installation EEEM: 15; Installation EESM: 15; Installation EETB: 15 | 112.68 | 8 | 8 | 2 | 18 | 132.9624 |  | 18
|  |  |  | Materials & Installation | Reroute & Reconnect |  |  | 1 | 12 | Cable | 48 | Hrs/ Cable | 576 | Hrs | 0.075 | 43.2 |  | 0 | [9 empty] | 57.456 | 8 | 8 | 2 | 18 | 67.7981 |  | 18
[5 empty] | Cable Tray |  |  | 1 |  |  |  |  | 50 | ft | 0.01 | 0.5 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 4 | 6.617 | 8 | 8 | 2 | 18 | 7.8081 |  | 18
[5 empty] | Install Tray |  |  | 1 |  |  |  |  | 50 | ft | 0.01 | 0.5 |  | 0 | [9 empty] | 0.665 | 8 | 8 | 2 | 18 | 0.7847 |  | 18
|  |  | DC Cabling to Coils in Test Cell | Design & Supervision |  | 2005-06-01 | 2005-12-01 | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Design/ Procurement Dm: 40; Installation EEEM: 10; Installation EESM: 10; Installation EETB: 10 | 81.44 | 8 | 8 | 2 | 18 | 96.0992 |  | 18
|  |  |  | Materials & Installation | 1000MCM 5kV Cable For Circuit |  |  | 1 | 6 | Ckt | 100 | ft/ckt | 600 | ft | 0.012 | 7.2 |  | 0 | [9 empty] | 9.576 | 8 | 8 | 2 | 18 | 11.2997 |  | 18
[5 empty] | Install Cable |  |  | 1 | 6 | Ckt | 100 | ft/ckt | 600 | ft | 0.055 | 33 |  | 0 | [9 empty] | 43.89 | 8 | 8 | 2 | 18 | 51.7902 |  | 18
[5 empty] | Cable Tray |  |  | 1 |  |  |  |  | 100 | ft | 0.01 | 1 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 4 | 7.282 | 8 | 8 | 2 | 18 | 8.5928 |  | 18
[5 empty] | Install Tray |  |  | 1 |  |  |  |  | 100 | ft | 0.01 | 1 |  | 0 | [9 empty] | 1.33 | 8 | 8 | 2 | 18 | 1.5694 |  | 18
[5 empty] | Install Tray |  |  | 1 | 6 | Ckt | 50 | ft/ckt | 300 | ft | 0.01 | 3 |  | 0 | [9 empty] | 3.99 | 8 | 8 | 2 | 18 | 4.7082 |  | 18
|  |  | DC Cabling to Trim Coils | Design & Supervision |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 10; Installation EEEM: 5; Installation EESM: 5; Installation EETB: 5 | 0 | 8 | 8 | 2 |  | 0
|  |  |  | Materials & Installation | 250MCM 5kV Cable For Circuit |  |  | 1 | 4 | Ckt | 150 | ft/ckt | 600 | ft | 0.012 | 7.2 |  | 0 | [9 empty] | 0 | 8 | 8 | 2 |  | 0
[5 empty] | Install Cable |  |  | 1 | 4 | Ckt | 150 | ft/ckt | 600 | ft | 0.055 | 33 |  | 0 | [9 empty] | 0 | 8 | 8 | 2 |  | 0
[5 empty] | Cable Tray |  |  | 1 |  |  |  |  | 100 | ft | 0.01 | 1 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 4 | 0 | 2 | 8 | 2 |  | 0
[5 empty] | Install Tray |  |  | 1 |  |  |  |  | 100 | ft | 0.01 | 1 |  | 0 | [9 empty] | 0 | 2 | 8 | 2 |  | 0
| 432 - D-to-C-Site DC Systems | 1387.9268 | 1719.0113
|  |  | DC Cabling | Design & Supervision |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Design/ Procurement Dm: 25; Installation EEEM: 15; Installation EESM: 10; Installation EETB: 15 | 78.16 | 8 | 8 | 2 | 18 | 92.2288 |  | 18
|  |  |  | Materials & Installation | 1000MCM 5kV Cable | 2003-10-01 | 2004-10-01 | 1 | 14 | Pole | 620 | ft/poles | 8680 | ft | 0.012 | 104.16 |  | 0 | Design/ Procurement EEEM: 5 | 144.8528 | 8 | 8 | 2 | 18 | 170.9263 |  | 18
[5 empty] | Install Cable |  |  | 1 | 14 | Pole | 620 | ft/poles | 8680 | ft | 0.055 | 477.4 |  | 0 | [9 empty] | 634.942 | 8 | 12 | 2 | 22 | 774.6292 |  | 22
[5 empty] | Cable Tray |  |  | 1 |  |  |  |  | 1100 | ft | 0.015 | 16.5 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 4 | 27.897 | 8 | 8 | 2 | 18 | 32.9185 |  | 18
[5 empty] | Install Tray |  |  | 1 |  |  |  |  | 1100 | ft | 0.025 | 27.5 |  | 0 | [9 empty] | 36.575 | 8 | 8 | 2 | 18 | 43.1585 |  | 18
[5 empty] | Structural Supports |  |  | 1 |  |  |  |  | 1 | lot |  |  |  | 0 | Installation SC: 350 | 465.5 | 8 | 20 | 2 | 30 | 605.15 |  | 30
| 433 - D-site DC Systems | 531.8382 | 627.569
|  |  | DC Cabling | Design & Supervision |  | 2004-10-01 | 2005-02-01 | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Design/ Procurement Dm: 50; Installation EEEM: 15; Installation EESM: 15; Installation EETB: 15 | 104.12 | 8 | 8 | 2 | 18 | 122.8616 |  | 18
|  |  |  | Materials & Installation | 1000MCM 5kV Cable For PSS |  |  | 1 | 10 | PSS | 50 | ft/PSS | 500 | ft | 0.012 | 6 |  | 0 | Design/ Procurement EEEM: 5 | 14.3 | 8 | 8 | 2 | 18 | 16.874 |  | 18
[5 empty] | Install Cable |  |  | 1 | 10 | PSS | 50 | ft/PSS | 500 | ft | 0.055 | 0.055 |  | 0 | [9 empty] | 0.07315 | 8 | 8 | 2 | 18 | 0.086317 |  | 18
[5 empty] | 1000MCM 5kV Cable For Circuit |  |  | 1 | 6 | Ckt | 150 | ft/ckt | 900 | ft | 0.012 | 10.8 |  | 0 | [9 empty] | 14.364 | 8 | 8 | 2 | 18 | 16.9495 |  | 18
[5 empty] | Install Cable |  |  | 1 | 6 | Ckt | 150 | ft/ckt | 900 | ft | 0.055 | 49.5 |  | 0 | [9 empty] | 65.835 | 8 | 8 | 2 | 18 | 77.6853 |  | 18
[5 empty] | Cable Tray |  |  | 1 |  |  |  |  | 200 | ft | 0.015 | 3 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 4 | 9.942 | 8 | 8 | 2 | 18 | 11.7316 |  | 18
[5 empty] | Install Tray |  |  | 1 |  |  |  |  | 200 | ft | 0.025 | 5 |  | 0 | [9 empty] | 6.65 | 8 | 8 | 2 | 18 | 7.847 |  | 18
|  |  | DC Current Limiting Reactors (CLRs) | Procure CLRs | [30 empty] | #DIV/0!
Write CLR Installation Procedure
|  |  |  | Install CLRs | [30 empty] | #DIV/0!
|  |  | NSTX TF Power Supply changes | Task of NSTX TF PS changes |  | 2004-10-01 | 2005-10-01 | 1 | [7 empty] | 0 |  | 0 | 6 | 15 | 2 | 2 |  | 10 | 1 | 1 | 2 | 41.548 | 8 | 8 | 2 | 18 | 49.0266
|  |  | NSTX OH PS changes | Task of NSTX OH PS changes |  | 2005-10-01 | 2006-10-01 | 1 | [7 empty] | 0 |  | 0 | 6 | 15 | 2 | 2 |  | 10 | 1 | 1 | 2 | 41.548 | 8 | 8 | 2 | 18 | 49.0266
[6 empty] | 1999-09-30 | 2000-09-30 | [20 empty] | 0
0
0
|  |  | Isolating Switch | Design & Specification |  | 2003-10-01 | 2004-04-01 | 1 | [7 empty] | 0 |  | 0 | Installation EEEM: 5; Installation EESM: 5 | 10.88 | 8 | 8 | 2 | 18 | 12.8384 |  | 18
|  |  |  | Procurement |  |  |  | 1 |  |  |  |  | 7 | switch | 13 | 91 |  | 0 | Installation EEEM: 5; Installation EESM: 5 | 131.91 | 8 | 8 | 2 | 18 | 155.6538 |  | 18
|  |  |  | Installation |  |  |  | 1 | [7 empty] | 0 |  | 0 | 2 | 5 | 5 | 5 | 10 | 50 |  |  |  | 90.668 | 8 | 8 | 2 | 18 | 106.9882 |  | 18
44 - Control & Protection Systems | 1633.2824 | 1941.5644
| 441 - Electrical Interlocks | 611.8756 | 725.6161
|  |  | C-site | Design Interlock System |  | 2004-10-01 | 2006-10-01 | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 15; Design/ Procurement Dm: 25; Installation EEEM: 8; Installation EESM: 15; Installation EETB: 40 | 90.072 | 12 | 8 | 2 | 22 | 109.8878 |  | 22
|  |  |  | Procure PLC | 1 + 1 spare |  |  | 1 |  |  |  |  | 1 | units | 10 | 10 | 1 | 10 | Design/ Procurement EEEM: 10; Design/ Procurement Dm: 20; Installation EEEM: 5; Installation EESM: 5; Installation EETB: 10 | 60.42 | 8 | 8 | 2 | 18 | 71.2956 |  | 18
|  |  |  | Procure I/O |  |  |  | 1 |  |  |  |  | 80 | channels | 0.012 | 0.96 |  | 0 | Design/ Procurement EEEM: 10; Design/ Procurement Dm: 10; Installation EEEM: 10; Installation EESM: 5; Installation EETB: 5 | 42.9168 | 8 | 8 | 2 | 18 | 50.6418 |  | 18
|  |  |  | Program PLC |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 10; Design/ Procurement Dm: 5; Installation EEEM: 5; Installation EESM: 5; Installation EETB: 10 | 34.28 | 8 | 8 | 2 | 18 | 40.4504 |  | 18
|  |  |  | Crate & PS |  |  |  | 1 |  |  |  |  | 1 | units | 1 | 1 |  | 0 | Design/ Procurement EEEM: 10; Installation EEEM: 5; Installation EESM: 5; Installation EETB: 10 | 31.33 | 8 | 8 | 2 | 18 | 36.9694 |  | 18
|  |  |  | Install I/O & Cabling |  |  |  | 1 |  |  |  |  | 1 | units | 8 | 8 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 4; Installation EESM: 5; Installation EETB: 20; Installation SC: 30 | 74.012 | 8 | 8 | 2 | 18 | 87.3342 |  | 18
|  |  | D-to-C-site | Design Interconnection |  | 2003-10-01 | 2004-10-01 | 1 |  |  |  |  | 1 | lot | 5 | 5 |  | 0 | 10 | 15 | 5 | 5 | 20 |  | 5 | 5 | 10 | 73.33 | 8 | 8 | 2 | 18 | 86.5294 |  | 18
|  |  | D-site | Design Interlock System |  | 2004-10-01 | 2005-10-01 | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 10; Design/ Procurement Dm: 15; Installation EEEM: 5; Installation EESM: 10; Installation EETB: 30 | 60.36 | 8 | 8 | 2 | 18 | 71.2248 |  | 18
|  |  |  | Procure PLC |  |  |  | 1 |  |  |  |  | 1 | units | 10 | 10 |  | 0 | Design/ Procurement EEEM: 3; Design/ Procurement Dm: 8; Installation EEEM: 0; Installation EESM: 0; Installation EETB: 0 | 23.94 | 8 | 8 | 2 | 18 | 28.2492 |  | 18
|  |  |  | Procure I/O |  |  |  | 1 |  |  |  |  | 80 | channels | 0.012 | 0.96 |  | 0 | Design/ Procurement EEEM: 0; Design/ Procurement Dm: 0; Installation EEEM: 0; Installation EESM: 0; Installation EETB: 0 | 1.2768 | 8 | 8 | 2 | 18 | 1.5066 |  | 18
|  |  |  | Program PLC |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 10; Design/ Procurement Dm: 5; Installation EEEM: 5; Installation EESM: 5; Installation EETB: 5 | 31.04 | 8 | 8 | 2 | 18 | 36.6272 |  | 18
|  |  |  | Crate & PS |  |  |  | 1 |  |  |  |  | 1 | units | 1 | 1 |  | 0 | Design/ Procurement EEEM: 10; Installation EEEM: 5; Installation EESM: 5; Installation EETB: 5 | 28.09 | 8 | 8 | 2 | 18 | 33.1462 |  | 18
|  |  |  | Install I/O & Cabling |  |  |  | 1 |  |  |  |  | 1 | units | 2 | 2 |  | 0 | Design/ Procurement EEEM: 1; Design/ Procurement Dm: 2; Installation EESM: 5; Installation EETB: 4; Installation SC: 10 | 26.088 | 8 | 8 | 2 | 18 | 30.7838 |  | 18
|  |  |  | Test Modified NSTX HCS |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 10; Commissioning EESM: 10; Commissioning EETB: 20 | 34.72 | 8 | 8 | 2 | 18 | 40.9696 |  | 18
| 442 - Kirk Key Interlocks | 96.732 | 114.1438
|  |  |  | Kirk Keys |  | 2003-10-01 | 2006-10-01 | 1 |  |  |  |  | 1 | lot | 10 | 10 |  | 0 | 15 | 15 | 3 | 5 | 35 |  | 5 | 5 | 15 | 96.732 | 8 | 8 | 2 | 18 | 114.1438 |  | 18
| 443 - Real Time Control | 37.92 | 44.7456
|  |  |  | Develop Control Algorithms |  | 2005-10-01 | 2006-03-01 | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 30 | 37.92 | 8 | 8 | 2 | 18 | 44.7456 |  | 18
| 444 - Instrumentation | 432.498 | 510.3476
|  |  | DC Current Transducers (DCCTs) |  |  | 2005-10-01 | 2006-10-01 | 1 |  |  |  |  | 2 | units | 18 | 36 | 1 | 18 | 5 | 10 | 4 | 8 | 35 |  | 3 | 3 | 15 | 114.04 | 8 | 8 | 2 | 18 | 134.5672 |  | 18
|  |  | DC Shunts |  |  |  |  | 1 |  |  |  |  | 4 | units | 8 | 32 | 1 | 8 | 5 | 10 | 4 | 8 | 35 |  | 3 | 3 | 15 | 108.72 | 8 | 8 | 2 | 18 | 128.2896
|  |  | Signal Conditioning & Associated Cabling |  |  | 2004-01-01 | 2006-01-01 | 1 |  |  |  |  | 1 | lot | 9 | 9 | 0 | 0 | 35 | 10 | 5 | 0 | 35 |  | 10 | 5 | 5 | 114.21 | 8 | 8 | 2 | 18 | 134.7678 |  | 18
|  |  | DC Potential Transducers (DCPTs) |  |  | 2003-10-01 | 2004-10-01 | 1 |  |  |  |  | 12 | units | 1 | 12 | 2 | 2 | 10 | 20 | 5 | 5 | 35 |  | 3 | 3 | 15 | 95.528 | 8 | 8 | 2 | 18 | 112.723
| 445 - Coil Protection | 287.61 | 348.6878
|  |  | Overload Protection & Associated Cabling |  |  | 2005-10-01 | 2006-10-01 | 1 |  |  |  |  | 7 | units | 4 | 28 | 1 | 4 | 50 | 55 | 8 | 25 | 25 | 10 | 10 | 4 | 10 | 232.7 | 12 | 8 | 2 | 22 | 283.894 |  | 22
|  |  | Ground Fault Protection |  |  | 2003-10-01 | 2004-10-01 | 1 |  |  |  |  | 1 | units | 3 | 3 | 1 | 3 | 10 | 10 | 4 | 4 | 15 |  | 4 | 4 | 4 | 54.91 | 8 | 8 | 2 | 18 | 64.7938 |  | 18
| 446 - Ground Fault Monitor | 166.6468 | 198.0235
|  |  | Ground Fault Monitor | Design System |  | 2004-10-01 | 2006-10-01 | 1 | [7 empty] | 0.5 |  | 0 | Design/ Procurement EEEM: 20; Design/ Procurement Dm: 10 | 34.505 | 12 | 8 | 2 | 22 | 42.0961 |  | 22
|  |  |  | Buy & Fabricate cards |  |  |  | 1 |  |  |  |  | 1 | lot | 30 | 30 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 2; Installation EEEM: 5; Installation EESM: 10; Installation EETB: 5 | 62.82 | 8 | 8 | 2 | 18 | 74.1276 |  | 18
|  |  |  | Bench Test |  |  |  | 1 |  |  |  |  | 1 | units | 1 | 1 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 2; Installation EEEM: 1; Installation EESM: 4; Installation EETB: 5 | 13.722 | 8 | 8 | 2 | 18 | 16.192 |  | 18
|  |  |  | Assemble in Rack |  |  |  | 1 |  |  |  |  | 4 | channels | 0.012 | 0.048 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 2; Installation EEEM: 2; Installation EESM: 5; Installation EETB: 5 | 14.6318 | 8 | 8 | 2 | 18 | 17.2656 |  | 18
|  |  |  | Program PLC |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 1; Installation EEEM: 1; Installation EESM: 5 | 7.088 | 8 | 8 | 2 | 18 | 8.3638 |  | 18
|  |  |  | Install Equipment & Cabling |  |  |  | 1 |  |  |  |  | 1 | units | 4 | 4 |  | 0 | 1 | 1 | 3 | 2 | 7 | 8 | 2 | 2 | 2 | 33.88 | 8 | 8 | 2 | 18 | 39.9784 |  | 18
198.0235
45 - System Design and Integration | 810.121 | 967.8384
| 451 - System Design | 475.416 | 560.9909
|  |  | Design Drawings & Drawings changes , as-builts | New drawings & Misc. updates |  | 2004-10-01 | 2007-10-01 | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 160; Design/ Procurement Dm: 160 | 339.2 | 8 | 8 | 2 | 18 | 400.256 |  | 18
|  |  | CDR Power system | All power systems |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 10.6 | 8 | 8 | 2 | 18 | 12.508 |  | 18
|  |  | PDR Power system | All power systems |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 10.6 | 8 | 8 | 2 | 18 | 12.508 |  | 18
|  |  | FDR D-Site | Transrex D-Site |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 10.6 | 8 | 8 | 2 | 18 | 12.508 |  | 18
|  |  | FDR C-Site | C-Site |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 10.6 | 8 | 8 | 2 | 18 | 12.508 |  | 18
|  |  | FDR Cabling | D site |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 10.6 | 8 | 8 | 2 | 18 | 12.508 |  | 18
|  |  | FDR Cabling | C site |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 10.6 | 8 | 8 | 2 | 18 | 12.508 |  | 18
|  |  | FDR DC transmission | D-site to C-site |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 10.6 | 8 | 8 | 2 | 18 | 12.508 |  | 18
|  |  | FDR AC auxiliaries & grounding | AC Auxiliaries power panels etc., grounding etc. |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 5; Design/ Procurement Dm: 5 | 10.6 | 8 | 8 | 2 | 18 | 12.508 |  | 18
|  |  | Calculations | Calculations - documentation |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 40; Design/ Procurement Dm: 1 | 51.416 | 8 | 8 | 2 | 18 | 60.6709 |  | 18
| 452 - Electrical Systems Support | 94.088 | 118.5509
|  |  | Diagnostics AC Power Distribution | Based on Input from Diagnostics WBS |  | 2004-09-30 | 2006-09-30 | 0.2 |  |  |  |  | 1 | racks | 1 | 1 |  | 0 | 10 | 80 | 10 | 10 | 80 |  | 5 | 10 | 20 | 36.89 | 16 | 8 | 2 | 26 | 46.4814 |  | 26
|  |  | Diagnostics sensor cabling | Based on Input from Diagnostics WBS |  | 2005-09-30 | 2006-09-30 | 0.2 |  |  |  |  | 10 | cables | 0.2 | 2 |  | 0 | 25 | 115 | 15 | 15 | 50 | 45 | 5 | 10 | 20 | 57.198 | 16 | 8 | 2 | 26 | 72.0695 |  | 26
| 46- FCPCBuilding Modifications | 54.607 | 68.8048
|  | 460-01 | Clear area in West wing from SPS cabinets to HVAC equipment (Elect) | Based on Input from Mech./construction |  | 2003-04-01 | 2003-10-01 | 0 |  |  |  |  | 1 | lot | 1 | 1 |  | 0 | Design/ Procurement EEEM: 8; Design/ Procurement Dm: 8; Installation EEEM: 2; Installation EESM: 2; Installation EETB: 12 | 0 | 16 | 8 | 2 |  | 0 |  | #DIV/0!
|  | 460-02 | Clear the small Vacuum prep lab | Based on Input from Mech./construction |  | 2003-04-01 | 2003-10-01 | 1 |  |  |  |  | 1 | lot | 0.5 | 0.5 |  | 0 | Installation EETB: 20 | 13.625 | 16 | 8 | 2 | 26 | 17.1675 |  | 26
|  | 460-03 | Mechanical Clearing | Based on Input from Mech./construction |  |  |  | 1 |  |  |  |  | 1 | lot | 2 | 2 |  | 0 | Design/ Procurement EEEM: 2; Design/ Procurement Dm: 2; Installation EEEM: 1; Installation EESM: 2; Installation EETB: 6 | 13.876 | 16 | 8 | 2 | 26 | 17.4838 |  | 26
|  | 460-04 | Floor & Wall Penetrations | Based on Input from Mech. (WBS-610) | 1 Wall penetration & 20 floor penetrations | 2004-02-01 | 2004-10-01 | 1 |  |  |  |  | 1 | lot | 5 | 5 |  | 0 | 1 | 2 | 1 | 2 | 14 | 4 |  |  |  | 27.106 | 16 | 8 | 2 | 26 | 34.1536 |  | 26
| 453 - System Testing | 186.01 | 219.4918
|  |  | Preop Testing |  |  |  |  | 1 | [7 empty] | 0 |  | 0 | [9 empty] | 0 |  |  |  |  | 0
|  |  |  | Test Equipment |  |  |  | 1 |  |  |  |  | 1 | lot | 25 | 25 |  | 0 | [9 empty] | 33.25 | 8 | 8 | 2 | 18 | 39.235 |  | 18
|  |  | Procedures PTPs, ISTPs | New Procedures |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 20; Design/ Procurement Dm: 20 | 42.4 | 8 | 8 | 2 | 18 | 50.032 |  | 18
|  |  |  | DC Circuit Hipots and Impedance Measurements |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 3; Commissioning EETB: 8 | 8.976 | 8 | 8 | 2 | 18 | 10.5917 |  | 18
|  |  |  | Electrical Interlock Testing |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 3; Commissioning EETB: 8 | 8.976 | 8 | 8 | 2 | 18 | 10.5917 |  | 18
|  |  |  | Kirk Key Interlock Testing |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 2; Commissioning EETB: 3 | 4.472 | 8 | 8 | 2 | 18 | 5.277 |  | 18
|  |  |  | Instrumentation Test & Calibration |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 2; Commissioning EETB: 2 | 3.824 | 8 | 8 | 2 | 18 | 4.5123 |  | 18
|  |  |  | Real Time Control System Testing |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 3; Commissioning EETB: 3 | 5.736 | 8 | 8 | 2 | 18 | 6.7685 |  | 18
|  |  |  | Coil Protection System Testing |  |  |  | 1 | [7 empty] | 0 |  | 0 | Design/ Procurement EEEM: 20; Commissioning EEEM: 3; Commissioning EETB: 3 | 31.016 | 8 | 8 | 2 | 18 | 36.5989 |  | 18
|  |  |  | Ground Fault Monitor Testing |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 2; Commissioning EETB: 2 | 0 | 8 | 8 | 2 |  | 0
|  |  |  | Coil Power Supply Dummy Load Testing |  |  |  | 1 |  |  |  |  | 10 | PS |  | 0 |  | 0 | Design/ Procurement EEEM: 0; Commissioning EEEM: 20; Commissioning EESM: 10; Commissioning EETB: 20 | 47.36 | 8 | 8 | 2 | 18 | 55.8848 |  | 18
|  |  |  | Trim Coil Power Supply Dummy Load Testing |  |  |  | 1 | [7 empty] | 0 |  | 0 | Commissioning EEEM: 10; Commissioning EETB: 10 | 0 | 8 | 8 | 2 |  | 0
|  |  | TOTALS | [12 empty] | 1158.585 |  | 45 | 724 | 988 | 221 | 278 | 741 | 539 | 130 | 107 | 259 | 5040.5291 | 760 | 720 | 176 | 1576 | 6053.8884 |  | 20.1042
IN MAN HOURS | [18 empty] | 5792 | 7904 | 1768 | 2224 | 5928 |  | 1040 | 856 | 2072
RATES | [14 empty] | M&S --> | 1158.585 | Spares--> | 45 | Installation EETB: SC -->; Installation SC: 539
|  |  | ron | raki | [23 empty] | ∑MD | Rate | $K | ∑FTE | Years | FTE/yr
EEEM | 1.264 | 0.984 | 1.264 | 1.2434 | [8 empty] | EEEM | 980 |  |  |  |  | Commissioning EESM: cross check; Commissioning EETB: EEEM | 1075 | 1.264 | 1358.8 | 4.8864 | 4 | 1.2216
EESM | 0.912 | 0.64 | 0.912 | 0.85729 | [8 empty] | EESM | 1060 |  |  |  |  | Commissioning EETB: EESM | 385 | 0.912 | 351.12 | 1.75 | 2 | 0.875
EETB | 0.648 | 0.64 | 0.648 | 0.62541 | [8 empty] | EEDM | 420 |  |  |  |  | Commissioning EETB: EETB | 1000 | 0.648 | 648 | 4.5455 | 2 | 2.2727
G&A (MHX) | 1.33 | 1.25 | 1.33 | 1.25 | [8 empty] | EETB | 1060 |  |  |  |  | Commissioning EETB: EADM | 988 | 0.856 | 845.728 | 4.4909 | 3 | 1.497
EADM | 0.856 |  | 0.856 | 0.88015 | [23 empty] | $K
[28 empty] | 539 | 1.33 | 716.87 | bar: Commissioning EETB
[19 empty] | Commissioning EETB: M&S | 1158.585 | 1.33 | 1540.9181
5461.4361
420.907
| 2001 rates |  | 2001 | 2002 | 2003 | [7 empty] | 2004 | Total MDs | Total k$
C. Neumeyer | 1.264 |  | 0 |  | 120 | [7 empty] | 0 | 120 | 151.68
Raki | 1.264 |  | 0 |  | 220 | [7 empty] | 0 | 220 | 200
R. Hatcher | 1.264 |  | 0 |  | 100 | [7 empty] | 0 | 100 | 126.4
R. Marsala | 1.264 |  | 0 |  | 120 | [7 empty] | 0 | 120 | 120
Mounir Awad | 1.264 |  | 0 |  | 100 | [7 empty] | 0 | 100 | 100
E.Baker | 1.264 |  | 0 |  | 120 | [7 empty] | 0 | 120 | 151.68
A. Ilic | 1.264 |  | 0 |  | 80 | [7 empty] | 0 | 80 | 101.12
P. Sichta | 1.264 |  | 0 |  | 80 | [7 empty] | 0 | 80 | 101.12
R. Parsells | 1.264 |  | 0 |  | 40 | [7 empty] | 0 | 40 | 50.56
Ray Gernhardt | 0.912 |  | 0 |  | 220 | [7 empty] | 0 | 220 | 200.64
D.McBride | 0.912 |  | 0 |  | 220 | [7 empty] | 0 | 220 | 200.64
Art Wise | 0.912 |  | 0 |  | 200 | [7 empty] | 0 | 200 | 182.4
Debonis | 0.912 |  | 0 |  | 200 | [7 empty] | 0 | 200 | 182.4
Freddie | 0.912 |  | 0 |  | 220 | [7 empty] | 0 | 220 | 200.64
J. Corl | 0.648 |  | 0 |  | 220 | [7 empty] | 0 | 220 | 142.56
Wes Reese | 0.648 |  | 0 |  | 220 | [7 empty] | 0 | 220 | 142.56
Marty | 0.648 |  | 0 |  | 220 | [7 empty] | 0 | 220 | 142.56
Collin | 0.648 |  | 0 |  | 200 | [7 empty] | 0 | 200 | 129.6
Techshop tech | 0.912 |  | 0 |  | 200 | [7 empty] | 0 | 200 | 182.4
van Kirk | 0.912 |  | 0 |  | 220 | [7 empty] | 0 | 220 | 200.64
Frank Jones | 0.912 |  | 0 |  | 100 | [7 empty] | 0 | 100 | 91.2
Nemi | 0.912 |  | 0 |  | 100 | [7 empty] | 0 | 100 | 91.2
| 4.2 | %
| 2 | % | [10 empty] | Raki, FYI your current estimate of $6.2m that I just calculated ,
de-escalates roughly to $5.27 in FY01$..Ron
raki rates
EEEM | 1.0504
EESM | 0.7088
EETB | 0.52
G&A | 1.25
Note on D14: This covers uninteruptible power for critical control and interlock systems and cryo system

## CDR - PDR COMPARISON
NCSX CD-2 Cost Baseline Update Reconciliation
WBS: 4 | Electrical Power Systems | 21
Manager: | Raki Ramakrishnan
|  | CDR Base |  |  |  |  | Revised Estimate |  |  |  |  | Delta's | [7 empty] | Delta's
|  | Estimate $ |  | Cont % | Cont $ | TOTAL $ | Estimate |  | Cont % | Cont $ | TOTAL $ |  | TOTAL $ |  | Cont | Cont % | NSTX w/Cntg |  | Comments
41- AC Power |  | 542 |  |  |  |  | 592.8956 | [5 empty] | 699.6168 |  | 180.5353 | 30.45% | 190
| 411 - Auxiliary AC Power |  | 499 | 17% | 84.83 | 583.83 |  | 475.7595 | 18% | 85.6367 | 561.3962 | -22.4338 |  | 570.8273 | 95.0678 | 19.98% |  | 169 | More work to ready C-site test cell and bring C-site infrastructure into operation, compared to D-site
| 412 - Experimental AC Power |  | 43 | 18% | 7.74 | 50.74 |  | 43.322 | 18% | 7.798 | 51.12 | 0.37996 |  | 128.7895 | 85.4675 | 197.3% |  | 21 | NSTX was underestimated
42 - AC/DC Converters |  | 14.5 |  |  |  |  | 26.1367 | [5 empty] | 30.8414 |  | 30.8414 | 118% | 41
| 421 - C-site AC/DC Converters |  | 0 | 0% | 0 | 0 |  | 0 | #DIV/0! | 0 | 0 | 0 |  | 0 | 0 | 0% |  |  | Not req'd for NSTX
| 422 - D-site AC/DC Converters |  | 14.5 | 18% | 2.61 | 17.11 |  | 0 | #DIV/0! | 0 | 0 | -17.11 |  | 30.8414 | 30.8414 | #DIV/0! |  | 41 | Approx equal
43 - DC Systems |  | 2395.449 |  |  |  |  | 3119.7109 | [5 empty] | 3732.8589 |  | 1488.1679 | 47.7% | 1154
| 431 - C-site DC Systems |  | 365.479 | 18% | 65.7862 | 431.2652 |  | 324.926 | 18% | 58.4867 | 383.4127 | -47.8525 |  | 456.3852 | 131.4592 | 40.46% |  | 0 | Not req'd for NSTX
| 432 - D-to-C-Site DC Systems |  | 1311.1 | 21.3% | 279.2643 | 1590.3643 |  | 1387.9268 | 23.85% | 331.0845 | 1719.0113 | 128.647 |  | 1916.3805 | 528.4537 | 38.08% |  | 0 | Not req'd for NSTX
| 433 - D-site DC Systems |  | 718.87 | 18% | 129.3966 | 848.2666 |  | 531.8382 | 18% | 95.7309 | 627.569 | -220.6976 |  | 1360.0932 | 828.2551 | 155.7% |  | 1154 | NCSX has more work per circuit but fewer circuits
44 - Control & Protection Systems |  | 1623.937 |  |  |  |  | 1565.4259 | [5 empty] | 1860.1072 |  | 393.4716 | 25.14% | 727
| 441 - Electrical Interlocks |  | 584.74 | 18.6% | 108.7616 | 693.5016 |  | 611.8756 | 18.59% | 113.7405 | 725.6161 | 32.1144 |  | 679.1534 | 67.2778 | 11% |  | 209 | NCSX system new, NSTX was modification of existing
| 442 - Kirk Key Interlocks |  | 96.4 | 18% | 17.352 | 113.752 |  | 96.732 | 18% | 17.4118 | 114.1438 | 0.39176 |  | 110.6858 | 13.9538 | 14.43% |  | 50 | NCSX requires interface between C-and D-sites
| 443 - Real Time Control |  | 39.63 | 18% | 7.1334 | 46.7634 |  | 37.92 | 18% | 6.8256 | 44.7456 | -2.0178 |  | 44.0176 | 6.0976 | 16.08% |  | 260 | NCSX is covered in different WBS
| 444 - Instrumentation |  | 607.84 | 12% | 72.9408 | 680.7808 |  | 432.498 | 18% | 77.8496 | 510.3476 | -170.4332 |  | 672.4144 | 239.9164 | 55.47% |  | 128 | NCSX system new, NSTX was modification of existing
| 445 - Coil Protection |  | 236.8 | 21.3% | 50.4384 | 287.2384 |  | 287.61 | 21.24% | 61.0778 | 348.6878 | 61.4494 |  | 353.836 | 66.226 | 23.03% |  | 80 | NCSX system new, NSTX was modification of existing
| 446 - Ground Fault Monitor |  | 58.527 | 18% | 10.5349 | 69.0619 |  | 166.6468 |  | 0 | 198.0235 | 128.9616 |  | #REF! | #REF! | #REF! |  |  | Not costed in NSTX baseline
45 - System Design and Integration |  | 1011.025 |  |  |  |  | 998.2616 | [5 empty] | 1218.8036 |  | 463.2896 | 46.41% | 784
| 451 - System Design |  | 378.4 | 18% | 68.112 | 446.512 |  | 475.416 | 18% | 85.5749 | 560.9909 | 114.4789 |  | 456.3183 | -19.0977 | -4.017% |  | 784 | NCSX design plus test approx equal to NSTX
| 452 - Electrical Systems Support |  | 466.935 | 26% | 121.4031 | 588.3381 |  | 94.088 | 26% | 24.4629 | 118.5509 | -469.7872 |  | 574.0006 | 479.9126 | 510.1% |  | 0 | NSTX was covered in different WBS
| 453 - System Testing |  | 165.69 | 18% | 29.8242 | 195.5142 |  | 186.01 | 18% | 33.4818 | 219.4918 | 23.9776 |  | 188.4847 | 2.4747 | 1.33% |  | 0 | In system design on NSTX
46 - FCPC Building Modifications |  | 5586.911 | 1e-05 |  |  | 1e-06 | #REF! | 54.607 | 26% | 14.1978 | 68.8048 | 68.8048 | #REF! |  | #REF! | #REF! | 2896
|  |  | 5586.911 |  | 1056.1275 | 6643.0385 |  | 5207.1759 |  | 1013.3594 | 6251.9119 | -391.1266 | 7542.2279 | #REF! | #REF! | #REF! | 2896 | 2896
[11 empty] | 6220.5353 | -391.1266
41- AC Power | 699.6168
42 - AC/DC Converters | 30.8414
43 - DC Systems | 3732.8589
44 - Control & Protection Systems | 1860.1072
45 - System Design and Integration | 1218.8036
Total w/ Contingency | 7542.2279

## .
|  | NCSX w/o Cntg |  | NCSX w/Cntg |  | Cont | Cont % | NSTX w/Cntg |  | Comments
41- AC Power |  | 519.0815 |  | 612.5162 |  | 93.4347 | 18% | 190
| 411 - Auxiliary AC Power |  | 475.7595 |  | 561.3962 | 85.6367 | 18% |  | 169 | More work to ready C-site test cell and bring C-site infrastructure into operation, compared to D-site
| 412 - Experimental AC Power |  | 43.322 |  | 51.12 | 7.798 | 18% |  | 21 | NSTX was underestimated
42 - AC/DC Converters |  | 0 |  | 0 |  | 0 | #DIV/0! | 41
| 421 - C-site AC/DC Converters |  | 0 |  | 0 | 0 | #DIV/0! |  |  | Not req'd for NSTX
| 422 - D-site AC/DC Converters |  | 0 |  | 0 | 0 | #DIV/0! |  | 41 | Approx equal
43 - DC Systems |  | 2244.691 |  | 2729.993 |  | 485.3021 | 21.62% | 1154
| 431 - C-site DC Systems |  | 324.926 |  | 383.4127 | 58.4867 | 18% |  | 0 | Not req'd for NSTX
| 432 - D-to-C-Site DC Systems |  | 1387.9268 |  | 1719.0113 | 331.0845 | 23.85% |  | 0 | Not req'd for NSTX
| 433 - D-site DC Systems |  | 531.8382 |  | 627.569 | 95.7309 | 18% |  | 1154 | NCSX has more work per circuit but fewer circuits
44 - Control & Protection Systems |  | 1633.2824 |  | 1941.5644 |  | 276.9053 | 16.95% | 727
| 441 - Electrical Interlocks |  | 611.8756 |  | 725.6161 | 113.7405 | 18.59% |  | 209 | NCSX system new, NSTX was modification of existing
| 442 - Kirk Key Interlocks |  | 96.732 |  | 114.1438 | 17.4118 | 18% |  | 50 | NCSX requires interface between C-and D-sites
| 443 - Real Time Control |  | 37.92 |  | 44.7456 | 6.8256 | 18% |  | 260 | NCSX is covered in different WBS
| 444 - Instrumentation |  | 432.498 |  | 510.3476 | 77.8496 | 18% |  | 128 | NCSX system new, NSTX was modification of existing
| 445 - Coil Protection |  | 287.61 |  | 348.6878 | 61.0778 | 21.24% |  | 80 | NCSX system new, NSTX was modification of existing
| 446 - Ground Fault Monitor |  | 166.6468 |  | 198.0235 | 31.3766 | 18.83% |  |  | Not costed in NSTX baseline
45 - System Design and Integration |  | 810.121 |  | 967.8384 |  | 133.2545 | 16.45% | 784
| 451 - System Design |  | 475.416 |  | 560.9909 | 85.5749 | 18% |  | 784 | NCSX design plus test approx equal to NSTX
| 46- FCPCBuilding Modifications |  | 54.607 |  | 68.8048 | 14.1978 | 26% |  | 0 | NSTX was covered in different WBS
| 453 - System Testing |  | 186.01 |  | 219.4918 | 33.4818 | 18% |  | 0 | In system design on NSTX
|  | 5207.1759 | 5113.0879 | 6251.9119 | 6133.361 | 1020.2731 | 19.95% | 2896 | 2896
41- AC Power | 612.5162
42 - AC/DC Converters | 0
43 - DC Systems | 2729.993
44 - Control & Protection Systems | 1941.5644
45 - System Design and Integration | 967.8384
Total w/ Contingency | 6251.9119