## Sheet1
WBS | ECP-04-005 Baseline | ECP-04-006 Estimate | Delta | Underestimate |  |  | Added Scope | TOTALS ADDED
|  |  |  | Re-Estimate of R&D Tasks | Revised M&S Estimate for Prototype Contracts | Re-Estimate of Analyses & Design Tasks | Coil Test Facility | w/o Contingency
111 - Limiters | 0.06 | 0.1 | 0.04 |  |  |  |  | 0.04
Subtotal WBS 11 | 0.06 | 0.1 | 0.04 | 0 | 0 | 0 | 0 | 0.04
121 - Vacuum Vessel Assembly | 5929 | 6260.287 | 331.287 | 43.75 | 212.537 | 75 |  | 331.287
122 - Vacuum Vessel Thermal Insulation | 174.9 | 174.9 | 0 |  |  |  |  | 0
123 - Vacuum Vessel Heating and Cooling Distrib | 375.8 | 375.8 | 0 |  |  |  |  | 0
124 - Vacuum Vessel Supports | 62.6 | 62.6 | 0 |  |  |  |  | 0
125 - Vacuum Vessel Local I&C | 26.7 | 26.7 | 0 |  |  |  |  | 0
Subtotal WBS 12 | 6569 | 6900.287 | 331.287 | 43.75 | 212.537 | 75 | 0 | 331.287
130 - General Conventional Coil Design | 407.1 | 460.09 | 52.99 |  |  | 52.99 |  | 52.99
131 - TF Coils | 1546.3 | 1546.3 | 0 |  |  |  |  | 0
132 - CS Solenoid/133-PF Ring Coils | 1747.4 | 1747.4 | 0 |  |  |  |  | 0
133 - External Trim Coils | 372 | 372 | 0 |  |  |  |  | 0
134 - Conventional Coil Local I&C | 85.5 | 85.5 | 0 |  |  |  |  | 0
Subtotal WBS 13 | 4158.3 | 4211.29 | 52.99 | 0 | 0 | 52.99 | 0 | 52.99
141 - Modular Coil Winding Form | 9171.9 | 9198.9 | 27 |  |  | 27 |  | 27
142 - Modular Coil Windings and Assembly | 8683.4 | 8683.4 | 0 |  |  |  |  | 0
143 - Modular Coil Local I&C | 121.2 | 121.2 | 0 |  |  |  |  | 0
144 - Modular Coil Winding Facility & Fixtures | 2283.4 | 2501.4 | 218 |  |  | 80 | 138 | 218
Subtotal WBS 14 | 20259.9 | 20504.9 | 245 | 0 | 0 | 107 | 138 | 245
151 - Coil Support Structure | 1435.9 | 1435.9 | 0 |  |  |  |  | 0
Subtotal WBS 15 | 1435.9 | 1435.9 | 0 | 0 | 0 | 0 | 0 | 0
161 - LN2 Distribution | 337.5 | 337.5 | 0 |  |  |  |  | 0
162 - Electrical Leads | 621.3 | 621.3 | 0 |  |  |  |  | 0
163 - Coil Protection System | 78.1 | 78.1 | 0 |  |  |  |  | 0
Subtotal WBS 16 | 1036.9 | 1036.9 | 0 | 0 | 0 | 0 | 0 | 0
171 -Cryostat | 858.5 | 858.5 | 0 |  |  |  |  | 0
172 - Base Support Structure | 438.2 | 438.2 | 0 |  |  |  |  | 0
Subtotal WBS 17 | 1296.7 | 1296.7 | 0 | 0 | 0 | 0 | 0 | 0
181 - Field Period Assembly Planning/Oversight | 1379.3 | 1379.3 | 0 |  |  |  |  | 0
182 - TFTR Test Cell Area preparations | 92.9 | 92.9 | 0 |  |  |  |  | 0
183 - Receive Inspect and Test Coils | 77.4 | 77.4 | 0 |  |  |  |  | 0
184 - Receive Inspect and Test VV | 326.3 | 326.3 | 0 |  |  |  |  | 0
185 - Assemble Field Periods | 1357.3 | 1357.3 | 0 |  |  |  |  | 0
186 - Tooling Design and Fabrication | 1341.5 | 1341.5 | 0 |  |  |  |  | 0
187 - Measurement Systems | 588.8 | 588.8 | 0 |  |  |  |  | 0
Subtotal WBS 18 | 5163.5 | 5163.5 | 0 | 0 | 0 | 0 | 0 | 0
191 - Stellarator Core Management & Oversight | 1083 | 1083 | 0 |  |  |  |  | 0
192 - Stellarator Core Integration & Analysis | 1581.6 | 1581.6 | 0 |  |  |  |  | 0
Subtotal WBS 19 | 2664.6 | 2664.6 | 0 | 0 | 0 | 0 | 0 | 0
21 - Fueling Systems | 140 | 140 | 0 |  |  |  |  | 0
Subtotal WBS 21 | 140 | 140 | 0 | 0 | 0 | 0 | 0 | 0
22 - Torus Vacuum Pumping Systems | 384.2 | 384.2 | 0 |  |  |  |  | 0
Subtotal WBS 22 | 384.2 | 384.2 | 0 | 0 | 0 | 0 | 0 | 0
25 - Neutral Beam Injection System | 1169.1 | 1169.1 | 0 |  |  |  |  | 0
Subtotal WBS 25 | 1169.1 | 1169.1 | 0 | 0 | 0 | 0 | 0 | 0
31 - Magnetic Diagnostics | 454.1 | 454.1 | 0 |  |  |  |  | 0
Subtotal WBS 31 | 454.1 | 454.1 | 0 | 0 | 0 | 0 | 0 | 0
36 - Edge and Divertor Diagnostics | 99.3 | 99.3 | 0 |  |  |  |  | 0
Subtotal WBS 36 | 99.3 | 99.3 | 0 | 0 | 0 | 0 | 0 | 0
38 - Electron Beam (EB) Mapping | 292.1 | 292.1 | 0 |  |  |  |  | 0
Subtotal WBS 38 | 292.1 | 292.1 | 0 | 0 | 0 | 0 | 0 | 0
39 - Diagnostics Integration | 847.2 | 847.2 | 0 |  |  |  |  | 0
Subtotal WBS 39 | 847.2 | 847.2 | 0 | 0 | 0 | 0 | 0 | 0
411 - Auxliary AC Power Systems | 569.3 | 569.3 | 0 |  |  |  |  | 0
412 - Experimental AC Power Systems | 42.8 | 42.8 | 0 |  |  |  |  | 0
Subtotal WBS 41 | 612.1 | 612.1 | 0 | 0 | 0 | 0 | 0 | 0
422 - D-Site AC/DC Converters | 23.5 | 23.5 | 0 |  |  |  |  | 0
Subtotal WBS 42 | 23.5 | 23.5 | 0 | 0 | 0 | 0 | 0 | 0
431 - C-Site DC Systems | 326.7 | 326.7 | 0 |  |  |  |  | 0
432 - D-to-C Site DC Systems | 1328.7 | 1328.7 | 0 |  |  |  |  | 0
433 - D-Site DC Systems | 487.9 | 487.9 | 0 |  |  |  |  | 0
Subtotal WBS 43 | 2143.3 | 2143.3 | 0 | 0 | 0 | 0 | 0 | 0
441 - Electrical Interlocks | 578.6 | 578.6 | 0 |  |  |  |  | 0
442 - Kirk Key Interlocks | 98 | 98 | 0 |  |  |  |  | 0
443 - Real Time Control Systems | 38.4 | 38.4 | 0 |  |  |  |  | 0
444 - Instrument Systems | 433.2 | 433.2 | 0 |  |  |  |  | 0
445 - Coil Protection Systems | 283.4 | 283.4 | 0 |  |  |  |  | 0
446 - Ground Fault Monitoring System | 167 | 167 | 0 |  |  |  |  | 0
Subtotal WBS 44 | 1598.6 | 1598.6 | 0 | 0 | 0 | 0 | 0 | 0
451 - System Design and Interfaces | 591.4 | 591.4 | 0 |  |  |  |  | 0
452 - Electrical Systems Support | 91.4 | 91.4 | 0 |  |  |  |  | 0
453 - System Testing (PTP's) | 192 | 192 | 0 |  |  |  |  | 0
Subtotal WBS 45 | 874.8 | 874.8 | 0 | 0 | 0 | 0 | 0 | 0
46 - FCPC Building Modifications | 78.6 | 78.6 | 0 |  |  |  |  | 0
Subtotal WBS 46 | 78.6 | 78.6 | 0 | 0 | 0 | 0 | 0 | 0
51 - TCP/IP Infrastructure Systems | 429 | 429 | 0 |  |  |  |  | 0
Subtotal WBS 51 | 429 | 429 | 0 | 0 | 0 | 0 | 0 | 0
52 - Central Instrumentation & Control | 578 | 578 | 0 |  |  |  |  | 0
Subtotal WBS 52 | 578 | 578 | 0 | 0 | 0 | 0 | 0 | 0
53 - Data Acquisition & Facility Computing | 407.8 | 407.8 | 0 |  |  |  |  | 0
Subtotal WBS 53 | 407.8 | 407.8 | 0 | 0 | 0 | 0 | 0 | 0
54 - Facility Timing & Synchronization | 352 | 352 | 0 |  |  |  |  | 0
Subtotal WBS 54 | 352 | 352 | 0 | 0 | 0 | 0 | 0 | 0
55 - Real Time Plasma & Power Supply Control Sys | 293.3 | 293.3 | 0 |  |  |  |  | 0
Subtotal WBS 55 | 293.3 | 293.3 | 0 | 0 | 0 | 0 | 0 | 0
56 - Central Safety Interlock Systems | 399.9 | 399.9 | 0 |  |  |  |  | 0
Subtotal WBS 56 | 399.9 | 399.9 | 0 | 0 | 0 | 0 | 0 | 0
57 - Control Room Facility | 119.7 | 119.7 | 0 |  |  |  |  | 0
Subtotal WBS 57 | 119.7 | 119.7 | 0 | 0 | 0 | 0 | 0 | 0
611 - C-Site Cooling System | 153.3 | 153.3 | 0 |  |  |  |  | 0
612 - NB Water Cooling Systems | 239.9 | 239.9 | 0 |  |  |  |  | 0
613 - Vacuum Pumping System | 100 | 100 | 0 |  |  |  |  | 0
614 - Bakeout Water System | 38.5 | 38.5 | 0 |  |  |  |  | 0
Subtotal WBS 61 | 531.7 | 531.7 | 0 | 0 | 0 | 0 | 0 | 0
621 - LN2-LHe Supply System | 252.9 | 252.9 | 0 |  |  |  |  | 0
622 - LN2 Coil Cooling Supply | 274.4 | 274.4 | 0 |  |  |  |  | 0
623 - 623 - GN2 Cryostat Cooling System | 220.2 | 220.2 | 0 |  |  |  |  | 0
Subtotal WBS 62 | 747.5 | 747.5 | 0 | 0 | 0 | 0 | 0 | 0
63 - Utility Systems | 120.9 | 120.9 | 0 |  |  |  |  | 0
Subtotal WBS 63 | 120.9 | 120.9 | 0 | 0 | 0 | 0 | 0 | 0
64 - PFC/VV Heating & Cooling | 628.9 | 628.9 | 0 |  |  |  |  | 0
Subtotal WBS 64 | 628.9 | 628.9 | 0 | 0 | 0 | 0 | 0 | 0
65 - Facility Systems Integration | 41.6 | 41.6 | 0 |  |  |  |  | 0
Subtotal WBS 65 | 41.6 | 41.6 | 0 | 0 | 0 | 0 | 0 | 0
71 - Shield Wall Reconfiguration | 32.2 | 32.2 | 0 |  |  |  |  | 0
Subtotal WBS 71 | 32.2 | 32.2 | 0 | 0 | 0 | 0 | 0 | 0
72 - Control Room Refurbishment | 47.6 | 47.6 | 0 |  |  |  |  | 0
Subtotal WBS 72 | 47.6 | 47.6 | 0 | 0 | 0 | 0 | 0 | 0
73 - Platform Design & Fabrication | 159.6 | 159.6 | 0 |  |  |  |  | 0
Subtotal WBS 73 | 159.6 | 159.6 | 0 | 0 | 0 | 0 | 0 | 0
741 - Planning Prior to Machine Assembly | 430 | 430 | 0 |  |  |  |  | 0
742 - Construction Management | 1184.2 | 1184.2 | 0 |  |  |  |  | 0
Subtotal WBS 74 | 1614.2 | 1614.2 | 0 | 0 | 0 | 0 | 0 | 0
75 - Test Cell and Basement Assembly Operations | 2160 | 2160 | 0 |  |  |  |  | 0
Subtotal WBS 75 | 2160 | 2160 | 0 | 0 | 0 | 0 | 0 | 0
76 - Tooling Design & Fabrication | 223.7 | 223.7 | 0 |  |  |  |  | 0
Subtotal WBS 76 | 223.7 | 223.7 | 0 | 0 | 0 | 0 | 0 | 0
77 - Measurement Systems | 0 | 0 | 0 |  |  |  |  | 0
Subtotal WBS 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 - Project Management and Control | 3354.3 | 3354.3 | 0 |  |  |  |  | 0
Subtotal WBS 81 | 3354.3 | 3354.3 | 0 | 0 | 0 | 0 | 0 | 0
82 - Project Engineering | 4723.1 | 4723.1 | 0 |  |  |  |  | 0
Subtotal WBS 82 | 4723.1 | 4723.1 | 0 | 0 | 0 | 0 | 0 | 0
84 - Project Physics | 507.7 | 507.7 | 0 |  |  |  |  | 0
Subtotal WBS 84 | 507.7 | 507.7 | 0 | 0 | 0 | 0 | 0 | 0
85 - Integrated Systems Testing | 1225 | 1225 | 0 |  |  |  |  | 0
Subtotal WBS 85 | 1225 | 1225 | 0 | 0 | 0 | 0 | 0 | 0
AA - PPPL Allocations | 983.3 | 983.3 | 0 |  |  |  |  | 0
Subtotal Allocations | 983.3 | 983.3 | 0 | 0 | 0 | 0 | 0 | 0
CC - Contingency | 15350.8 | 14721.5 | -629.3 | -43.8 | -212.5 | -235 | -138 | -629.3
Subtotal Contingency | 15350.8 | 14721.5 | -629.3 | -43.8 | -212.5 | -235 | -138 | -629.3
Totals | 86336.56 | 86336.577