## Sheet1
| ECP 04-006 analysis by FPD (April 27, 2004) | Contingency | Mgmt Reserve
WBS 121 | New scope - required by finalization of port configuration | 75000
| New scope - weld joint prototyping requirements | 44000
| New scope - vendor prototype fabrication processes/requirements | 213000
WBS 130 | New scope - analysis and testing of revised conductor insulation scheme | 53000
WBS 141 | Changes to MWCF due to port configuration changes (see WBS 121) | 27000
WBS 142 | Re-estimate of design requirements for twisted racetrack |  | 9000
| Re-estimate of design requirements for straight section |  | 70000
| Re-estimate of design requirements for winding details |  | 71000
| Overtime requirements |  | 20000
WBS 144 | New scope - coil test facility personnel and equipment protection | 80000
| New scope - coil test facility N2 loop & NSTX fault protection | 138000
| Overtime requirements |  | 20000
WBS 192 | Re-estimate of analysis requirements for coil center details |  | 20000
WBS 81 | Re-estimate of Project Management & Control requirements |  | 170000
| Breakdown of proposed &1.01M ECP 04-004 | 630000 | 380000