## Sheet1
Task No. | Title | Gernhardt | McBride | Gettelfinger | EADD | EMTB | Delany | Marsala | Gibney | Herskwoitz | M&S (Direct)
Original Job
1409-029 | Oversight/Supervision | 28 | 80 | 280
1409-026 | Install Electrical (Powers) | [9 empty] | 95.2
1409-025 | Design Test Stand |  |  |  | 240
1409-025 | Design Test Stand ETC |  |  |  | 269
1409-027 | Cryo Lline Installation |  |  |  |  | 120 | 70 |  |  |  | 9
1409-028 | System Testing |  |  | 80 |  | 65
1409-030 | Generate I2T Requirements |  |  | 16
1409-032 | Design I2T Protection | [6 empty] | 40
1409-034 | Fabricate I2T Cards |  |  |  |  | 120 |  |  | 30
1409-036 | Define N2 Ejection System |  |  | 16
1409-038 | Plan/Procure N2 Ejection System
1409-040 | Install N2 Ejection System | [9 empty] | 10 | P&H Ducting
1409-042 | Peer Review for Facility
1409-044 | Final Design Review for Facility
1409-046 | Declare Facility Available
1409-110 | ES&H Peer Review
1409-100 | Design Control Modifications | 92 |  | 60 |  |  |  | 180
1409-120 | Install Control Modifications |  |  |  |  | 160
1409-125 | Controls Peer Review
1409-140 | Design Closed Loop N2 System
1409-130 | Cryostat Design (Specimen Shroud) |  |  | 40
1409-145 | Closed Loop N2 System Peer Review
1409-150 | Proc Matls./Pump/Closed Loop N2 | [9 empty] | 15
1409-155 | Fab/Instl Closed Loop N2 System | [5 empty] | 120
1409-135 | Fab/Instl Cryostat Shroud |  |  |  |  | 120 |  |  |  |  | 10
1409-160 | Test Closed Loop N2 System | [8 empty] | 40
1409-165 | Closed Loop N2 Facility Available
Totals |  | 120 | 80 | 492 | 509 | 585 | 190 | 220 | 30 | 40 | 139.2
Spent Through March |  |  |  | 167 | 240 | 55.7 |  |  |  |  | 99.86
ETC (April-July) |  | 120 | 80 | 325 | 269 | 529.3 | 190 | 220 | 30 | 40 | 39.34
Note: Revised figures discussed and agreed to my A. vonHalle & G. Gettelfinger
Original ECP-006 ETC |  | 292 | 120 | 365 | 269 | 605 | 190 | 392 | 120 | 40 | 39.3
| Delta | -172 | -40 | -40 | 0 | -75.7 | 0 | -172 | -90 | 0 | 0.04