## Sheet1
ECP-6
Cost Summary
WBS Level 3 | Job | Description | Justification | Increase (includes applicable overhead) | comments
121 | 1202 | Vac Vessel R&D Field Weld Joint | add'l cost to procure full size sample | 43750
121 | 1202 | Vac Vessel Prototype Fabrication | Increased cost for Major Tool | 85010
121 | 1202 | Vac Vessel Prototype Fabrication | Increased cost for Rohwedder | 127527
121 | 1203 | Vac Vessel Final Design | Port Location studies, extra drawings | 75000
130 | 1301 | Conventional coil design | Material property analysis & testing | 52990
141 | 1403 | MCWF final design | shell modifications for more ports | 27000
142 | 1403 | Winding design and R&D | analysis, winding details | 150000
142 | 1406 | Coil winding R&D | unplanned overtime (premium only) | 20000
144 | 1407 | Winding facility fabrication & setup | unplanned overtime (premium only) | 20000
144 | 1409 | Coil Test Stand |  |  | was $262,170
192 | 1901 | Stellarator core integration | Coil winding center determination analysis | 20000
810 | 8101 | Project management | Increase level of project controls | 97000
810 | 8101 | Project management | Increase level of engineering support | 56500
810 | 8101 | Project management | Increase level of administrative support | 16000
790777