| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Bob Simmons | Date: Draft A - May 6, 2004 |
| ECP No: 04-008 | ECP Title: New Port Configuration |
| Required Reviewers |
| Required Reviewers for this ECP: Stellarator and Ancilary Systems Project Engineers, NCSX Project Control Manager, NCSX Engineering Manager |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Update technical,cost, and schedule baselines Update WAFs to reflect the new detailed costs and schedules Report status against these revised baselines, starting with the July statusing Update DOE PARS as necessary to reflect this information |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: Draft A – May 6, 2004 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: A significant revision to the vacuum vessel port configuration, including the net addition of 33 new ports, was necessary to meet the requirements for heating and diagnostics access. ECP-04-006 previously incorporated the impact of these changes on the design costs. This ECP addresses the changes to the technical baseline and the fabrication and assembly cost impacts. Impacted WBS Elements: WBS 12 (Vacuum Vessel), WBS 13 (Conventional Coils), WBS 14 (Modular Coils), WBS 171 (Cryostat), WBS 18 (Field Period Assembly), and WBS 75 (Machine Assembly). Impacts of Change (Briefly Describe): The major impact will be on the vacuum vessel. Other impacts will involve modifications to the coils and the cryostat to avoid interferences with the port extensions. This ECP only includes the first set of port extensions that extend just outside the modular coil shell. ??Please clarify, since I thought (perhaps incorrectly) we were keeping the removable extensions, all the way out through the cryostat. The following ports are impacted by the addition of additional smaller ports: NBI Duct - The configuration has changed slightly. Port 3 – 3 additional ports (4 inch o.d.) Port 9 – 6 additional ports (6 inch o.d.) Port 10 – 6 smaller, round ports (10 inch o.d.) replacing larger oblong ports Port 15 – 6 additional ports (4 inch o.d.) Port 16 – 6 additional ports (2 inch o.d.) Port 17 – 6 additional ports (4. inch o.d.) Port 18 – 6 additional ports (4 inch o.d.) As a result of the above changes, it is proposed to draw down contingency by approximately $300K from $14,720K to $14,420K. Assessment of Other Options: Consideration was given to expanding existing port structure and configuration What does this mean?, but this proved infeasible. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: Draft A – May 6, 2004 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. Attachment 1 – Detailed Breakdown of Cost Impacts Attachment 2 – Updated ECP-04-008 Barcharts Attachemnt 3 – List of Impacted Drawings Description of Change: This DRAFT A only addresses the technical, cost and schedule impacts on the VVSA (WBS 121). Impacts on the other WBS elements is still be assessed. WBS 121 (Vacuum Vessel Assembly) Technical Impacts: This ECP will result in creating an additional 27 penetrations and port extensions on the VVSA shell. These new extensions will only protrude through the modular coil shell; the second part of the extensions from just outside the modular coil shell will be deferred until such time that diagnostics identifies a need. Accordingly, these new ports will be blanked off until such time that they are needed. Cost impact: Port 3 – 3 additional ports (4 inch o.d.) - $10K cost increase for each additional port (+$30K) Port 9 – 6 additional ports (6 inch o.d.) - $10K cost increase for each additional port (+$60K) Port 10 – six smaller, round ports (10 inch o.d.) - $5K cost reduction for each modified port (-$30K) Port 15 – 6 additional ports (4 inch o.d.) - $10K cost increase for each additional port (+$60K) Port 16 – 6 additional ports (2 inch o.d.) - $10K cost increase for each additional port (+$60K) Port 17 – 6 additional ports (4. inch o.d.) - $10K cost increase for each additional port (+$60K) Port 18 – 6 additional ports (4 inch o.d.) - $10K cost increase for each additional port (+$60K) Schedule Imapct: TBD WBS 13 (Conventional Coils) - TBD WBS 142 (Modular Coil Windings and Assembly) - TBD WBS 171 (Cryostat) - TBD WBS 18 (Field Period Assembly) - TBD WBS 75 (Machine Assembly) - TBD |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: | Date: |
| Continuation Sheet: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) |