| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Bob Simmons | Date: June 21, 2004 |
| ECP No: 04-008 | ECP Title: Update of Technical Baseline to Reflect VVSA and MCWF FDR Design Configuration |
| Required Reviewers |
| Required Reviewers for this ECP: Stellarator and Ancilary Systems Project Engineers, NCSX Project Control Manager, NCSX Engineering Manager |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Update technical, cost, and schedule baselines Update WAFs to reflect the new detailed costs and schedules Report status against these revised baselines, starting with the July statusing Update DOE PARS as necessary to reflect this information |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: June 21, 2004 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: New Scope - Revised design configurations for the VVSA and MCWF were presented at the VVSA and MCWF FDR held May 19-20, 2004. This ECP updates the performance baselines to reflect the FDR configuration. The activities added represent entirely new scope. Reprogrammed Scope - The Project has made the decision to eliminate several scope items and to reprogram that budget to existing activities where experience has demonstrated that the planned budget is inadequate. Impacted WBS Elements: New Scope - WBS 12 (Vacuum Vessel), WBS 14 (Modular Coils), and WBS 18 (Field Period Assembly). Reprogrammed Scope: WBS 14 (Modular Coils), WBS 18 (Field Period Assembly), [IDENTIFY WHERE BUDGET FROM WBS 14 & WBS 18 WILL GO] Impacts of Change (Briefly Describe): (1) New Scope - The major scope change in the VVSA design configuration was the net addition of 27 new ports. These ports were added to meet the requirements for heating and diagnostic access. The additional design scope associated with this change was addressed in an earlier ECP. As a result of the above changes, it is proposed to draw down contingency by approximately $540K from $14,720K to $14,180K. In addition, since much of this new scope and reprogrammed work is FY2004 work, start of non-critical path systems will be deferred until FY2005. At this time WBS 15 structures design will be deferred to begin in early FY2005. (2) Reprogrammed Scope – net impact is $0K as budget from eliminated scope activities are reprogrammed to existing scope activities. Assessment of Other Options: Studies were conducted that considered adding fewer than 27 ports and adding more ports (up to 45). Due to port structural considerations, the higher number was rejected. The final selection of 27 new ports provided adequate diagnostic flexibility. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: June 21, 2004 |
| Detailed Description of the Change: List Attachments, Impacted Documents, etc. Attachment 1 – Detailed Breakdown of Cost Impacts Attachment 2 – Updated ECP-04-008 Bar Charts Description of Change: The following items provide details of the components making up this ECP: Scope Increases +$540K WBS 121 (Vacuum Vessel Assembly) Technical Impacts: This ECP will result in creating an additional 27 penetrations and port extensions on the VVSA shell. These new extensions will only protrude through the modular coil shell. A second set of stainless steel extensions are included from the inconel/stainless steel extension transition joint through the cryostat. The current configuration for these extensions are circular, but the configuration of these port extensions may have to be modified slightly later when the exact diagnostic configuration requirements are determined. Cost impacts: Addition of 27 new ports (+$240K) Port 3 – 3 additional ports (4 inch o.d.) - $10K cost increase for each additional port (+$30K) Port 9 – 6 additional ports (6 inch o.d.) - $10K cost increase for each additional port (+$60K) Port 10 – 6 smaller, round ports (10 inch o.d.) - $5K cost reduction for each modified port (-$30K) Port 15 – 6 additional ports (4 inch o.d.) - $10K cost increase for each additional port (+$60K) Port 17 – 6 additional ports (4. inch o.d.) - $10K cost increase for each additional port (+$60K) Port 18 – 6 additional ports (4 inch o.d.) - $10K cost increase for each additional port (+$60K) Addition of stainless steel port extensions on those ports not already extending through the cryostat (+$150K) Schedule Impact: None. WBS 141 – Modular Coil Winding Form Technical Impact: The MCWF manufacturing developing and prototype fabrication effort was revised to include the padding, flow solidification analysis, pattern making, and casting of an additional prototype reflecting the final design configuration. The technical impact of the change is that it provides early identification of any casting-related problems with the final design configuration, reducing associated risks during the production phase. Cost Impact: The only cost impact will be the incremental cost of having a second supplier work on a MCWF prototype through the point of making a pattern for casting. (+ $75K). |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: – June 21, 2004 |
| Schedule Impact: The prototype casting should be useable as a production article. Initiating this work during the manufacturing development and prototype fabrication phase accelerates delivery of the first casting by 1-2 months. Since this is a critical path activity, the project schedule contingency would be increased by the same amount. WBS 18 (Field Period Assembly) Technical Impact: The addition of the 27 new ports will necessitate a greater than planned effort to weld on those ports. . Cost Impacts: Additional welding of new ports (+$75K) Schedule Impact: None Reprogramming ($0K Net Change) Activities Eliminated WBS 142 (Modular Coil Windings and Assembly) - Due to the additional R&D activities planned for the latter third of FY2004 that will include winding characterization and winding of a twisted racetrack coil, the need to wind a full-size prototype winding is no longer necessary. Elimination of the full-size prototype winding activities: (-$265K). WBS 18 (Field Period Assembly) – The Project has made the decision to use the first article for field period assembly practice with the assembly fixture vs. doing this with a full-scale assembly mockup. Elimination of the full scale assembly mockups: (-$199K) Reprogrammed Activities – based on experience to date, it is evident that some existing activities were inadequately budgeted. The Project has made the decision to reprogram the budget from the eliminated activities described above to the following existing activities: RON WILL PROVIDE THIS LIST |