| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Bob Simmons | Date: Draft C1 – June 10, 2004 |
| ECP No: 04-008 | ECP Title: Update of Technical Baseline to Reflect VVSA and MCWF FDR Design Configuration |
| Required Reviewers |
| Required Reviewers for this ECP: Stellarator and Ancilary Systems Project Engineers, NCSX Project Control Manager, NCSX Engineering Manager |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Update technical,cost, and schedule baselines Update WAFs to reflect the new detailed costs and schedules Report status against these revised baselines, starting with the July statusing Update DOE PARS as necessary to reflect this information |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: Draft C1 – June 10, 2004 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: The design configuration of the VVSA and MCWF was changed as a result of the VVSA and MCWF FDR held May 19-20, 2004. This ECP addresses the design configuration changes, recognizes some cost growth of those activities leading up to and following the FDR, and updates the design scope to reflect deletion of several activities no longer deemed necessary. Impacted WBS Elements: WBS 12 (Vacuum Vessel), WBS 14 (Modular Coils), WBS 18 (Field Period Assembly), and WBS 82 (Design Integration). Impacts of Change (Briefly Describe): The major scope change in the VVSA design configuration was the net addition of 33 new ports. These ports were added to meet the requirements for heating and diagnostic access. The additional design scope associated with this change was addressed in an earlier ECP. In addition, this ECP recognizes some actual and projected cost growth in the modular coil design and analyses efforts, the modular coil winding R&D, and in the design integration effort. Offsetting this cost growth was the determination that several specific scope items that were included in the original baseline effort are no longer needed since other existing and planned activities will achieve those stated goals. In addition, since much of this cost growth is FY2004 work, start of some non-critical path activities (e.g., design of stellarator structures, etc.) were deferred until FY2005. As a result of the above changes, it is proposed to draw down contingency by approximately $810K from $14,720K to $13,910K. Assessment of Other Options: Studies were conducted that considered adding fewer than 33 ports and adding more ports (up to 45). Due to port structural considerations, the higher number was rejected. The final selection of 33 new ports provided maximum diagnostic flexibility. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: Draft C1 – June 10, 2004 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. Attachment 1 – Detailed Breakdown of Cost Impacts Attachment 2 – Updated ECP-04-008 Barcharts Attachment 3 – List of Impacted Drawings Description of Change: The following items provide details of the components making up this ECP: WBS 121 (Vacuum Vessel Assembly) Technical Impacts: This ECP will result in creating an additional 33 penetrations and port extensions on the VVSA shell. These new extensions will only protrude through the modular coil shell. A second set of stainless steel extensions are included from the inconel/stainless steel extension transition joint through the cryostat. The current configuration for these extensions are circular, but the configuration of these port extensions may have to be modified slightly later when the exact diagnostic configuration requirements are determined. Cost impact: Addition of 33 new ports - $300K Port 3 – 3 additional ports (4 inch o.d.) - $10K cost increase for each additional port (+$30K) Port 9 – 6 additional ports (6 inch o.d.) - $10K cost increase for each additional port (+$60K) Port 10 – 6 smaller, round ports (10 inch o.d.) - $5K cost reduction for each modified port (-$30K) Port 15 – 6 additional ports (4 inch o.d.) - $10K cost increase for each additional port (+$60K) Port 16 – 6 additional ports (2 inch o.d.) - $10K cost increase for each additional port (+$60K) Port 17 – 6 additional ports (4. inch o.d.) - $10K cost increase for each additional port (+$60K) Port 18 – 6 additional ports (4 inch o.d.) - $10K cost increase for each additional port (+$60K) Addition of 33 new stainless steel port extensions - $150K Schedule Impact: None. WBS 141 (Modular Winding Form) Technical Impact: The development of the final design of the modular coil winding form required greater than planned design and analysis effort to arrive at a self-consistent design that addressed all the design challenges. Cost Impact: Additional design and analysis tasks - $498K Schedule Impact: None. Additional resources applied to maintain FDR schedule. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: Draft C1 – June 10, 2004 |
| Continuation Sheet: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) WBS 142 (Modular Coil Windings and Assembly) Technical Impact: Additional winding R&D activities, including winding characterization and winding of prototypical coils were deemed necessary to prove out the winding techniques and conductor material properties. However, due to this additional work, it was determined that the need to wind a full-size prototype winding was no longer necessary.. Cost Impacts: Additional modular coil R&D efforts - $260K Elimination of the full-size prototype winding activities – ($265K) Schedule Impact: None WBS 18 (Field Period Assembly) Technical Impact: The addition of the 33 new ports will necessitate a greater than planned effort to weld on those ports. However, due to the additional winding R&D, it was felt that the need for full-scale mockups for assembly practice could be eliminated. In addition, as a result of the excellent results being obtained using the laser tracker, it was determined that the need for a GPS metrology system could be eliminated. Cost Impacts: Additional welding of new ports - $75K Elimination of the procurement of a full-scale assembly mockup – ($160K) Elimination of the GPS metrology system – ($130K) Schedule Impact: TBD WBS 82 (Systems Engineering) Technical Impact: Development of a self-consistent final design of the VVSA and MCWF required more effort than originally planned. This merely reflect recognition of this cost growth in the design integration effort. Cost Impact: Greater than anticipated design integration effort - $80K Schedule Impact: None ITEMS NEEDING RESOLUTION BY TIME OF CCB ON JUNE 18TH. Need cost estimate backup details for: Additional modular coil R&D efforts (Chrzanowski/Nelson) Additional welding of new ports (Chrzanowski) Need schedule impact assessment for: Impact on overall schedule of eliminating the full-scale assembly mockups and how the delivery of the MCWF needs to be revised to permit timely arrival of each MCWF type to permit use vs. full-scale assembly mockup (Heitzenroeder/Chrzanowski) |