| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Bob Simmons | Date: June 22, 2004 |
| ECP No: 04-009 | ECP Title: Reprogramming |
| Required Reviewers |
| Required Reviewers for this ECP: Stellarator Project Engineer, NCSX Project Control Manager, and NCSX Project Engineer |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Update technical, cost, and schedule baselines Update WAFs to reflect the new detailed costs and schedules Report status against these revised baselines, starting with the July statusing Update DOE PARS as necessary to reflect this information |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: June 22, 2004 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: The Project has made the decision to eliminate several scope items and to reprogram that budget to existing activities where added work is planned. Experience to date has demonstrated that the anticipated scope for these existing activities is more complex and that resources needed are greater than originally planned. Impacted WBS Elements: WBS 14 (Modular Coils), WBS 18 (Field Period Assembly), WBS 81 (Project Management and Control), and WBS 82 (Engineering Management and Systems Engineering Support) Impacts of Change (Briefly Describe): The net impact is $0K as budget from eliminated scope activities are reprogrammed to existing scope activities. Assessment of Other Options: The Project assessed the performance to date in several critical activities and determined that these activities were inadequately budgeted. These activities were the ones that received reprogrammed budget from eliminated activities. Detailed Description of the Change: List Attachments, Impacted Documents, etc. Attachment 1 – Detailed Breakdown of Cost Impacts Attachment 2 – Updated ECP-04-008 Bar Charts Description of Change: The following items provide details of the components making up this ECP: Reprogramming ($0K Net Change) Activities Eliminated WBS 142 (Modular Coil Windings and Assembly) - Due to the additional R&D activities planned for the latter third of FY2004 that will include winding characterization and winding of a twisted racetrack coil, the need to wind a full-size prototype winding is no longer necessary. Elimination of the full-size prototype winding activities: (-$265K). WBS 18 (Field Period Assembly) – The Project has made the decision to use the first article for field period assembly practice with the assembly fixture vs. doing this with a full-scale assembly mockup. Elimination of the full scale assembly mockups: (-$199K) |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: – June 22, 2004 |
| Reprogrammed Activities – based on experience to date, it is evident that some ongoing activities will require more effort to complete. The Project has made the decision to reprogram the budget from the eliminated activities described above to the following existing activities: WBS 142 (Modular Windings and Assembly) – additional resources needed to complete the twisted racetrack R&D program and to complete the design and assembly of the modular coil winding facility: (+$160K). WBS 81 (Project Management and Control) – additional resources needed to support the award of the VVSA and MCWF production contracts and additional project control effort: (+$113K). WBS 82 (Engineering Management and Systems Engineering Support) – additional resources needed in the Design Integration and Systems Analysis efforts: (+$147K) Miscellaneous WBS Elements – the above efforts are all in FY2004, it was necessary to defer some non-critical activities until FY2005 (e.g., WBS 15 –design of stellarator structures) and to make minor accounting adjustments. The net impact of these numerous minor adjustments is approximately (+$44K). |