| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Bob Simmons |  |  | Date: July 8, 2004 |  |
| ECP No: 04-009 |  | ECP Title: Reprogramming |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: Stellarator Project Engineer, NCSX Project Control Manager, and NCSX Project Engineer |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |  |  |  |  |
| Actions - Update technical, cost, and schedule baselines - Update Performance Measurement Baseline (PMB) to reflect the new detailed costs and schedules - Report status against these revised baselines, starting with the June WAF statusing |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Under Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Bob Simmons | Date: July 8, 2004 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: The Project has made the decision to eliminate several scope items and to reprogram that budget to existing activities where added work is planned. Experience to date has demonstrated that the anticipated scope for these existing activities is more complex and that resources needed are greater than originally planned. Impacted WBS Elements: WBS 14 (Modular Coils) and WBS 18 (Field Period Assembly) Impacts of Change (Briefly Describe): The net impact is $0K as budget from eliminated scope activities are reprogrammed to existing scope activities. Assessment of Other Options: The Project assessed the performance to date in several critical activities and determined that these activities were inadequately budgeted. These activities were the ones that received reprogrammed budget from eliminated activities. Detailed Description of the Change: List Attachments, Impacted Documents, etc. Attachment 1 – Detailed Breakdown of Cost Impacts Attachment 2 – Updated ECP-04-009 Bar Charts Description of Change: The following items provide details of the components making up this ECP: Reprogramming ($0K Net Change) - Activities Eliminated - WBS 142 (Modular Coil Windings and Assembly) - Due to the additional R&D activities planned for the latter third of FY2004 that will include winding characterization and winding of a twisted racetrack coil, the need to wind a full-size prototype winding is no longer necessary. Elimination of the full-size prototype winding activities: (-$261.7K). - WBS 18 (Field Period Assembly) – The Project has made the decision to use the first article for field period assembly practice with the assembly fixture vs. doing this with a full-scale assembly mockup. Elimination of the full scale assembly mockups: (-$196.4K) |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Bob Simmons | Date: – July 8, 2004 |
| - Reprogrammed Activities – based on experience to date, it is evident that some ongoing activities will require more effort to complete. The Project has made the decision to reprogram the budget from the eliminated activities described above to the following Modular Coil activities: - WBS 141 (Modular Coil Winding Forms) - Completion of the production Modular Coil Winding Form models and drawings to support the production MCWF procurement (+$77.2K) - WBS 142 (Modular Windings and Assembly) - Completion of the Modular Coil Analyses activities (+$300.6K) - Twisted Racetrack winding design activities (+ 50.7K) In addition, in order to provide sufficient FY2004 funding at ORNL to accommodate the above reprogrammed near term activities, the non-critical path tooling design efforts for the field period assembly (WBS 185) have been deferred until FY2005. This has a cost impact of $29.6K due to escalation. - Summary Affected WBS Element; Eliminated Tasks; Re-Estimated Tasks; Net Change. WBS 141 – Mod Coils Winding Forms; --; +$77.2K; +$77.2K. WBS 142 – Mod Coils Windings & Assembly; -$261.7K; +$351.3K; +$89.6K. WBS 185 – Field Period Assembly; -$196.4K; $29.6K; -166.7K. TOTALS; -$458.1K; +$458.1K; $0K. |