| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Hutch Neilson | Date: July 30, 2004 |
| ECP No: 04-011 | ECP Title: Re-Baseline WBS 14 Modular Coils |
| Required Reviewers |
| Required Reviewers for this ECP: Stellarator Core (WBS 1) Project Engineer, WBS 14 Manager, Project Control Manager |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Update technical,cost, and schedule baselines Update WAFs to reflect the new detailed costs and schedules Report status against these revised baselines, starting with the July statusing Update DOE PARS as necessary to reflect this information |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: Draft C1 – June 10, 2004 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: WBS 14 Modular Coils is being rebaselined following completion of Title II design of the modular coil winding forms (MCWF) with the release for fabrication of the CAD models, PDF drawings, and specifications on July 20-21, 2004. 1) Past cost and schedule variances driven by MCWF Title II design are being eliminated. With the completion of MCWF Title II design, the associated risks are now retired, so it is appropriate to cover the variances in 3 MCWF design and R&D jobs with contingency. 2) The work in WBS 14 from now to the next major critical-path milestone, start of production coil winding, has been planned in greater detail (to Level IV). Changes have been made in detailed schedules and job budgets in order keep the critical path on schedule and provide adequate budget for the planned work scope. Though the work scope has been reduced to the minimum, the estimated costs have increased as a result of detailed planning and better understanding of the design challenges, number of drawings required, fabrication challenges, and testing/analysis needs that has been gained through the work to date. Impacted WBS Elements: WBS 14 (Modular Coils) Impacts of Change (Briefly Describe): Past cost and schedule variances driven by MCWF Title II design, now complete, are being covered with $700k of contingency. The performance measurement baseline for future work in WBS 14 is being expanded in detail and revised to be consistent with updated plans. Contingency of $839k is being requested to cover increases in estimates for future work in WBS 14 jobs. As a result of the above changes, it is proposed to draw down contingency by $1,539K from $14,180K to $12,641K. Assessment of Other Options: The updated plan reflects growth in cost and schedule estimates for certain tasks, but also scope reductions (some already captured in ECP-04-009) and optimizations which keep the critical path on schedule with minimum cost growth. Failure to provide realistic design and R&D budgets based on improved understanding of the difficulties would risk variances in the next phase and would constitute a failure to learn from past problems. Any further reductions in work scope preparatory to winding the production coils would introduce unacceptable cost and schedule risks in the following phase, fabrication of the production modular coils. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: Draft C1 – June 10, 2004 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. Attachment 1 – Detailed Breakdown of Cost Impacts Attachment 2 – Updated Barcharts Description of Change: The following items provide details of the WBS 14 jobs affected by this ECP Job 1403, Modular Coil Final Design Cost impact: Eliminate past variances associated with completion of MCWF final design deliverables: $400k Increase estimates for winding details and assembly drawings; additional analysis addressing FDR issues: fracture life and winding pack shear loads: $170k Schedule impact: Eliminate past schedule variance, associated with completion of MCWF Title II design, of $155k. Job 1404, Modular Coil Winding Form R&D Cost impact: Reduce budget per latest vendor forecast: –$100k Schedule impact: Eliminate past schedule variance, associated with completion of MCWF Title II design, of $572k and update schedule for remaining work to be consistent with current forecasts. (Any future work on the MCWF prototypes will support manufacturing planning and estimates, not design.) Job 1406, Modular Coil Winding R&D Cost impact: Eliminate past variances in work (materials properties testing) associated with completion of MCWF final design deliverables: $300k. Increase estimates for fabrication of twisted racetrack demo coil and additional testing to address FDR issue of winding pack shear: $300k Schedule impact: Eliminate past schedule variance, due to delays in non-critical testing tasks in order to support completion of MCWF Title II design, of $115k and update schedule for remaining work to be consistent with current forecasts. Future work will support design and manufacture of the winding assemblies. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: Draft C1 – June 10, 2004 |
| Continuation Sheet: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) Job 1407, Winding Fixtures and Facilities Cost impact: Increase estimates for design, fabrication, installation of fistures and supports. Justification?? $205K. Job 1408, Production Materials, Supplies, and Component Fab. Cost impact: Increase estimates due to added complexity for fabrication of clamps, chill plates, and cladding. $215K. Job 1410, Prototype winding fabrication Cost impact: Increase/Decreased (?) estimates due to… $___K. |