| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Bob Simmons |  |  | Date: July XX, 2004 |  |
| ECP No: 04-011 |  | ECP Title: Update of Technical, Cost, and Schedule Baselines |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: Plasma Facing Components (WBS 12 Manager), Conventional Coils WBS 13) Manager, Modular Coils (WBS 14) Manager, Stellarator Core Systems Project Engineer, Electrical Power Systems WBS Manager (WBS 4), Electrical Power Systems Project Engineer, NCSX Engineering Manager, NCSX Project Control Manager, NCSX Project Manager |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |  |  |  |  |
| Actions - Update technical, cost, and schedule performance measurement baseline - Update WAFs to reflect the new detailed cost estimates - Report status against these revised baselines, starting with the August statusing - Update DOE PARS as necessary to reflect this information |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Under Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |
| --- | --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |  |
| Originator: Bob Simmons |  | Date: July XX, 2004 |
| ECP No: 04-011 | ECP Title: Update of Technical, Cost, and Schedule Baselines |  |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: (1) As the stellarator core design is finalized, it has become evident that in some areas, there is new scope and added effort needed to complete the final design. The has resulted in some cost growth and new scope that will impact the performance measurement baseline. (2) Recently awarded contracts for the installation of the transmission towers and cable trays was higher than budgeted. (3) Additional effort is needed for Project Control, Design Integration, and Global Analyses work to support the completion of the stellarator core design in the areas of the vacuum vessel and modular coils. Impacted WBS Elements: WBS 12 (Vacuum Vessel Systems), WBS 13 (Conventional Coil Systems), WBS 14 (Modular Coil Systems), WBS 432 (D-to-C Site DC Systems, WBS 81 (Project Management and Control), and WBS 82 (Project Engineering). Impacts of Change (Briefly Describe): The net impact of all the above listed items is approximately $XXXK. As a result of the above changes, it is proposed to draw down contingency by $XXXK from $14,180K to $XXXXXK. Assessment of Other Options: None. |  |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |
| --- | --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |  |
| Originator: Bob Simmons |  | Date: – July XX, 2004 |
| ECP No: 04-011 | ECP Title: Update of Technical, Cost, and Schedule Baselines |  |
| Detailed Description of the Change (Continued): List Attachments, Impacted Documents, etc. (1) Attachment 1 – Details of Change (2) Attachment 2 – Updated ECP-04-011 Bar Charts (Primavera) Description of Changes: - WBS 12 (Vacuum Vessel) - Technical Impacts: - Cost Impacts (Including any Offsetting Cost Adjustments): - Schedule Impacts: - WBS 13 (Conventional Coil Systems) - Technical Impacts: - Cost Impacts (Including any Offsetting Cost Adjustments): - Schedule Impacts: - WBS 14 (Modular Coil Systems) - Technical Impacts: - Cost Impacts (Including any Offsetting Cost Adjustments) - Schedule Impacts - WBS 432 (D-to-C Site DC Systems) - Technical Impacts: None - Cost Impacts (Including any Offsetting Cost Adjustments): $0K. Although the contract awarded on July 13, 2004 was approximately $83K higher than budgeted, reprogramming activities within this WBS element have provided the necessary budget. Cost increase primarily due to material cost growth of steel and the need to add an additional cable tray for the control cables (vs. portioning existing planned cable trays to accommodate the control cables). - Schedule Impacts: None - WBS 81 (Project Management and Control) - Technical Impacts: None - Cost Impacts (Including any Offsetting Cost Adjustments): +$115K Additional resources needed to support the award of the VVSA and MCWF production contracts and to provide project control support. - Schedule Impacts: |  |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |
| --- | --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |  |
| Originator: Bob Simmons |  | Date: – July XX, 2004 |
| ECP No: 04-011 | ECP Title: Update of Technical, Cost, and Schedule Baselines |  |
| Detailed Description of the Change (Continued): - WBS 82 (Modular Coil Systems) - Technical Impacts: None - Cost Impacts (Including any Offsetting Cost Adjustments): +$150K Additional resources needed in the Design Integration and Systems Analysis efforts. Schedule Impacts: |  |  |