Attachment [1] – Detailed Description of Change

Modular Coil Winding Form (MCWF) Procurement (WBS 141)

The NCSX project recently received two fixed price bids for fabricating the production winding forms.  The scope of work in the bids included casting seventeen winding forms and machining eighteen.  The first casting will be provided under the current manufacturing development and prototype fabrication contract.

We are in final negotiations with one of the suppliers.  The price for the production winding forms is $8.0M.  Assuming a contract start date of 15 September 2004, the first casting would be delivered on or before 13 May 2005, with subsequent castings being delivered every 4 weeks (29 days) thereafter.  The last casting would be received on or before 15 September 2006.  Payments would be made monthly between 15 October 2004 and 15 September 2006.

Work on the prototype winding forms has been stopped by both suppliers, saving $118K and $196K respectively.  Pre-production casting activities (added scope per ECP-04-008) had been initiated by the two MCWF suppliers. .  Work on the pre- production casting has been stopped by the supplier with whom we are not negotiating.  ECP-04-008 added $75K to the cost baseline to fund a second supplier to initiate work on a pre-production casting.  Initial cost estimates were based on using the same pattern process that was used for the prototype.  The supplier with whom we are in final negotiations has identified the need to change the pattern design, moving from foam patterns to hard (wood) patterns because of the heavier than anticipated weight of the casting.  The wood patterns are re-usable, which is advantageous, but they cost more and require more time to fabricate.  The fixed price proposal was predicated on using a hard Type C pattern produced as part of the pre-production casting activities.  It is estimated that an additional $329K will be required to complete the pre-production casting activities with the supplier with whom we are in final negotiations and an additional $20K will be required to close out pre-production casting activities with the other supplier.

The budgeted direct cost for this work scope was $4.8M.  The budgeted cost and schedule were derived from input from both suppliers participating in the Manufacturing Development and Prototype Fabrication phase.  It was assumed that the contract would run from 01 October 2004 through 24 April 2006.  The first casting would arrive on 20 January 2005.  The last casting would be received by 24 April 2006.  This assumed that a casting would be arriving on average every 27 days.  The planned Budget Authorization (BA) was $0.6M in FY04, $3.2M in FY05, and $1.0M in FY06.

The impacts of this proposal are clear:

- Cost increase. An (unloaded) cost increase of $3.2M, which is substantially more than the 40% contingency ($1.9M) allotted to this scope of work.

- Schedule delays.  A delay in receiving the first casting of 16 weeks, which represents a delay in winding the first coil.  A delay in receiving the last casting of 20 weeks, which represents a delay in winding the last coil.

- Funding constraints.  The increase in the required BA for the winding forms requires that other activities be postponed to make funding available for these critical path activities.

The project has revised the resource-loaded schedule to accommodate the supplier’s delivery and payment schedules and developed offsets to mitigate these impacts.

Vacuum Vessel Sub-assembly Procurement (WBS 121)

The NCSX project also received two fixed price bids for fabricating the vacuum vessel sub-assemblies (VVSAs).  We are in final negotiations with one of the suppliers. The price for the production VVSAs is $4.5M.  Assuming a contract start date of 31 August 2004, the three VVSAs would be delivered in the period from 5 September 2005 through 25 October 2005.  Payments would be made as the work was completed.    All but perhaps fabrication and receipt of the 3rd VVSA and receipt of the tooling would be billed in FY05 with the balance being billed in the very first part of FY06.

The budgeted direct cost for this procurement was $2.7M.  The budgeted cost and schedule was derived from input from both suppliers participating in the Manufacturing Development and Prototype Fabrication phase.  The proposed schedule was consistent with the baseline schedule.  However, the required BA is significantly higher than the planned BA of $0.6M in FY04, $2.27M in FY05, and $0M in FY06.

The impacts of this proposal are clear:

- Cost increase. An (unloaded) cost increase of $1.8M, which is substantially more than the 40% contingency ($1.1M) allotted to this scope of work.

- Funding constraints.  The increase in the required BA for the VVSAs requires accommodation.

The project has developed offsets to mitigate the cost increase.  The stretch-out in the MCWF schedule permits the delivery date for the last VVSA to slip to 24 May 2006, a slip of 30 weeks, while reducing the total float in the VVSA by less than 2 weeks.  The stretch-out reduces BA requirements in FY05 allowing more funding to be available for the more schedule-critical MCWF procurement.

Modular Coil Winding (WBS 142)

One of the recognized schedule risks in winding the modular coils is that the application of the chill plates and cooling tubes might take longer than the schedule would allow.  This risk has been mitigated by changing Station 4 into a winding station.  Station 4 previously was used to apply the chill plates, cooling tubes, and to prepare the winding for VPI.  Now that work will be done on the three winding stations, improving efficiency and schedule robustness.  Winding of the last six coils will be done on a two-shift basis to mitigate the schedule impact of the delayed production of the winding forms.  The figure below illustrates the new flow with three winding stations.

VV Outer Port Extensions and NB Transition Ducts (WBS 121)

The VVSA design features an Inconel shell with Inconel port extensions that are welded on during field period assembly.  The port extensions extend through the modular coil shell and have vacuum flanges at the ends.  Outer port extensions, made of stainless steel, will be attached at these flanges to extend the ports through the cryostat.  For initial operation, there are no diagnostics which use these outer port extensions so they were removed from the MIE project scope.  Likewise, the three NB transition ducts are not required for initial operation and were removed from the MIE project scope.  The vacuum pumping system, which will ultimately be connected to a NB transition duct, can be connected to one of the vertical ports or to the large port adjacent to the NB transition duct for initial operation.  Elimination of the outer port extensions and NB transition ducts from the MIE project will save $250K.

Modular Coil Winding From Title III Engineering (WBS 141)

Title III Engineering costs were reduced to levels more in line with our experience during the Manufacturing Development and Prototype Fabrication phase saving $150K.

Laser-based GPS (WBS 187)

The laser-based GPS was eliminated saving $129K.  Metrology needs can be satisfied using two multi-link coordinate measurement machines (Romer arms) and one Leica laser tracker.

Neutral Beams (WBS 25)

The NB equipment tests required for CD-4 will be satisfied this month.  The equipment has been shown to be in good condition.  Remaining project tasks would make progress toward full operation, but nor provide any capability required for CD-4.  These remaining tasks have been eliminated saving $833K.

Diagnostic Integration (WBS 39) and Project Physics (WBS 84)

Many ports were added prior to the VVSA FDR, satisfying the MIE diagnostic interface goals and ensuring that required upgrade diagnostics can be accommodated.  The budget has been reduced by $481K in Diagnostics Integration (WBS 39) and by $95K in Proejct Physics (WBS 84).  (Diagnostics required for CD-4 will still be provided within the MIE project scope.)

Electrical Power System (WBS 4)

CD-4 coil power requirements will be satisfied using C-site equipment.  All work associated with the D-Site power supplies, including the DC transmission from D- to C-site, has been deleted from the MIE scope.  Assignment of the power supplies for each coil and the available voltage and current are shown in the table below.

| Coil | Max.Voltage (Volts) | Max. Current (kiloAmps) | Assigned Power Supply |
| --- | --- | --- | --- |
| M1, M2, M3 in series | 500 | 20 | R20 |
| TF | 300 | 5 | R5-1 |
| PF1, PF2 in series | 550 | 5 | R5-2 &3 in series |
| PF3 | 300 | 5 | R5-4 |
| PF4 | 500 | 5 | UCLA |
| PF5 |  |  | Not required for First Plasma |
| PF6 | 100 | 10 | R10 |

Each of the above seven rectifier supplies presently installed in C-Site will be cabled up to the NCSX coils listed above. Protection for the coil system will be designed and installed in C-Site. A redundant PLC system will be designed and installed to provide hardwired controls for the rectifiers.  The change to the C-site power supplies should save $1626K.

Plasma Control (WBS 5)

CD-4 control requirements can be satisfied with a more basic I&C system.  This approach sacrifices convenience, but provides essential control and protection.  Some savings were also realized as a result of NSTX developments.  Total savings from adopting this approach are estimated to be $402K.

Cryogenic Cooling Supply (WBS 622)

The baseline NCSX cryogenic cooling design provides highly efficient liquid cryogen transfer lines from the existing 9200 gallon tank to the NCSX device.  These vacuum insulated and thermal radiation shielded lines are held by the cryogenics industry as the best economic choice for years-long service.  The insulation quality of this type of line minimizes the amount of liquid lost to phase change to gas.  Also planned was a sub-cooled single phase (all liquid) cooling circuit for the NCSX field windings.  A simplified representation of such a system is shown in the figure.  Key points are that the expansion volume maintains the minimum system (pump suction) pressure above the saturation pressure (boiling point) associated with the warmest points in the windings:  The system stays in the liquid phase.  The single phase aspect of the system coupled with redundant pumps (less mechanical downtime) yields a design that supports the heat rejection rate requirements.  A final notable feature is that the heat exchanger for the liquid circuit is cooled by boiling atmospheric pressure liquid nitrogen whose off-gas is used to cool the machine cryostat.

A simplified single phase approach is proposed that will cool the NCSX windings with liquid nitrogen that is prevented from boiling in the cooling circuits by an appropriate back-pressure valve and control scheme (see figure below).  The back-pressure can be maintained at a useful level that remains less that the supply pressure from the 9200 gallon storage tank:  The differential pressure between the tank and the back-pressure control drives flow through the winding’s coolant passages.  This low-cost design will allow enough heat rejection capacity to support recently-issued first plasma and field line mapping scenarios.  A further cost-saving measure in this proposal is the substitution of less-thermally efficient urethane foam-insulated lines for the vacuum insulated lines mentioned above.

These changes will provide a cost savings of $300K.

Vacuum Vessel Heating/Cooling System (WBS 64)

The Heating/Cooling System was given a bottoms up re-estimate using a once-through low temperature (150 C) air design.  The once through system would be operating at low pressure, which would ease welding and inspection requirements needed for a High Pressure Helium system. The new design would eliminate the return loop, high temperature (350 C) compatible valves, and a heat exchanger and associated water piping with connections on the inlet to the first compressor.  It would also eliminate the need for the helium makeup system.  There would be no schedule impacts but there may be additional technical risk since this is a new concept that has not been designed and built before at PPPL.  A flow diagram of the revised H/C system design is shown in the figure below.  The revised design should save $166K.

Startup (WBS 85)

The revised startup testing schedule completes the final CD-4 tests in two months, recouping most of the schedule impact from the late delivery of the modular coil winding forms.  E-beam mapping will be limited to confirming that the basic magnet system produces magnetic surfaces.  Coil and power supply tests and First Plasma will be performed at cryogenic temperature.  The startup period was reduced by moving tasks (e.g., cryostat installation, close out “punch list” of construction items, and the ACC safety assessment) formerly in the startup phase forward into the construction phase.  Moving to the C-site power supplies, which are powered directly off the PSE&G line, avoids use of the D-site MGs and potential scheduling conflicts with NSTX.

Cryostat installation will occur during the construction phase (6 weeks savings).  E-beam mapping will be performed only at cryogenic temperature