## Sheet1
Activity ID | Activity Description | Early Start | Work Days | Early Finish
P1-241 | First field period ready for installation |  |  | 2007-02-26
P2-241 | Second field period ready for installation |  |  | 2007-03-14
P3-241 | Third field period ready for installation |  |  | 2007-04-27
| Install and test TC HVAC and Fire Protection | 2006-08-01 | 40 | 2006-09-26
730.1000 | Begin assembly activities | 2006-10-01 | 0 | 2006-10-01 | Start at the beginning of FY07
730.1020 | Position, level, and mount base support structure | 2006-10-01 | 30 | 2006-11-10
| Install 3/4 of platform | 2006-10-01 | 40 | 2006-11-24
| Install Electrical Systems (WBS 4) equipment in TC | 2006-11-24 |  | 2007-04-27 | Complete by when the third field period is ready for installation
| Install Neutral Beam (WBS 25) equipment in TC | 2006-11-24 |  | 2007-04-27 | Complete by when the third field period is ready for installation
| Install TVPS (WBS 22) equipment in TC | 2006-11-24 |  | 2007-04-27 | Complete by when the third field period is ready for installation
| Install VV H/C (WBS 64) equipment in TC | 2006-11-24 |  | 2007-04-27 | Complete by when the third field period is ready for installation
| Install Water Cooling System (WBS 61) equipment in TC | 2006-11-24 |  | 2007-04-27 | Complete by when the third field period is ready for installation
| Install Cryogenic System (WBS 62) equipment in TC | 2006-11-24 |  | 2007-04-27 | Complete by when the third field period is ready for installation
| Install Utility Systems (WBS 63) equipment in TC | 2006-11-24 |  | 2007-04-27 | Complete by when the third field period is ready for installation
| Install lighting, fire detection, and fire suppression systems under platform | 2006-11-24 | 10 | 2007-05-30 | Work days after completion of platform
730.1070 | Pre-position lower ring coils on base support plates | 2007-01-29 | 10 | 2007-02-12 | Complete two weeks prior to arrival of the first field period
730.1061 | Deliver and mount all three field periods | 2007-02-26 | 5 | 2007-05-02 | Work days after arrival of the last field period
730.1091 | Install remaining platform section | 2007-05-02 | 10 | 2007-05-16
| Simulataneously move field periods to final radial position | 2007-05-16 | 10 | 2007-05-30
| Position field periods and bolt modular coil and coil support structures together | 2007-05-30 | 20 | 2007-06-27
| Align and wedge TF coils together. Apply pre-load. | 2007-06-27 | 15 | 2007-07-18
| Install lower PF ring coils | 2007-07-18 | 5 | 2007-07-25
| Install upper PF ring coils and central solenoid (CS) assembly | 2007-07-25 | 10 | 2007-08-08
| Install trim coils that cross assembly planes | 2007-08-08 | 5 | 2007-08-15
| Connect coil services (electrical leads, cooling, and I&C) between field periods and to cryostat feedthroughs | 2007-06-27 | 10 | 2007-08-25 | Work days after all coil installations are complete
| Perform local, low power testing of coil electrical circuits to verify that electrical leads and instrumentation are properly connected and coils/leads are functioning as expected (PTP) | 2007-08-25 | 5 | 2007-08-31
| Perform pressure tests of coil cooling circuits to verify integrity of cooling loops inside the cryostat (PTP) | 2007-08-25 | 5 | 2007-08-31
| Position VV segment for welding to spool pieces. Field weld (6) closure joints. Leak check closure joints. Connect final VV supports. | 2007-08-31 | 20 | 2007-09-28
| Connect vacuum pump duct between VV and TVPS | 2007-09-28 | 2 | 2007-10-02
| Connect VV H/C equipment (WBS 64) | 2007-10-02 | 3 | 2007-10-05
| Pump down VV, bake to 150C, and perform vacuum leak check (TEP Section 6.2). Vent VV and resume final assembly operations. | 2007-10-05 | 10 | 2007-10-19
| Complete shield wall installation | 2007-10-05 | 10 | 2007-10-19 | Work done while VV is being pumped and baked
| Scrub stellarator core, clear all ground faults, perform hi-pot tests for equipment within the cryostat | 2007-10-19 | 5 | 2007-10-26 | Make sure we are not burying any problems
| Install cryostat | 2007-10-26 | 20 | 2007-11-23
| Connect TC buswork (WBS 4) to cryostat feedthroughs | 2007-10-26 | 10 | 2007-12-03 | Work days after cryostat installation is completed
| Connect coil local I&C | 2007-10-26 | 10 | 2007-12-03 | Work days after cryostat installation is completed
| Connect TC LN2 supply (WBS 622) to cryostat feedthroughs | 2007-10-26 | 10 | 2007-12-03 | Work days after cryostat installation is completed
| Install and test Gas Fueling System (WBS 211) equipment | 2007-10-26 | 10 | 2007-12-03 | Work days after cryostat installation is completed
| Connect remaining local I&C and diagnostics (WBS 3/5) | 2007-10-26 | 10 | 2007-12-03 | Work days after cryostat installation is completed
| Connect and test water cooling (WBS 61) (TEP Section 6.3) | 2007-10-26 | 10 | 2007-12-03 | Work days after cryostat installation is completed
| Install GN2 Cryostat Cooling System (WBS 623) | 2007-10-26 | 10 | 2007-12-03 | Work days after cryostat installation is completed
| Cool down stellarator core to 80K (PTP) | 2007-10-26 | 10 | 2007-12-03 | Work days after cryostat installation is completed
| Install and test hardwired interlock system (HIS) and hardwired control system (HCS) | 2007-10-26 | 10 | 2007-12-03 | Work days after cryostat installation is completed
| Install e-beam mapping system | 2007-10-26 | 10 | 2007-12-03 | Work days after cryostat installation is completed
| Complete facility preparations (TEP Section 6.1) | 2007-12-03 | 5 | 2007-12-10
| Perform operational readiness assessment (ACC) | 2007-11-12 | 20 | 2007-12-10 | Complete concurrently with the completion of facility preparations
| END OF CONSTRUCTION | 2007-12-10 | 0 | 2007-12-10
| Complete Energy Conversion Systems testing (TEP Section 6.4) | 2007-12-10 | 5 | 2007-12-17
| Complete preparations for coil energization (TEP Section 6.5) | 2007-12-10 | 5 | 2007-12-17
| Perform e-beam mapping | 2007-12-17 | 5 | 2007-12-24
| ES&H ESB review and approval of ACC recommendation. Issue limited safety certificate. | 2007-12-10 | 10 | 2007-12-24 | Start when ACC recommendation is received
| Perform coil energization testing (TEP Section 6.6) with coils at cryogenic temperature. | 2007-12-24 | 5 | 2007-12-31
| Bake vacuum vessel for First Plasma (TEP Section 6.7) | 2007-12-24 | 5 | 2007-12-31
| Complete First Plasma Approval Requirements (TEP Section 7.2) | 2007-12-24 | 5 | 2008-01-07 | Work days after completion of ISTP
| FIRST PLASMA | 2008-01-07 | 0 | 2008-01-07
Formulas:
Early Finish = WORKDAY([Early Start],[Work Days],0)
Early Finish = WORKDAY(E21,[Work Days],0)
Early Start = [Early Finish, row above]
Early Start = WORKDAY([Early Finish],-[Work Days],0)