## Hutch mods
NCSX Impact Analysis
Scenario 3 CD-3
Assumptions;
1) Vac Vsl Contract cost growth 50% (from $3.2m to $4.8).
2) Mod Coil Contract cost growth 185% (from $4.8m to $8.9m.
Results;
|  | Cost |  | Scope | Contingency | TEC | BCWP (est as of 8/1) | BCWR (est as of 8/1)
|  |  | Current (ECP 11)= | 73.605 | 12.695 | 86.3 | 16.8 | 56.805 |  | 22.35%
|  | p3 "00X3" | Increases
|  | x | WBS 121 VVSA increase | 1.889 | -1.889 | 0 |  | 1.889
|  | x | WBS 14 MCWF Increase= | 4.053 | -4.053 | 0 |  | 4.053
|  | x | WBS 14 Pre-proposal casting JPP = | 0.02 | -0.02 | 0 |  | 0.02
|  | x | WBS 14 Pre-proposal casting EIO = | 0.329 | -0.329 | 0 |  | 0.329 |  |  | -0.35
|  | x | Escalation due to rescheduling | 0.057 | -0.057 |  |  | 0.057
|  |  |  | 6.348 | -6.348 | 0 |  | 6.348 |  |  | -0.5
|  |  | Cost Reductions |  |  | 0 |  |  |  |  | -0.8
|  | x | WBS 121 NB ports | -0.15 | 0.15 | 0 |  | -0.15 | -0.03
|  | x | WBS 121 port extensions | -0.15 | 0.15 | 0 |  | -0.15 | -0.03
|  | x | WBS 14 Prototype maching EIO= | -0.118 | 0.118 | 0 |  | -0.118
|  | x | WBS 14 Prototype maching JPP= | -0.196 | 0.196 | 0 |  | -0.196 |  |  | -0.4
|  | x | WBS 14 Title 3 on casting fab | -0.15 | 0.15 | 0 |  | -0.15 | -0.03
|  | x | WBS 18 laser based GPS syst | -0.129 | 0.129 | 0 |  | -0.129 | -0.0258
|  | x | WBS 25 NBI TBD | -0.833 | 0.833 | 0 |  | -0.833 | -0.1666
|  | x | WBS 39 diag integration | -0.481 | 0.481 | 0 |  | -0.481 | -0.0962
|  | ? | WBS 4 add'l TBD c-site onlt? | -0.4 | 0.4 | 0 |  | -0.4 | -0.08
|  | x | WBS 4 c/d site hybrid | -0.3 | 0.3 | 0 |  | -0.3 | -0.06
|  | x | WBS 5 plasma cntrl & cntrl rm | -0.478 | 0.478 | 0 |  | -0.478 | -0.0956
|  | x | WBS 622 Cryogenic cooling supply | -0.387 | 0.387 | 0 |  | -0.387 | -0.0774
|  | x | WBS 64 Heating/Cooling system | -0.122 | 0.122 | 0 |  | -0.122 | -0.0244
|  | x | WBS 84 Project physics | -0.095 | 0.095 | 0 |  | -0.095 | -0.019 |  | -1.791
|  | x | WBS 85 startup TBD | -0.099 | 0.099 | 0 |  | -0.099 | -0.0198 |  |  | WBS 13 Trim Coils Dsn/Fab | -0.372
Changes week of 8/16
|  |  | WBS 121 NB ports | 0.025 | -0.025 | 0 |  | 0.025 | 0.005
|  |  | WBS 64 Heating/Cooling system | -0.037 | 0.037 | 0 |  | -0.037 | -0.0074
|  |  | WBS 64 Heating/Cooling system | 0.045 | -0.045 | 0 |  | 0.045 | 0.009
|  |  | WBS 4 c-site only | -1.3 | 1.3 | 0 |  | -1.3 | -0.26
|  |  | WBS 5 plasma cntrl & cntrl rm | 0.055 | -0.055 | 0 |  | 0.055 | 0.011
|  |  | WBS 121 VVSA improvement |  |  | 0 |  | 0
|  |  | WBS 14 MCWF improvement |  |  | 0 |  | 0
[6 empty] | 0 |  | 0 | 0 | -0.9972
|  |  |  | -5.3 | 5.3 | 0 |  | -5.3 |  | Alternate Contingency Assessment
Bottoms up scope remaining x risk %
|  |  | CD-3 Baseline = | 74.653 | 11.647 | 86.3 | 16.8 | 57.853 | B | Includes cost of VVSA & MCWF @ 10% conting
57.853
[7 empty] | less VVSA = | -4.8
[7 empty] | less MCWF = | -8.9
[7 empty] | Remaining risk= | 44.153 | A | 11.3528
|  |  | Contingency on VVSA & MCWF | 1.37 | 10% |  | Contingency balance = | 11.647
| Have; |  | Contingency on All Other Scope | 10.277 | 23.28% |  | % ContA = | 26.38% |  | 19.62%
| Should have |  | Contingency on All Other Scope | 9.9828 | 22.61% |  | % ContB = | 20.13% |  | TEC = | 86.0058
| Used to Have: |  | Contingency on All Other Scope | 9.5918 | 19.56% |  |  |  |  | -0.2942
|  |  |  | -0.15 | 0.15 | 0 |  | -0.15 | -0.03
|  |  | Scope item | ∆cost ($M) | Responsible
|  |  | WBS 121 NB ports | -0.125 | Nelson
|  |  | WBS 121 port extensions | -0.15 | Nelson
|  |  | WBS 14 Prototype maching EIO= | -0.118 | Nelson
|  |  | WBS 14 Prototype maching JPP= | -0.196 | Nelson
|  |  | WBS 14 Title 3 on casting fab | -0.15 | Nelson
|  |  | WBS 18 laser based GPS syst | -0.129 | Nelson
|  |  | WBS 25 NBI | -0.833
|  |  | WBS 39 diag integration | -0.481 | D. Johnson
|  |  | WBS 4 Adopt All-C-site Design | -2 | Ramakrishnan
|  |  | WBS 5 cuts as documented by G.O. Add T/C & strain gauge data aq. | -0.423 | Oliaro
|  |  | WBS 622 Cryogenic cooling supply | -0.387 | Gettelfinger
|  |  | WBS 64 Heating/Cooling system | -0.114 | Dudek
|  |  | WBS 84 Project physics | -0.095
|  |  | WBS 85 startup TBD (estimate to be updated) | -0.099 | Gentile
|  |  | Total | -5.3
Note on E34: Hutch Neilson: Elbow for the TVPS.
Note on E35: Hutch Neilson: Dudek found more savings.
Note on E37: Hutch Neilson: Raki found a lot more savings. Corrected spreadsheet error.
Note on E38: Hutch Neilson: Add WBS 52 Eng. Data Acquisition System.
Note on E39: Hutch Neilson: Placeholder for anticipated contract savings.
Note on E36: Hutch Neilson: Restore 150C bake.

## Ron 0813
NCSX Impact Analysis
Scenario 3 CD-3
Assumptions;
1) Vac Vsl Contract cost growth 50% (from $3.2m to $4.8).
2) Mod Coil Contract cost growth 185% (from $4.8m to $8.9m.
Results;
|  | Cost |  | Scope | Contingency | TEC | BCWP (est as of 8/1) | BCWR (est as of 8/1)
|  |  | Current (ECP 11)= | 73.605 | 12.695 | 86.3 | 16.8 | 56.805 |  | 22.35%
|  | p3 "00X3" | Increases
|  | x | WBS 121 VVSA increase | 1.889 | -1.889 | 0 |  | 1.889
|  | x | WBS 14 MCWF Increase= | 4.053 | -4.053 | 0 |  | 4.053
|  | x | WBS 14 Pre-proposal casting JPP = | 0.02 | -0.02 | 0 |  | 0.02
|  | x | WBS 14 Pre-proposal casting EIO = | 0.329 | -0.329 | 0 |  | 0.329 |  |  | -0.35
|  | x | Escalation due to rescheduling | 0.057 | -0.057 |  |  | 0.057
|  |  |  | 6.348 | -6.348 | 0 |  | 6.348 |  |  | -0.5
|  |  | Cost Reductions |  |  | 0 |  |  |  |  | -0.8
|  | x | WBS 121 NB ports | -0.15 | 0.15 | 0 |  | -0.15 | -0.03
|  | x | WBS 121 port extensions | -0.15 | 0.15 | 0 |  | -0.15 | -0.03
|  | x | WBS 14 Prototype maching EIO= | -0.118 | 0.118 | 0 |  | -0.118
|  | x | WBS 14 Prototype maching JPP= | -0.196 | 0.196 | 0 |  | -0.196 |  |  | -0.4
|  | x | WBS 14 Title 3 on casting fab | -0.15 | 0.15 | 0 |  | -0.15 | -0.03
|  | x | WBS 18 laser based GPS syst | -0.129 | 0.129 | 0 |  | -0.129 | -0.0258
|  | x | WBS 25 NBI TBD | -0.833 | 0.833 | 0 |  | -0.833 | -0.1666
|  | x | WBS 39 diag integration | -0.481 | 0.481 | 0 |  | -0.481 | -0.0962
|  | ? | WBS 4 add'l TBD c-site onlt? | -0.4 | 0.4 | 0 |  | -0.4 | -0.08
|  | x | WBS 4 c/d site hybrid | -0.3 | 0.3 | 0 |  | -0.3 | -0.06
|  | x | WBS 5 plasma cntrl & cntrl rm | -0.478 | 0.478 | 0 |  | -0.478 | -0.0956
|  | x | WBS 622 Cryogenic cooling supply | -0.387 | 0.387 | 0 |  | -0.387 | -0.0774
|  | x | WBS 64 Heating/Cooling system | -0.122 | 0.122 | 0 |  | -0.122 | -0.0244
|  | x | WBS 84 Project physics | -0.095 | 0.095 | 0 |  | -0.095 | -0.019 |  | -3.003
|  | x | WBS 85 startup TBD | -0.099 | 0.099 | 0 |  | -0.099 | -0.0198 |  |  | WBS 13 Trim Coils Dsn/Fab | -0.372
[6 empty] | 0 |  | 0 | 0 | -0.7548
|  |  |  | -4.088 | 4.088 | 0 |  | -4.088 |  | Alternate Contingency Assessment
Bottoms up scope remaining x risk %
|  |  | CD-3 Baseline = | 75.865 | 10.435 | 86.3 | 16.8 | 59.065 | B | Includes cost of VVSA & MCWF @ 10% conting
59.065
[7 empty] | less VVSA = | -4.8
[7 empty] | less MCWF = | -8.9
[7 empty] | Remaining risk= | 45.365 | A | 11.5952
|  |  | Contingency on VVSA & MCWF | 1.37 | 10% |  | Contingency balance = | 10.435
| Have; |  | Contingency on All Other Scope | 9.065 | 19.98% |  | % ContA = | 23% |  | 19.63%
| Should have |  | Contingency on All Other Scope | 10.2252 | 22.54% |  | % ContB = | 17.67% |  | TEC = | 87.4602
| Had: |  | Contingency on All Other Scope | 9.5918 | 19.56% |  |  |  |  | 1.1602
|  |  |  | FY03 | FY04 | FY05 | FY06 | FY07 | FY08 | FY09 | Total
|  |  | MIE Planned scope = | 5.9447 | 15.4515 | 16.9985 | 20.7477 | 14.5936 | 2.1117 | 0 | 75.8477
|  |  | MIE Contingency = |  |  | 1.3 | 1.4 | 4.8 | 2.95 |  | 10.45
|  |  | MIE Total = | 5.9447 | 15.4515 | 18.2985 | 22.1477 | 19.3936 | 5.0617 |  | 86.2977
|  |  | BA Funding Profile (MIE ONLY) | 5.9 | 17.9 | 15.9 | 22.1 | 19.4 | 5.1
|  |  | MIE cum plan | 5.9447 | 21.3962 | 39.6947 | 61.8424 | 81.236 | 86.2977
|  |  | MIE cum funding | 5.9 | 23.8 | 39.7 | 61.8 | 81.2 | 86.3
|  |  | Res Prep = | 0.8 | 0.8 | 0.8 | 1.7 | 7.6 | 22.7
|  |  | Total MIE & RP = | 6.7447 | 16.2515 | 19.0985 | 23.8477 | 26.9936 | 27.7617
|  |  | BA Funding Profile (MIE & RP) | 6.7 | 18.7 | 16.7 | 23.8 | 27 | 27.8
|  |  | Plan cumulative |  | 103.8371 | 42.0947 | 65.9424 | 92.936 | 120.6977
|  |  | BA Funding Profile cumulative (MIE & RP) |  | 25.4 | 42.1 | 65.9 | 92.9 | 120.7
|  |  | ORNL |  |  | 2 | 1.65 | 1.19 | 0.5
Schedule
First Plasma MAY 2008 with 4.5 month float
Milestone impact
|  |  |  | Baseline | New | mo. Slip
|  |  | Delivery of VVSA | 2005-11-01 | 2006-01-01 | 2.0333 | Stretched out VV fabrication due to BA
|  |  | Delivery of First MCWF | 2005-01-05 | 2005-05-15 | 4.3333 | EIO Proposal
|  |  | Delivery of Last MCWF | 2006-05-01 | 2006-09-15 | 4.5667 | EIO Proposal
|  |  | Award TF | 2005-01-01 | 2005-05-01 | 4
|  |  | Award PF | 2006-04-01 | 2006-09-01 | 5.1
|  |  | Award CS suptr struct | 2006-03-01 | 2006-07-01 | 4.0667
|  |  | Award Structure | 2005-08-01 | 2006-12-01 | 16.2333
|  |  | Last Field Period Assembled | 2007-01-01 | 2007-04-26 | 3.8333
|  | Manpower Impact in FY05 (relative to FWP |  |  |  | 0
|  |  | EA Engr | -2.1 | makes undercoverage worst. 4.1 to 6.2 | #VALUE!
|  |  | EE Engr | -0.8 | better fit | #VALUE!
|  |  | EM Engr | 0.6 | helps undercoverage | #VALUE!
|  |  | EM Techs | -3.2 | makes undercoverage worst 1 to 4.2 | #VALUE!
0
0
| RES |  | None | RESOURCE | FY 2004 | #VALUE! | FY 2006 | FY 2007 | FY 2008 | FY 2009
|  |  | B///CB - PPPL Project Clerical | B///CB | 0.3 | #VALUE! | 0.2 | 0
|  |  | EA//EM - PPPL Analysis engineer | EA//EM | 7 | #VALUE! | 3.6 | 2.6 | 0.6
|  |  | EA//SM - PPPL Designer | EA//SM | 3.4 | #VALUE! | 3.6 | 1.7 | 0
|  |  | EC//EM - PPPL Comuter Engineer | EC//EM | 0 | #VALUE! | 1.5 | 3.3 | 0.3
|  |  | EC//SM - PPPL Computer Senior Tech | EC//SM |  | #VALUE! | 0 | 1.5
|  |  | EE//AM - | EE//AM | 0 | #VALUE! | 0.2 | 0.2 | 0.1
|  |  | EE//EM - PPPL Electrical engineer | EE//EM | 1.1 | #VALUE! | 2.6 | 1.2 | 0.2
|  |  | EE//SM - PPPL Electrical Senior Tech | EE//SM | 0.9 | #VALUE! | 1.9 | 3.4 | 0.6
|  |  | EE//TB - PPPL Electrical Technician | EE//TB | 0.7 | #VALUE! | 2.5 | 1.9
|  |  | EM//EM - PPPL FO&M Engineer | EM//EM | 2.9 | #VALUE! | 4.1 | 2.6 | 1.7
|  |  | EM//SM - PPPL FO&M Senior Tech | EM//SM | 3.7 | #VALUE! | 4.6 | 5.9 | 1.8
|  |  | EM//TB - PPPL FO&M Technician | EM//TB | 8.5 | #VALUE! | 14.8 | 21.2 | 4.2
|  |  | FC//AM - PPPL P&CO am | FC//AM | 0.5 | #VALUE! | 0.5 | 0.5 | 0.3
|  |  | FC//EM - PPPL P&CO em | FC//EM | 0.7 | #VALUE! | 0.5 | 0.5 | 0.2
|  |  | R///RM2 - PPPL Scientist pdg2 | R///RM2 | 0.5 | #VALUE! | 0.3 | 0.2 | 0.5
|  |  | R///RM3 - PPPL Scientist pdg3 | R///RM3 | 1.4 | #VALUE! | 1 | 0.9 | 0.6
|  |  | SH//TB - HP Techs | SH//TB | 0.7 | #VALUE! | 0.7 | 0
0
[5 empty] | 32.3 | 1.0767 | 42.6 | 47.6 | 11.1 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Begin Pumpdown | 2007-03-01 | 2007-07-01 | 4.0667
|  |  | First Plasma | 2008-05-28 | 2008-05-28 | 0
Major Budgets re-scheduled
[5 empty] | FY04 | FY05 | FY06 | FY07 | FY08 | Total
|  |  | VVSA | Baseline | 0.4 | 2.3 | 0.3 |  |  | 3
|  |  |  | CD-3 Plan | 0.4 | 3.04 | 1.4 |  |  | 4.84
|  |  | MCWF | Baseline |  | 2.8 | 2.1 |  |  | 4.9
|  |  |  | CD-3 Plan |  | 4.7 | 4.2 |  |  | 8.9
|  |  | TF Procurement | Baseline |  | 0.4 | 0.7 |  |  | 1.1
|  |  |  | CD-3 Plan |  | 0.2 | 0.68 | 0.25 |  | 1.13
|  |  | PF Procurement | Baseline |  |  | 1.2 | 0.6 |  | 1.8
|  |  |  | CD-3 Plan |  |  | 0.15 | 1.7 |  | 1.85
|  |  | Structure | Baseline |  | 0.17 | 0.98 |  |  | 1.15
|  |  |  | CD-3 Plan |  |  | 0.93 | 0.24 |  | 1.17
|  |  | Winding/Assy Ops (labor $) | Baseline |  | 1.7 | 2.5 |  |  | 4.2
|  |  |  | CD-3 Plan |  | 0.88 | 2.61 | 0.66 |  | 4.15
|  |  | MC Winding Component Procurement & Fab | Baseline |  | 1 | 0.3 |  |  | 1.3
|  |  |  | CD-3 Plan |  | 0.43 | 0.9 |  |  | 1.33
|  |  | Deleted Scope | Baseline | 0.1 | 1.03 | 1.2 | 1.8 |  | 4.13
|  |  |  | CD-3 Plan | 0 | 0 | 0 | 0 |  | 0
|  |  | Summar of major drivers | Baseline | 0.5 | 9.4 | 9.28 | 2.4 | 0 | 21.58
|  |  |  | CD-3 Plan | 0.4 | 9.25 | 10.87 | 2.85 | 0 | 23.37
|  |  |  | None | RESOURCE | RESOURCE DESCRIPTION | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008
|  |  |  | B///CB - PPPL Project Clerical | B///CB | PPPL Project Clerical | 0.3 | 0.3 | 0.2 | 0
|  |  |  | EA//EM - PPPL Analysis engineer | EA//EM | PPPL Analysis engineer | 7 | 5 | 4.7 | 2.7 | 0.6
|  |  |  | EA//SM - PPPL Designer | EA//SM | PPPL Designer | 3.4 | 3 | 4 | 1.6
|  |  |  | EC//EM - PPPL Comuter Engineer | EC//EM | PPPL Comuter Engineer | 0 | 0 | 0.3 | 4.4 | 0.4
|  |  |  | EC//SM - PPPL Computer Senior Tech | EC//SM | PPPL Computer Senior Tech |  |  |  | 1.5 | 0
|  |  |  | EE//AM - | EE//AM | EE//AM | 0 | 0.1 | 0.2 | 0.2 | 0.1
|  |  |  | EE//EM - PPPL Electrical engineer | EE//EM | PPPL Electrical engineer | 1.1 | 0.9 | 2.5 | 1.2 | 0.2
|  |  |  | EE//SM - PPPL Electrical Senior Tech | EE//SM | PPPL Electrical Senior Tech | 0.9 | 0.2 | 1.7 | 3.7 | 0.6
|  |  |  | EE//TB - PPPL Electrical Technician | EE//TB | PPPL Electrical Technician | 0.7 | 0.2 | 2.4 | 2.2
|  |  |  | EM//EM - PPPL FO&M Engineer | EM//EM | PPPL FO&M Engineer | 2.9 | 2.4 | 3.5 | 2.5 | 1.7
|  |  |  | EM//SM - PPPL FO&M Senior Tech | EM//SM | PPPL FO&M Senior Tech | 3.9 | 2.1 | 5.3 | 6.7 | 1.1
|  |  |  | EM//TB - PPPL FO&M Technician | EM//TB | PPPL FO&M Technician | 8.6 | 6.8 | 18.8 | 20.5 | 1.6
|  |  |  | FC//AM - PPPL P&CO am | FC//AM | PPPL P&CO am | 0.5 | 1 | 0.5 | 0.3 | 0.1
|  |  |  | FC//EM - PPPL P&CO em | FC//EM | PPPL P&CO em | 0.7 | 0.6 | 0.5 | 0.5 | 0.2
|  |  |  | R///RM2 - PPPL Scientist pdg2 | R///RM2 | PPPL Scientist pdg2 | 0.5 | 0.1 | 0.3 | 0.1 | 0.5
|  |  |  | R///RM3 - PPPL Scientist pdg3 | R///RM3 | PPPL Scientist pdg3 | 1.4 | 1 | 0.9 | 0.8 | 0.5
|  |  |  | SH//TB - HP Techs | SH//TB | HP Techs | 0.7 | 0.7 | 0.7 | 0
32.6
Formulas:
Contingency = +[Scope]