## P3
Work Breakdown Structure (WBS) |  | ECP 11 Baseline | Delta | ECP 14 Baseline
|  | (K$) | (K$) | (K$)
WBS 11 - Plasma Facing Components
| 111 - Limiters | 0.1 | 0 | 0.1
Subtotal WBS 11 |  | 0.1 | 0 | 0.1
WBS 12 - Vacuum Vessel
| 121 - Vacuum Vessel Assembly | 6648.1 | 1242.2 | 7890.3
| 122 - Vacuum Vessel Thermal Insulation | 174.9 | -0.2 | 174.7
| 123 - Vacuum Vessel Heating and Cooling Distrib | 375.8 | -0.1 | 375.7
| 124 - Vacuum Vessel Supports | 62.6 | -0.6 | 62
| 125 - Vacuum Vessel Local I&C | 26.7 | 0.6 | 27.3
Subtotal WBS 12 |  | 7288.1 | 1241.9 | 8530
WBS 13 - Conventional Coils
| 130 - Conventional Coils Design | 462.1 | 151 | 613.1
| 131 - TF Coils | 1546.3 | -87.5 | 1458.8
| 132 - PF Coils | 1747.4 | 29.9 | 1777.3
| 133 - External Trim Coils | 372 | 9.1 | 381.1
| 134 - Conventional Coil Local | 85.5 | -12.1 | 73.4
Subtotal WBS 13 |  | 4213.3 | 90.4 | 4303.7
WBS 14 - Modular Coils
| 141 - Modular Coil Winding Form | 10077.6 | 2710.8 | 12788.4
| 142 - Modular Coil Windings and Assembly | 9339.4 | 98.6 | 9438
| 143 - Modular Coil Local I&C | 121.2 | 0 | 121.2
| 144 - Modular Coil Winding Facility & Fixtures | 2707.3 | 0 | 2707.3
Subtotal WBS 14 |  | 22245.5 | 2809.4 | 25054.9
WBS 15 - Coil Support Structure
| 151 - Structures and Base | 1441.1 | 6.7 | 1447.8
Subtotal WBS 15 |  | 1441.1 | 6.7 | 1447.8
WBS 16 - Coil Services
| 161 - LN2 Distribution | 337.5 | 0 | 337.5
| 162 - Electrical Leads | 621.3 | 0 | 621.3
| 163 - Coil Protection System | 78.1 | 0 | 78.1
Subtotal WBS 16 |  | 1036.9 | 0 | 1036.9
WBS 17 - Cryostat and Base Support Structure
| 171 -Cryostat | 858.5 | 4.4 | 862.9
| 172 - Base Support Structure | 438.2 | 0 | 438.2
Subtotal WBS 17 |  | 1296.7 | 4.4 | 1301.1
WBS 18 - Field Period Assembly
| 181 - Field Period Assembly Planning/Oversight | 1379.3 | 0 | 1379.3
| 182 - TFTR Test Cell Area preparations | 92.9 | 0 | 92.9
| 183 - Receive Inspect and Test Coils | 77.4 | 0 | 77.4
| 184 - Receive Inspect and Test VV | 326.3 | 0 | 326.3
| 185 - Assemble Field Periods | 1433.8 | 75.6 | 1509.4
| 186 - Tooling Design and Fabrication | 1175.9 | 41.3 | 1217.2
| 187 - Measurement Systems | 591.6 | -128.4 | 463.2
Subtotal WBS 18 |  | 5077.2 | -11.5 | 5065.7
WBS 19 - Stellarator Core Management and Integration
| 191 - Stellarator Core Management & Oversight | 1083 | 0 | 1083
| 192 - Stellarator Core Integration & Analysis | 1579 | -10.5 | 1568.5
Subtotal WBS 19 |  | 2662 | -10.5 | 2651.5
WBS 21 - Fueling Systems
| 210 - Fueling Systems | 140 | 0 | 140
Subtotal WBS 21 |  | 140 | 0 | 140
WBS 22 - Torus Vacuum Pumping Systems
| 220 - Torus Vacuum Pumping Systems | 384.2 | 3.9 | 388.1
Subtotal WBS 22 |  | 384.2 | 3.9 | 388.1
WBS 25 - Neutral Beam Injection systems
| 250 - Neutral Beam Injection System | 1169.1 | -860.2 | 308.9
Subtotal WBS 25 |  | 1169.1 | -860.2 | 308.9
WBS 31 - Magnetic Diagnostic Systems
| 310 - Magnetic Diagnostics | 454.1 | 1.5 | 455.6
Subtotal WBS 31 |  | 454.1 | 1.5 | 455.6
WBS 36 - Edge and Divertor Diagnostics Systems
| 360 - Edge and Divertor Diagnostics | 99.3 | -56 | 43.3
Subtotal WBS 36 |  | 99.3 | -56 | 43.3
WBS 38 - Electron Beam Mapping Systems
| 380 - Electron Beam (EB) Mapping | 292.1 | 3.2 | 295.3
Subtotal WBS 38 |  | 292.1 | 3.2 | 295.3
WBS 39 - Diagnostic Integration
| 390 - Diagnostics Integration | 847.2 | -480.5 | 366.7
Subtotal WBS 39 |  | 847.2 | -480.5 | 366.7
WBS 41 - AC Power Systems
| 411 - Auxliary AC Power Systems | 569.3 | -98.2 | 471.1
| 412 - Experimental AC Power Systems | 42.8 | -0.1 | 42.7
Subtotal WBS 41 |  | 612.1 | -98.3 | 513.8
WBS 42 - AC/DC Convertors
| 422 - D-Site AC/DC Converters | 23.5 | -23.5 | 0
Subtotal WBS 42 |  | 23.5 | -23.5 | 0
WBS 43 - DC Systerms
| 431 - C-Site DC Systems | 326.7 | 196.9 | 523.6
| 432 - D-to-C Site DC Systems | 1328.7 | -875.6 | 453.1
| 433 - D-Site DC Systems | 487.9 | -474.5 | 13.4
Subtotal WBS 43 |  | 2143.3 | -1153.2 | 990.1
WBS 44 - Control and Protection Systems
| 441 - Electrical Interlocks | 578.6 | -248.2 | 330.4
| 442 - Kirk Key Interlocks | 98 | -7.8 | 90.2
| 443 - Real Time Control Systems | 38.4 | -25.6 | 12.8
| 444 - Instrument Systems | 433.2 | -84.1 | 349.1
| 445 - Coil protection Systems | 283.4 | 83.5 | 366.9
| 446 - Ground Fault Monitoring | 167 | -167 | 0
Subtotal WBS 44 |  | 1598.6 | -449.2 | 1149.4
WBS 45 - Power Systems Design and Integration
| 451 - System Design and Interfaces | 591.4 | -81.4 | 510
| 452 - Electrical Systems Support | 91.4 | 148.8 | 240.2
| 453 - System Testing (PTP's) | 192 | 110.4 | 302.4
Subtotal WBS 45 |  | 874.8 | 177.8 | 1052.6
WBS 46 - FCPC Building Modifications
| 460 - FCPC Building Modifications | 78.6 | -77.3 | 1.3
Subtotal WBS 46 |  | 78.6 | -77.3 | 1.3
WBS 51 - TCP/IP Infrastructure Systems
| 510 - TCP/IP Infrastructure Systems | 429 | -123.2 | 305.8
Subtotal WBS 51 |  | 429 | -123.2 | 305.8
WBS 52 - Central Instrumentation & Control
| 520 - Central Instrumentation & Control | 578 | 82.7 | 660.7
Subtotal WBS 52 |  | 578 | 82.7 | 660.7
WBS 53 - Data Acquisition & Facility Computing
| 530 - Data Acquisition & Facility Computing | 407.8 | 7.1 | 414.9
Subtotal WBS 53 |  | 407.8 | 7.1 | 414.9
WBS 54 - Facility Timing & Synchronization
| 540 - Facility Timing & Synchronization | 352 | -60 | 292
Subtotal WBS 54 |  | 352 | -60 | 292
WBS 55 - Real Time Plasma & Power Supply Control Systems
| 550 - Real Time Plasma & Power Supply Control Systems | 293.3 | -139.6 | 153.7
Subtotal WBS 55 |  | 293.3 | -139.6 | 153.7
WBS 56 - Central Safety Interlock Systems
| 560 - Central Safety Interlock Systems | 399.9 | -38.2 | 361.7
Subtotal WBS 56 |  | 399.9 | -38.2 | 361.7
WBS 57 - Control Room Facility
| 570 - Control Room Facility | 119.7 | -119.7 | 0
Subtotal WBS 57 |  | 119.7 | -119.7 | 0
WBS 61 - Water Cooling Systems
| 611 - C-Site Cooling System | 153.3 | 0 | 153.3
| 612 - NB Water Cooling Systems | 239.9 | 0 | 239.9
| 613 - Vacuum Pumping System | 100 | 0 | 100
| 614 - Bakeout Water System | 38.5 | 0 | 38.5
Subtotal WBS 61 |  | 531.7 | 0 | 531.7
WBS 62 - Cryogenic Systems
| 621 - LN2-LHe Supply System | 252.9 | -28 | 224.9
| 622 - LN2 Coil Cooling Supply | 274.4 | -274.4 | 0
| 623 - GN2 Cryostat Cooling System | 220.2 | 2.3 | 222.5
Subtotal WBS 62 |  | 747.5 | -300.1 | 447.4
WBS 63 - Utility Systems
| 630 - Utility Systems | 120.9 | 1.8 | 122.7
Subtotal WBS 63 |  | 120.9 | 1.8 | 122.7
WBS 64 - PFC/VV Heating & Cooling Systems
| 640 - PFC/VV Heating & Cooling | 628.9 | -628.9 | 0
Subtotal WBS 64 |  | 628.9 | -628.9 | 0
WBS 65 - Facility Systems Integration
| 650 - Facility Systems Integration | 41.6 | 0 | 41.6
Subtotal WBS 65 |  | 41.6 | 0 | 41.6
WBS 71 - Shield Wall Modifications
| 710 - Shield Wall Seismic Modifications | 32.2 | 0 | 32.2
Subtotal WBS 71 |  | 32.2 | 0 | 32.2
WBS 72 - Control Room Refurbishment
| 720 - Control Room Refurbishment | 47.6 | 1.2 | 48.8
Subtotal WBS 72 |  | 47.6 | 1.2 | 48.8
WBS 73 - Platform Design & Fabrication
| 730 - Platform Design & Fabrication | 70 | 0 | 70
| 731 - Platform Design & Fabrication | 89.6 | 1.3 | 90.9
Subtotal WBS 73 |  | 159.6 | 1.3 | 160.9
WBS 74 - Machine Assembly Planning & Oversight
| 740 - Machine Assembly Planning and Oversight | 147.8 | 0.2 | 148
| 741 - Planning Prior to Machine Assembly | 281.6 | 0 | 281.6
| 742 - Construction Management | 1184.8 | 9.4 | 1194.2
Subtotal WBS 74 |  | 1614.2 | 9.6 | 1623.8
WBS 75 - Test Cell & Baasement Assembly Operations
| 750 - Test Cell & Basement Assembly Operations | 2160 | 24.9 | 2184.9
Subtotal WBS 75 |  | 2160 | 24.9 | 2184.9
WBS 76 - Tooling Design & Fabrication
76 - 76 - Tooling Design & Fabrication |  | 223.7 | 0 | 223.7
Subtotal WBS 76 |  | 223.7 | 0 | 223.7
WBS 81 - Project Management & Control
| 810 - Project Management & Control | 3354.3 | 202.5 | 3556.8
Subtotal WBS 81 |  | 3354.3 | 202.5 | 3556.8
WBS 82 - Project Engineering
| 820 - Project Engineering | 4723.1 | -709.4 | 4013.7
Subtotal WBS 82 |  | 4723.1 | -709.4 | 4013.7
WBS 84 - Project Physics
| 840 - Project Physics | 507.7 | -95.5 | 412.2
Subtotal WBS 84 |  | 507.7 | -95.5 | 412.2
WBS 85 - Integrated Systems Testing
| 850 - Integrated Systems Testing | 1225 | -4.9 | 1220.1
Subtotal WBS 85 |  | 1225 | -4.9 | 1220.1
AA - PPPL Allocations
| AA - PPPL Allocations | 983.3 | 0 | 983.3
Subtotal PPPL Allocations |  | 983.3 | 0 | 983.3
NCSX Performance Baseline |  | 73658.8 | -769.4 | 72889.4
CC - Contingency |  | 12695 | 760 | 13455
NCSX TEC |  | $86.3M |  | $86.3M