| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Ron Strykowsky |  |  | Date: November 9, 2004 (Rev 1) |  |
| ECP No: 016 |  | ECP Title: Reprogramming for FY-04 Closeout |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: M. Kalish (WBS 13), R. Ramakrishnan (WBS 432), B. Blanchard (WBS 21), D. Williamson (WBS 14) , B. Nelson (WBS 1), M. Cole (WBS 19), L. Dudek (WBS 61), P. Goranson (WBS 12), A. vonHalle (WBS 4), R. Strykowsky (Project Control), W. Reiersen (NCSX Engineering Manager), H. Neilson (NCSX Project Manager) |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: 3 Project Approving Official: 3 Project |  |  |  |  |
| Actions - Revise cost and schedule baselines and WAFs to reflect these changes. |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Under Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Ron Strykowsky | Date: October 15, 2004 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: Determination made that specific job scopes are not needed to satisfy CD-4 requirements and that budget made available will be reprogrammed augment the budgets for existing work scope in which the scope is determined to be more complex and costly than originally planned. Net impact is a zero cost. Impacted WBS Elements: - Jobs in which funds being reprogrammed from: - WBS 133 Job 1354 – trim coil system. Reprogramming $200K by adopting a simplified initial trim coil system that is adequate for CD-4 and initial research phases. - WBS 21 – fueling system. Reprogramming $60K by adopting a simplified initial fueling system. The ability to inject one gas species at a time is adequate for CD-4 and initial research phases. - WBS 432 Jobs 4310 and 4350 – D to C site systems. Reprogramming $439K of budget and FY2004 costs. This scope has been reclassified as a non-MIE NCSX scope. - WBS 612 - NB Cooling System. Reprogramming ~$240K by deleting scope that exceeds CD-4 requirements. - WBS 614 – Bakeout Water System. Reprogramming 38K by deleting scope that exceeds CD-4 requirements. - Job in which funds to be reprogrammed: - WBS 121 Job 1202 – VV R&D. Added $15K. - WBS 141 Job 1404 – MCWF R&D. Added $93K for prototype and contract admin oversight. - WBS 142 Job 1403 – Mod coil final design. Added $139K. - WBS 144 Job 1407 – MC winding facility. Added 507K for additional winding tooling, fixtures, and hardware complexity. - WBS 19 Job 1901 – Stellarator core management and oversight. Added $30K. - WBS 82 Job 8202 and 8203 – Engineering management and design integration. Added $193K. Impacts of Change (Briefly Describe): None Assessment of Other Options: None |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Ron Strykowsky | Date: October 15, 2004 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. None Description of Change: Included above. |  |