| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: W. Reiersen | Date: November 19, 2004 |
| ECP No: 018 | ECP Title: FY2005 Re-planning |
| Required Reviewers |
| Required Reviewers for this ECP: Neilson, Zarnstorff, Reiersen, Heitzenroeder, Viola, Williamson, Goranson, Kalish, Nelson, Brown, Cole, Chrzanowski, Dudek, Johnson, Ramakrishnan, Perry, Malsbury, Levine |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: Note: Change is a Level 2 because it requires use of contingency funds |
| Actions Update TF Design Description (Kalish, 12/04) Update Field Period Assembly Plan (Brown. 1/05) Update Final Assembly Plan (Brown, 1/05) |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: W. Reiersen | Date: November 19, 2004 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: To replan forward remaining work scope (including previously reported uncompleted tasks) and strategically re-estimate scope based upon the current evolution of design. This is necessary to ensure consistency with FY2005 funding guidance and to establish near term manpower plans. No changes are proposed to level I or II milestones. No changes are proposed to the CD-4 deliverables. No changes are proposed to the annual funding levels including the TEC of $86.3M. This re-planning needs to be incorporated into a revised Resource Loaded Schedule (RLS). In addition, there are areas where [1] cost and schedule have been re-estimated; and [2] technical changes have been made which have cost and schedule impacts. Impacted WBS Elements: 12-Vacuum Vessel, 13-Conventional Coils, 14-Modular Coils, 15 – Structures, 18-Field Period Assembly, 19-Stellarator Core Management and Integration, 3-Diagnostics, 4-Power Systems, 5-Central I&C, 7-Test Cell Preparations and Machine Assembly, and 8-Project Oversight and Support Impacts of Change (Briefly Describe): The impacts of the changes are that: The RLS has adequate detail in FY05 for earned value reporting Improved cost and schedule estimates for all work packages have been incorporated into the RLS including the effects of rate changes and schedule optimizations. Major improvements in the cost and schedule estimates for Field Period Assembly (WBS 18) and Final Assembly (WBS 75) are reflected in the proposed baseline. Cost and schedule impacts for a re-designed TF coil are reflected in the proposed baseline. The new TF design eliminates the need to machine the nose of the winding after coil fabrication resulting in reduced risk of chip inclusion in the insulation and improved reliability. The Level 2 milestone for award of the TF coil contract has been slipped from July 2005 to October 2005 with no impact on critical path milestones. The new estimates include both increases and decreases at the job level, but a net increase overall. Therefore, this change requires use of $402K in contingency funds. Assessment of Other Options: No other options exist for improving the level of detail in the RLS for FY05 and incorporating our best cost and schedule estimates. The change in the TF design was motivated by a desire to minimize the risks associated with machining the nose of the winding. Not adopting that change would have resulted in higher technical risk. Periodically updating the estimates for all remaining work is necessary to surface and resolve latent issues before they materialize. Failure to do so would increase cost and schedule risks. It is most efficiently done in conjunction with the detailed planning at the start of a fiscal year. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: W. Reiersen | Date: November 19, 2004 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. Attachments Reconciliation Table of Costs by WBS Revised Resource Loaded Schedule Impacted Documents TF Design Description Field Period Assembly Plan Final Assembly Plan Description of Change: Revised Resource Loaded Schedule and Reconciliation Table attached. Table below provides a summary description of changes by WBS. ECP-016 Baseline ECP-018 Baseline Delta 1. Stellarator Core 49,976.9 50,655.9 +679.0 +1.4% 11 Limiters 0.1 0.1 +0.0 +0.0% 12 Vacuum Vessel 8,546.0 8,737.4 +191.4 +2.2% Weld joint test sample, VVSA oversight, lateral supports. 13 Conventional coils 4,103.7 4,441.1 +337.4 +8.2% Re-estimate of new design. 14 Modular Coils 25,794.1 26,200.4 +406.3 +1.6% MCWF Prototypes, Title III, & Analysis; TRC oversight 15 Coil Structures 1,447.8 1,380.7 -67.1 -4.6% Re-estimate/reallocate design labor. 16 Coil Services 1,036.9 1,036.0 -0.9 -0.1% Rates, escalation, etc. 17 Cryostat & Base 1,301.1 1,321.1 +20.0 +1.5% Rates, escalation, etc. 18 Field Period Assy. 5,065.7 5,118.1 +52.4 +1.0% Re-estimate design and assembly labor. 19 Stellarator Int. & Mgt. 2,681.5 2,421.0 -260.5 -9.7% Re-estimate 2. Fueling & Pumping 777.0 778.3 +1.3 +0.2% Rates, escalation, etc. 3. Diagnostics 1,160.9 1,116.7 -44.2 -3.8% Eliminated double counting of magnetic sensor installation. 4. Power Systems 3,268.1 3,214.1 -54.0 -1.7% Eliminated 2nd-level outlets; re-estimate/re-allocate budgets 5. Central I&C / Data Acq. 2,188.8 1,915.2 -273.6 -12.5% Re-estimate design and programming labor. 6. Facility Systems 864.9 825.2 -39.7 -4.6% Rates, escalation, etc. 7. Test Cell Prep / Machine Assy. 4,274.4 4,207.9 -66.5 -1.6% Eliminate FY-06 oversight & planning; eliminate platform. 8. Project Mgt. & Integ. 9,396.6 9,450.9 +54.3 +0.6% Re-estimate PPPL Allocations 983.3 1,128.6 +145.3 +14.8% Revised budgets & allocation maps BCWS 72,890.9 73,292.8 +401.9 +0.6% Includes $120k due to rate changes. Contingency 13,455.0 13,052.9 -402.1 -3.0% EAC 86,345.9 86,345.7 -0.2 -0.0% |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: W. Reiersen | Date: November 19, 2004 |
| Continuation Sheet: Summary of Estimate Changes 14 Modular Coils +406.3 MCWF Prototypes, Title III, & Analysis; TRC oversight 13 Conventional coils +337.4 Re-estimate of new design. 12 Vacuum Vessel +191.4 Weld joint test sample, VVSA oversight, lateral supports. PPPL Allocations +145.3 Revised budgets & allocation maps 18 Field Period Assy. +52.4 Re-estimate design and assembly labor. 4. Power Systems -54.0 Eliminated 2nd-level outlets; re-estimate/re-allocate budgets 3. Diagnostics -44.2 Eliminated double counting of magnetic sensor installation. 15 Coil Structures -67.1 Re-estimate/reallocate design labor. 7. Test Cell Prep / Machine Assy. -66.5 De-scoped platform and re-estimated work. 19 & 8 Mgt./Integration -206.2 Re-estimate 5. Central I&C / Data Acq. -273.6 Re-estimate design and programming labor. Other -19.2 Total +401.9 |