| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: | Date: |
| ECP No: 18 | ECP Title: FY05 Re-planning |
| Required Reviewers |
| Required Reviewers for this ECP: Neilson, Zarnstorff, Reiersen, Heitzenroeder, Viola, Williamson, Goranson, Kalish, Nelson, Brown, Cole, Chrzanowski, Dudek, Johnson, Ramakrishnan, Perry, Malsbury, Levine |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: Note: Change is a Level 2 because it requires use of contingency funds |
| Actions Update TF Design Description (Kalish, 12/04) Update Field Period Assembly Plan (Brown. 1/05) Update Final Assembly Plan (Brown, 1/05) |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: | Date: |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: More detailed plans have been developed for the work to be accomplished in FY05. This re-planning needs to be incorporated into a revised Resource Loaded Schedule (RLS). In addition, there are areas where [1] cost and schedule have been re-estimated; and [2] technical changes have been made which have cost and schedule impacts. Impacted WBS Elements: 12-Vacuum Vessel, 13-Conventional Coils, 14-Modular Coils, 15 – Structures, 18-Field Period Assembly, 19-Stellarator Core Management and Integration, 3-Diagnostics, 4-Power Systems, 5-Central I&C, 7-Test Cell Preparations and Machine Assembly, and 8-Project Oversight and Support Impacts of Change (Briefly Describe): The impacts of the changes are that: The RLS has adequate detail in FY05 for earned value reporting Improved cost and schedule estimates for all work packages have been incorporated into the RLS including the effects of rate changes and schedule optimizations. Major improvements in the cost and schedule estimates for Field Period Assembly (WBS 18) and Final Assembly (WBS 75) are reflected in the proposed baseline. Cost and schedule impacts for a re-designed TF coil are reflected in the proposed baseline. The new TF design eliminates the need to machine the nose of the winding after coil fabrication resulting in reduced risk of chip inclusion in the insulation and improved reliability. The Level 2 milestone for award of the TF coil contract has been slipped from July 2005 to October 2005 with no impact on critical path milestones. The new estimates include both increases and decreases at the job level, but a net increase overall. Therefore, this change requires use of $377K in contingency funds. Assessment of Other Options: No other options exist for improving the level of detail in the RLS for FY05 and incorporating our best cost and schedule estimates. The change in the TF design was motivated by a desire to minimize the risks associated with machining the nose of the winding. Not adopting that change would have resulted in higher technical risk. Periodically updating the estimates for all remaining work is necessary to surface and resolve latent issues before they materialize. Failure to do so would increase cost and schedule risks. It is most efficiently done in conjunction with the detailed planning at the start of a fiscal year. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: | Date: |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. Attachments Reconciliation Table of Costs by WBS Revised Resource Loaded Schedule Impacted Documents TF Design Description Field Period Assembly Plan Final Assembly Plan Description of Change: Revised Resource Loaded Schedule and Reconciliation Table attached. Table below provides a summary description of changes by WBS. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: | Date: |
| Continuation Sheet: |