| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Ron Strykowsky |  |  | Date: October 25, 2005 |  |
| ECP No: 039 |  | ECP Title: Performance Measurement Baseline (PMB) Update – October 2005 |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: Paul Goranson, Brad Nelson, Dave Williamson, Mike Cole, Wayne Reiersen, H. Neilson, Judy Malsbury, Frank Malinowski, Jerry Levine, Ron Strykowsky |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |  |  |  |  |
| Actions - Update PMB by October 31st. |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Deputy Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-039 |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Ron Strykowsky | Date: October 25, 2005 |
| Overview of Change Type of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL Description and Reasons for Change: Summary: Approval of this ECP will require a drawdown of contingency of $2,357K from $11,969K in ECP-036 to $9,612K (~21.6% of remaining work scope). This ECP is a combination of replanned work and retirement of unrecoverable cost variances (work activity completed). The replanned work does not impact Level 3 or higher milestones. The breakdown of proposed changes is as follows: - Proposed PMB Updates (+$764K) - WBS 12 – Vacuum Vessel (+$106K) - WBS 121 Job 1203 – Vacuum Vessel Final Design (+$204K) – redesign of insulation scheme and cooling tubes. - WBS 122 and 123 Job 1204 – VV Non-VVSA Procurements (-$98K) – less expensive tubes and insulation due to redesign. - WBS 13 – Conventional Coils (-$188K) - WBS 131 Job 1361 - TF Coil Fabrication (+$432K) – replanned effort for facility, material, and winding operations. - WBS 132 Job Job 1302 – PF Coil Design & Fabrication (-$466K) – revised plan to use NSTX PF1a coil for central solenoid. - WBS 133 Job 1354 – Trim Coils Design and Fabrication (-$154K) – simplified design of trim coils. - WBS 14 – Modular Coils (+$1,227KK) - WBS 142 Job 1416 – Modular Coils Type A & B Final Design (+$520K) – replanned effort to reflect Type C experiences. - WBS 142 Job 1451 – Modular Coil Winding (-$17K) – increased effort for ground wrap, interlacing, and shift differential offset by supervision and oversight effort reduction due to shortened schedule. - WBS 142 Job 1408 – Mod Coil Winding Supplies (+$655K) – revised estimate to reflect experiences gained in the procurement of Type C1 shims and high strength bolts . - WBS 142 Job 1403 – Modular Coil Final Design (+$69K) – revised estimate of oversight (Title III) of contract based on experience gained on C1 casting. - WBS 18 – Field Period Assembly (-$90K) - Job 1810 – Field Period Asembly (-$40K) – eliminated requirement to bakeout field period assembly to 350°C. - Job 1803 – Field Period Assembly Tooling & Constructability (-$50K) – eliminated need for second set of assembly fixtures. |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-039 |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Ron Strykowsky | Date: October 25, 2005 |
| Overview of Change - WBS 3 – Diagnostics (-$42K) - WBS 31 Job 3101 – Magnetic Diagnostics (+$62K) – Redesign of saddle loops and termination box. - WBS 38 Job 3801 – E-Beam Mapping (-$104) – simplified application of e-beam mapping scheme. - WBS 55 Job 5501 – Plasma Control Systems (-$100K) – simplified plasma control system design. - WBS 81 – Project Management (-$54K) – reflects revised FY2009 estimate. - WBS 82 Job 8205 – Dimensional Control (+$84K) – reflects increased coordination between metrology and design integration efforts. - Various Miscellaneous WBS Elements – Rescheduling and Rate Changes (-$180K) - Unrecoverable Cost Variances – tasks completed (+$1,593K) - WBS 13 – Conventional Coils (+$268K) - WBS 131 Job 1301 – TF Design (+$109K) – unanticipated iterations on the TF design. - WBS 131 Job 1350 – TF Coil fabrication Preparations (+$149K) – unanticipated additional effort to finalize the design, increased material costs, and additional effort to debug electrical system. - WBS 14 – Modular Coils (+806K) - WBS 142 Job 1403 – Modular Coil Final Design (+$409K) – increased effort on the MCWF C Final Design to reflect experiences gained in the Twisted Racetrack Coil winding. - WBS 144 Job 1409 – Completion of Coil Test Facility (+$150K) – additional efforts required to debug cryogenic systems and to incorporate design safeguards into the facility. - WBS 141 Job 1404 – Fabrication of First Casting as Part of R&D Contract (+$137K) – additional costs associated with the fabrication of the first production casting. - WBS 142 Job 1403 – Modular Coil Final Design (+$110K) – additional Title III efforts to work with vendor to address technical requirements and schedule. - WBS 17 Job 1701 – Cryostat & Base Support Structure Design (+$178K) – underestimate of design and engineering effort needed. - WBS 43 Job 4301 – DC Power Systems (+$68K) – revised estimate for the design effort. - WBS 74 Job 7401 - Test Cell Preparations (+$178K) – additional efforts to restore/refurbish house power to ensure its availability for the NCSX test cell. - Various Miscellaneous WBS Elements – unrecoverable cost variances for work now completed (+$95K) |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-039 |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Ron Strykowsky | Date: October 25, 2005 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) Assessment of Other Options: None. No other offsets identified at this time. List Attachments, Impacted Documents, etc. - Budget Reconciliation Sheet - Revised Cost and Schedule Bar Charts for October 2005 Summary of Cost Impacts: WBS Element; Previous Baseline (ECP-036) ($); Current Baseline (ECP-039) ($); Change ($). 12 – Vacuum Vessel; $9,400K; $9,439K; +$39K. 13 – Conventional Coils; $4,790K; $4,831K; +$41K. 14 – Modular Coils; $29,114K; $31,356K; +$2,242K. 15 - Structures; $1,413K; $1,386K; -$27K. 16 – Coil Services; $1,140K; $1,135K; -$5K. 17 – Cryostat & Base Suppt Structure; $1,361K; $1,533K; +$172K. 18 – Field Period Assembly; $5,430K; $5,281K; -$149K. 19 – Stellarator Core Mgmt & Integration; $2,738K; $2,767K; +$29K. Subtotal WBS 1 – Stellarator Core; $55,385K; $55,728K; +$2,343K. WBS 2 – Auxiliary Systems; $783K; $791K; +$8K. WBS 3 – Diagnostic Systems; $1,143K; $1,149K; +$6K. WBS 4 – Electrical Power Systems; $3,301K; $3,305K; +$4K. WBS 5 – I&C Systems; $2,050K; $1,874K; -$176K. WBS 6 – Facility Systems; $691K; $679K; -$13K. WBS 7 Test Cell Prep & Machine Assembly; $4,473K; $4,555K; +$182K. WBS 8 – Project Oversight & Support; $11,053K; $11,025K; -$28K. Subtotal; $78,779K; $78,779K; +$797K. PPPL Allocations; $1,577K; $1,608K; +$32K. Contingency; $11,969K; $9,612K; -$2,357K. DCMA; 75k; 75k; -. TOTALS; $92,401K; $92,401K; -. Remaining contingency ($9,612K) is ~ 21.6% of remaining work. Although detailed schedules adjusted, no Level 3 or higher milestones are impacted. |

|  | Current Baseline (ECP-036) ($K) |  | Unrecoverable Cost Variances ($K) |  | ETC Updates & Design Changes ($K) |  | Total Budget Change ($K) |  | Proposed PMB (ECP-039) ($K) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12 - Vacuum Vessel Systems | 9,400 |  | (68) |  | 107 |  | 39 |  | 9,439 |
| 13 - Conventional Coils | 4,790 |  | 246 |  | (205) |  | 41 |  | 4,831 |
| 14 - Modular Coils | 29,114 |  | 1,044 |  | 1,198 |  | 2,242 |  | 31,356 |
| 15 - Structures | 1,413 |  | (1) |  | (26) |  | (27) |  | 1,386 |
| 16 - Coil Services | 1,140 |  |  |  | (5) |  | (5) |  | 1,135 |
| 17 - Cryostat and Base Support Struct | 1,361 |  | 178 |  | (6) |  | 172 |  | 1,533 |
| 18 - Field Period Assembly | 5,430 |  | (23) |  | (126) |  | (149) |  | 5,281 |
| 19 - Stellarator Core Mgt & Integr | 2,738 |  | 9 |  | 20 |  | 29 |  | 2,767 |
| 1 Stellarator Core Systems | 55,386 |  | 1,385 |  | 957 |  | 2,342 |  | 57,728 |
| 2 Heating, Fueling & Vac Sys | 783 |  |  |  | 8 |  | 8 |  | 791 |
| 3 Diagnostics | 1,143 |  | 18 |  | (12) |  | 6 |  | 1,149 |
| 4 Electrical Power Sys | 3,301 |  | 68 |  | (64) |  | 4 |  | 3,305 |
| 5 Central I&C Sys | 2,050 |  | (7) |  | (169) |  | (176) |  | 1,874 |
| 6 Facility Sys | 691 |  |  |  | (13) |  | (13) |  | 678 |
| 7 Test Cell Prep & MachAssy | 4,373 |  | 129 |  | 54 |  | 183 |  | 4,556 |
| 8 Project Oversight & Support | 12,630 |  | 1 |  | 3 |  | 4 |  | 12,634 |
| Subtotal PMB | 80,357 |  | 1,593 |  | 764 |  | 2,357 |  | 82,714 |
| Contingency | 11,969 |  | (1,593) |  | (764) |  | (2,357) |  | 9,612 |
| TEC = | 92,326 |  |  |  |  |  |  |  | 92,326 |
| DCMA | 75 |  |  |  |  |  |  |  | 75 |
| TOTALS - TPC | 92,401 |  |  |  |  |  |  |  | 92,401 |
|  |  |  |  |  |  |  | BCWR |  | 44,400 |
|  |  |  |  |  |  |  | Contingency Balance |  | 9,612 |
|  |  |  |  |  |  |  |  |  | 21.6% |