| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Ron Strykowsky | Date: January 28, 2005 |
| ECP No: 021 | ECP Title: Close Out of Jobs & Contingency Draw |
| Required Reviewers |
| Required Reviewers for this ECP: W. Reiersen, R. Strykowsky, Brad Nelson, J. Malsbury, R. Simmons, J. Levine, M. Zarnstorff, D. Williamson, P. Heitzenroeder |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Close Out Jobs and Draw Down on Contingency by January 31, 2005 Revise Master Resource Loaded Schedule to reflect ECP021 by January 31, 2005 |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: January 28, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: WBS 141 (Job 1404) MCWF Prototypes & First Production Casting – Additional $185K for final prototype cost, pre-production casting work, including additional laser scanning and pattern re-work. Should also include any adjustments in the original prototype workscope, either JPP or EIO. What drove the cost growth and why are the risks behind us?(we still don't have a firm estinate from EIO) WBS 142 (Job 1406) – Additional estimated costs of $229K for close-out of the winding R&D and Testing. Baseline budget underestimate the extent of required material testing (fatigue tests, conductor keystone testing) and fabrication of components for the twisted racetrack test. WBS 84 (Jobs 8401 & 8402) – Additional $58K for close-out of the project physics work scope, which was completed in FY-04. Cost growth was driven by additional physics effort required to support Title II design in FY-04, for example the redesign of the vacuum vessel shell geometry and port configuration. WBS 12 and 14 – re-optimized schedules for VVSA and MCWF fabrication to better reflect latest schedule projections of Major Tool and EIO – no cost impact. No impact to level I or II milestones. Project critical path totalk float reduced from 5 months to 4 1/2 months however due to the estimated MCWF delivery WBS 18 – re-optimized field period assembly tooling design and fabrication activities to reflect revised plans – no cost impact. No impact to milestones or critical path. Impacts of Change (Briefly Describe): Budget: Requesting contingency draw down of $472K, reducing remaining contingency from $13,053 to $12,581. Schedule: Critical path total float from 5.0 months to 4.5 months Assessment of Other Options: None |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: January 28, 2005 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. ECP-018 to ECP-021 Reconciliation Updated Primavera Barcharts for ECP-021 Description of Change: We are reflecting the estimated costs at completion of several jobs that are being closed or near the end of their period of performance. These final costs will require a contingency draw of $472K. In addition, several jobs have been re-optimized to better reflect supplier schedules and revised plans. These re-optimized jobs have no budget impact. |