| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Ron Strykowsky | Date: January 28, 2005 |
| ECP No: 021 | ECP Title: Close Out of Jobs & Contingency Draw |
| Required Reviewers |
| Required Reviewers for this ECP: W. Reiersen, R. Strykowsky, Brad Nelson, J. Malsbury, R. Simmons, J. Levine, M. Zarnstorff, D. Williamson, P. Heitzenroeder |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Close Out Jobs and Draw Down on Contingency by January 31, 2005 Revise Master Resource Loaded Schedule to reflect ECP021 by January 31, 2005 |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: January 28, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: WBS 141 (Job 1404 – MCWF R&D & 1st Production Casting) – Additional $185K for pre-production casting work, including additional laser scanning and pattern re-work. Should also include any adjustments in the original prototype workscope, either JPP or EIO. What drove the cost growth and why are the risks behind us? WBS 142 (Job 1406 – Modular Coil Winding R&D Preparations) – Additional estimated costs of $229K for close-out of the winding R&D and Testing. What drove the cost growth in this job and why are the risks behind us? WBS 84 (Jobs 8401 and 8402 – PPPL and ORNL Project Physics) – Additional $58K for close-out of the project physics work scope, which was completed in FY2004. Cost growth was driven by additional physics effort required to support Title II design in FY2004 (e.g., the redesign of the vacuum vessel shell geometry and port configuration). WBS 12 and 14 – re-optimized fabrication schedules for VVSA and MCWF to better reflect latest schedule projections of Major Tool and EIO – no cost impact. As a result to the re-optimization of the MCWF fabrication schedule, the critical path float has been reduced by two weeks from 5 months to approximately 4.5 months. There are no impacts on either Level 1 or Level 2 milestones. WBS 18 – re-optimized field period assembly tooling design and fabrication activities to reflect revised plans – no cost impact. There are no impacts on Level 1 or Level 2 milestones or on the critical path. Impacts of Change (Briefly Describe): Budget: Requesting contingency draw down of $472K, reducing remaining contingency from $13,053K to $12,581K. Schedule: No impact on Level 1 or Level II milestones. However, due to the re-optimization of the MCWF fabrication schedule the critical path float has been reduced by two weeks from 5 months to 4.5 months. Assessment of Other Options: None |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: January 28, 2005 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. ECP-018 to ECP-021 Reconciliation Updated Primavera Barcharts for ECP-021 Description of Change: We are reflecting the estimated costs at completion of several jobs that are being closed or near the end of their period of performance. These final costs will require a contingency draw of $472K. In addition, several jobs have been re-optimized to better reflect supplier schedules and revised plans. These re-optimized jobs have no budget impact. |