| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Ron Strykowsky |  |  | Date: January 28, 2005 |  |
| ECP No: 021 |  | ECP Title: Close Out of Jobs & Contingency Draw |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: W. Reiersen, R. Strykowsky, Brad Nelson, J. Malsbury, R. Simmons, J. Levine, M. Zarnstorff, D. Williamson, P. Heitzenroeder |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |  |  |  |  |
| Actions - Close Out Jobs and Draw Down on Contingency by January 31, 2005 - Revise Primavera Barcharts to reflect ECP021 by January 31, 2005 |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Under Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Ron Strykowsky | Date: January 28, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: - WBS 141 (Job 1404) – Additional $185K for pre-production casting work, including additional laser scanning and pattern re-work. - WBS 142 (Job 1406) – Additional estimated costs of $229K for close-out of the winding R&D and Testing - WBS 84 (Job 8481) – Additional $58 for close-out of FY2004 work. - WBS 12 and 14 – re-optimized schedules for VVSA and MCWF to better reflect latest schedule projections of Major Tool and EIO – no cost impact. - WBS 18 – re-optimized field period assembly tooling design and fabrication activities to reflect revised plans – no cost impact. Impacts of Change (Briefly Describe): Requesting contingency draw down of $472K. Assessment of Other Options: None |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Ron Strykowsky | Date: January 28, 2005 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. - ECP-018 to ECP-021 Reconciliation - Updated Primavera Barcharts for ECP-021 Description of Change: We are reflecting the estimated costs at completion of several jobs that are being closed or near the end of their period of performance. These final costs will require a contingency draw of $472K. In addition, several jobs have been re-optimized to better reflect supplier schedules and revised plans. These re-optimized jobs have no budget impact. |  |