| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Ron Strykowsky |  |  | Date: January 31, 2005 |  |
| ECP No: 021 |  | ECP Title: Close Out of Jobs & Contingency Draw |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: W. Reiersen, R. Strykowsky, Brad Nelson, J. Malsbury, R. Simmons, J. Levine, M. Zarnstorff, D. Williamson, P. Heitzenroeder |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |  |  |  |  |
| Actions - Close Out Jobs and Draw Down on Contingency by January 31, 2005 - Revise Master Resource Loaded Schedule to reflect ECP021 by January 31, 2005 |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Under Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Ron Strykowsky | Date: January 31, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: - WBS 142 (Job 1406 – Modular Coil Winding R&D Preparations) – Additional estimated costs of $239K for close-out of the winding R&D and Testing. Baseline budget underestimated the extent of required material testing (e.g., fatigue testing, conductor keystone testing, etc.) and fabrication of components for the twisted race track coil tests. - WBS 84 (Jobs 8401 and 8402 – PPPL and ORNL Project Physics) – Additional $58K for close-out of the project physics work scope, which was completed in FY2004. Cost growth was driven by additional physics effort required to support Title II design in FY2004 (e.g., the redesign of the vacuum vessel shell geometry and port configuration). - WBS 12 and 14 – re-optimized fabrication schedules for VVSA and MCWF to better reflect latest schedule projections of Major Tool and EIO – no cost impact. There is no impact on Level 1 or Level 2 milestones, or on the critical path. Impacts of Change (Briefly Describe): - Budget: Requesting contingency draw down of $297K, reducing remaining contingency from $13,053K to $12,756K. - Schedule: There are no impacts on Level 1 or Level 2 milestones, or on the critical path. Assessment of Other Options: None List Attachments, Impacted Documents, etc. - ECP-018 to ECP-021 Reconciliation - Update Master Resource Loaded Schedule for ECP-021 Description of Change: We are reflecting the estimated costs at completion of several jobs that are being closed or near the end of their period of performance. These final costs will require a contingency draw of $297K. There is no schedule impact to Level 1 or Level 2 milestones, or to the critical path. In addition, several jobs have been re-optimized to better reflect supplier schedules and revised plans. These re-optimized jobs have no budget or schedule impacts. |  |