| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Ron Strykowsky |  |  | Date: March 2, 2005 |  |
| ECP No: 024 |  | ECP Title: Miscellaneous Rescheduling and Contingency Draw for Added and Re-Estimated Scope |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: P. Goranson, B. Nelson, M. Kalish, W. Reiersen, E. Perry, G. Gettlefinger, T. Brown, J. Levine, J. Malsbury |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |  |  |  |  |
| Actions - Revise VVSA Schedule to reflect revised delivery schedules - Add Dimensional Coordinator to WBS 82 – prepare WAF => contingency draw of $58K - Retire FY2004 Scope for WBS 81 => contingency draw of $146K - Revise Master Schedule to reflect revised schedules in WBS 15, WBS 172, WBS 18, & WBS 7 - Rescheduled WBS 13 job 1301 final design of the TF coil system from 2/28/05 to 5/1/05 => contingency draw of $XXK |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Under Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Ron Strykowsky | Date: march 2, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: Miscellaneous rescheduling , added and re-estimated scope. Will require contingency draw of ~ $XXK. Impacted WBS Elements: WBS 12, WBS 82, WBS 15, WBS 172, WBS 18, & WBS 7 Impacts of Change (Briefly Describe): 1) The VVSA contract with MTM was rescheduled to factor in the latest forecasted deliveries. No changes were made to the cost estimate. The first vessel shell is now planned for 11/30/04, the second and third shell are now planned for 2/28/06 which is the same as our level II milestone of Feb06 for vessel delivery. Also, we broke out as separate deliveries the ports and spacer now planned for 6/1/06. The free float for the above (relative to the critical path and baseline funding profile) is; VVSA#1 2.0mo, VVSA#2 4.4mo, VVSA#3 7.1mo, ports 7.6mo. 2)New scope; Dimensional control coordinator for FY05 WBS 82 job 8205 (FY06 and beyond estimate TBD) Brent Stratton 25% time with travel = $58.158k contingency draw. 3)Prior year scope retirement WBS 81 job 8101 PPPL project management effort for FY04. $146k contingency draw. 4)Misc schedule realignments for completed scope and yet to be started tasks; no cost impact; 4a)WBS 7 Job 7401 Test Cell mods and upgrades, job 7301 platform design and fabrication, job 7201 control room walls and floors 4b) WBS 18 job 1803 Field period assembly tooling and fixturing design. Rescheduled based on designer leveling. 4c) WBS 172 job 1701 Rescheduled start of final design for base support structure from 12/15/04 to 4/4/05. 4D) WBS 15 job 1501 rescheduled start of the coil support structure from 3/1/05 to 5/1/05 5) Rescheduled WBS 13 job 1301 final design of the TF coil system from 2/28/05 to 5/1/05. Re-estimated final design. Cost increase to be drawn from contingency = $________. |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Ron Strkowsky | Date: march 2, 2005 |
| Continuation Sheet: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) Total draw on contingency; $204 + $_____ = $_____. Contingency reduced from $12,756K to $YYYYK. Assessment of Other Options: None |  |