## Sheet1
| MIE |  |  |  | BO
| PPPL | ORNL | TOTAL
FY03 BA | 6577 | 1320 | 7897
FY03 Spent | -4796 | -1146 | -5942 |  | 5942
0
0
FY03/04 CO | 1781 | 174 | 1955
FY04 BA | 14415 | 1506 | 15921
FY04 Budget | 16196 | 1680 | 17876
0
fin plan feb04 pppl to ornl | -600 | 600 | 0
fin plan mar04 pppl to ornl | -311 | 311 | 0
fin plan jun04 pppl to ornl | -317 | 317 | 0
fin plan 04 pppl to ornl | -75 | 75 | 0
fin plan 04 pppl to indirect equipt (out of project) | -75 |  | -75
spent FY04 | -11392 | -2847 | -14239 |  | 14239 | 20181
0
0
FY04/05 CO | 3426 | 136 | 3562
FY05 FWP | 14400 | 1500 | 15900
FY05 Initial guidance (DOE tax removed from project | -100 | 0 | -100
FY05 credit for FY04 cost on pwr systems (reclassified from MIE to Upgrade) | 439 | 0 | 439 |  | -439
FY05 Budget | 18165 | 1636 | 19801 |  | 19801 | 39543
0
FY06 BA Plan |  |  | 22100 |  | 22310
FY07 BA Plan |  |  | 19400 |  | 19280
FY08 BA Plan |  |  | 5100 |  | 5584
0
0
MIE Total |  |  | 86143 |  | 86717
|  |  | 0 | 86346
203
0
0
0
0
0
0

## BY organization
RES | None | FY 2003 | FY 2004 | FY 2005 | FY 2006 | FY 2007 | FY 2008 | TOTAL
| 35 - PPPL Travel |  | 110.47 | 174.31 | 119.92 | 46.25 | 13.76 | 464.71
| 41 - PPPL M&S | 1029.53 | 2399.22 | 3213.99 | 4224.04 | 4799.99 | 1826.26 | 17493.03
| 41MYATT - $k myatt at 125 hr |  | 126.32 | 38.22 |  |  |  | 164.54
| 41TITUS - $k ritus at 124 hr |  | 66.8 |  |  |  |  | 66.8
| 48 - |  | 543.09 | 7716.04 | 5919.57 | 900 |  | 15078.7
| 4E - PPPL M&S exempt |  | 85 |  | 749.93 | 728.51 |  | 1563.45
| 54 - Allocations |  | 265.92 | 314.33 | 320.75 | 166.89 |  | 1067.89
| 81 - no G&A cost | 3741.48 | 1500.33 | 100 |  |  |  | 5341.81
| B///CB - PPPL Project Clerical |  | 28.29 | 49.09 | 49.98 | 41.99 | 10.5 | 179.85
| EA//EM - PPPL Analysis engineer |  | 1980.95 | 2238.71 | 2070.9 | 1089.84 | 253.37 | 7633.77
| EA//SM - PPPL Designer |  | 413.27 | 611.79 | 803.54 | 387.03 | 4.62 | 2220.25
| EC//EM - PPPL Comuter Engineer |  | 12.36 | 12.9 | 67.34 | 914.36 | 71.57 | 1078.52
| EC//SM - PPPL Computer Senior Tech |  |  |  |  | 175.34 |  | 175.34
| EE//AM - |  | 6.84 | 14.29 | 14.84 | 15.41 |  | 51.38
| EE//EM - PPPL Electrical engineer |  | 101.93 | 323.17 | 557.55 | 460.77 | 228.59 | 1672.02
| EE//SM - PPPL Electrical Senior Tech |  | 124.88 | 59.33 | 497.99 | 629.68 | 216.6 | 1528.48
| EE//TB - PPPL Electrical Technician |  | 7.33 | 51.72 | 197.64 | 259.76 | 75.02 | 591.47
| EM//EM - PPPL FO&M Engineer | 24.9 | 728.17 | 575.08 | 622.66 | 1741.33 | 653.57 | 4345.7
| EM//SM - PPPL FO&M Senior Tech |  | 565.83 | 517.26 | 724.87 | 1445.82 | 813.7 | 4067.48
| EM//TB - PPPL FO&M Technician |  | 1051.29 | 1280.78 | 3087.57 | 3583.64 | 781.16 | 9784.44
| FC//AM - PPPL P&CO am |  | 116.86 | 216.69 | 220.82 | 204.71 | 70.55 | 829.64
| FC//EM - PPPL P&CO em |  | 234.57 | 174.64 | 141.69 | 35.33 | 0.14 | 586.38
| ORNL35 - ORNL Travel |  | 4.16 | 3.18 | 2.16 | 2.21 | 4.42 | 16.13
| ORNL41 - ORNL M&S |  | 34.28 | 33.8 | 32.06 | 33.33 |  | 133.46
| ORNL81 - ORNL cost | 1146.37 | 439 |  |  |  |  | 1585.37
| ORNLAM - ORNL Admin |  | 51.49 | 26.76 | 13.98 |  |  | 92.23
| ORNLEM - ORNL Engineer |  | 1942.97 | 1434.04 | 974.66 | 373.57 | 117.54 | 4842.78
| ORNLRM - ORNL Scientist |  | 122.57 | 63.6 | 92.37 | 48.92 |  | 327.46
| R///RM2 - PPPL Scientist pdg2 |  | 126.12 | 47.15 | 53.13 | 59.1 | 84.1 | 369.6
| R///RM3 - PPPL Scientist pdg3 |  | 550.92 | 378.85 | 345.84 | 257.07 | 44.34 | 1577.02
| SH//TB - HP Techs |  | 115.32 | 142.13 | 144.38 | 0.58 |  | 402.42
| XORNL - contingency-ornl | 0 | 0 | 0 | 0 | 780 | 234 | 1014
|  | 5942.28 | 13856.55 | 19811.85 | 22050.18 | 19181.43 | 5503.81 | 86346.12
| PPPL | 4795.91 | 11262.08 | 18250.47 | 20934.95 | 17943.4 | 5147.85 | 78334.69
| BA |  |  | 14300
| Carryover |  |  | 3426
| credit (FY04 pwr sys xfr) |  |  | 439
| Total Budget |  |  | 18165
| ORNL | 1146.37 | 2594.47 | 1561.38 | 1115.23 | 1238.03 | 355.96 | 8011.43
| BA |  |  | 1500
| Carryover |  |  | 136
| Total Budget |  |  | 1636

## WBS III by year
WBS2 | DESC | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | TOTAL
11 | 111 - Limiters | 0.06 | [5 empty] | 0.06
12 | 121 - Vacuum Vessel Assembly | 1183.01 | 1619.71 | 3952.35 | 1300.47 | 5.75 |  | 8061.3
12 | 122 - Vacuum Vessel Thermal Insulation |  | 10.17 | 53.48 | 112.38 |  |  | 176.03
12 | 123 - Vacuum Vessel Heating and Cooling Distrib |  | 14.93 | 24.06 | 334.38 |  |  | 373.37
12 | 124 - Vacuum Vessel Supports |  | 10.17 | 46.5 | 40.27 | 0.7 |  | 97.63
12 | 125 - Vacuum Vessel Local I&C |  |  | 24.21 | 4.83 |  |  | 29.04
13 | 130 - Conventional Coil Design | 91.66 | 335.85 | 238.23 |  |  |  | 665.75
13 | 131 - TF Coils |  |  | 418.63 | 844 | 221.99 |  | 1484.61
13 | 132 - PF Coils |  |  | 140.09 | 360.04 | 1370.3 |  | 1870.43
13 | 133 - External Trim Coils |  |  |  | 27.89 | 118.21 |  | 146.1
13 | 134 - Conventional Coil Local |  |  |  |  | 92.63 |  | 92.63
14 | 141 - Modular Coil Winding Form | 1106.41 | 3141.76 | 5176.98 | 3755.52 |  |  | 13180.68
14 | 142 - Modular Coil Windings and Assembly | 1028.98 | 1433.68 | 2807.56 | 3594.77 | 758.99 |  | 9623.99
14 | 143 - Modular Coil Local I&C |  |  |  | 51.31 | 69.11 |  | 120.42
14 | 144 - Modular Coil Winding Facility & Fixtures | 267.55 | 2645.09 | 372.58 |  |  |  | 3285.22
15 | 151 - Coil Support Structure |  | 53.67 | 170.74 | 949.84 | 206.58 |  | 1380.84
16 | 161 - LN2 Distribution |  |  |  | 199.88 | 137.34 |  | 337.22
16 | 162 - Electrical Leads |  |  |  | 236.91 | 357.38 | 24.73 | 619.03
16 | 163 - Coil Protection System |  |  |  | 78.86 |  |  | 78.86
17 | 171 -Cryostat | 12.18 | 107.56 | 72.31 | 244.71 | 433.72 | 5.57 | 876.05
17 | 172 - Base Support Structure |  | 42.93 | 70.12 | 330.4 |  |  | 443.45
18 | 181 - Field Period Assembly Planning/Oversight | 60.8 | 219.19 | 189.53 | 364.09 | 180.81 |  | 1014.42
18 | 183 - Receive Inspect and Test Coils |  |  |  | 58.4 | 20.71 |  | 79.12
18 | 184 - Receive Inspect and Test VV |  |  |  | 483.98 | 46.16 |  | 530.14
18 | 185 - Assemble Field Periods |  |  |  | 393.82 | 1431.12 |  | 1824.94
18 | 186 - Tooling Design and Fabrication |  |  | 600.05 | 588.24 | 9.81 | 0.04 | 1198.13
18 | 187 - Measurement Systems |  | 241.41 | 173.56 | 60.86 |  |  | 475.83
19 | 191 - Stellarator Core Management & Oversight | 187.09 | 175.7 | 170.65 | 169.99 | 179.99 | 63.02 | 946.44
19 | 192 - Stellarator Core Integration & Analysis | 67.07 | 524.77 | 409.09 | 270.16 | 137.22 | 66.28 | 1474.58
21 |  |  |  |  | 41.01 | 39.71 |  | 80.72
22 |  | 60.2 |  |  | 102.44 | 223.93 |  | 386.56
25 | 250 - Neutral Beam Injection System | 146.31 | 162.57 |  |  |  |  | 308.88
31 |  |  |  | 200.82 | 213 |  |  | 413.82
36 | [5 empty] | 42.87 |  | 42.87
38 | [5 empty] | 290.58 |  | 290.58
39 |  | 155.45 | 78.02 | 67.3 | 68.63 |  |  | 369.41
41 | 411 - Auxliary AC Power Systems |  | 157.23 |  | 140.3 | 142.3 |  | 439.83
41 | 412 - Experimental AC Power Systems |  |  |  | 17.07 | 27.95 |  | 45.02
43 | 431 - C-Site DC Systems |  |  | 239.33 | 206.19 |  |  | 445.52
44 | 441 - Electrical Interlocks |  |  |  | 334.71 | 8.79 |  | 343.5
44 | 442 - Kirk Key Interlocks |  |  |  | 28.04 | 49.76 |  | 77.8
44 | 443 - Real Time Control Systems |  |  |  | 10.53 | 2.82 |  | 13.35
44 | 444 - Instrument Systems |  |  |  | 148.35 | 145.85 |  | 294.19
44 | 445 - Coil protection Systems |  | 1.05 |  | 373.14 | 111.72 |  | 485.91
45 | 451 - System Design and Interfaces | 112.34 | 34.18 | 163.19 | 114.85 | 90.61 |  | 515.17
45 | 452 - Electrical Systems Support |  |  |  | 153.43 | 88.36 |  | 241.79
45 | 453 - System Testing (PTP's) |  |  |  | 65.25 | 240.25 |  | 305.49
46 | 460 | 1.3 | [5 empty] | 1.3
51 |  | 11.9 | 12.36 |  | 4 | 260.66 |  | 288.92
52 |  |  |  |  | 36.51 | 532.84 |  | 569.35
53 |  |  |  |  | 24.84 | 303.52 |  | 328.36
54 | [5 empty] | 206.79 |  | 206.79
55 | [5 empty] | 151.25 |  | 151.25
56 | [5 empty] | 357.66 |  | 357.66
58 |  |  |  | 12.9 |  |  |  | 12.9
61 | 611 - C-Site Cooling System |  |  |  |  | 151.1 |  | 151.1
61 | 613 - Vacuum Pumping System |  |  |  |  | 89.35 |  | 89.35
62 | 621 - LN2-LHe Supply System |  |  |  |  | 220.93 |  | 220.93
62 | 622 - LN2 Coil Cooling Supply
62 | 623 - GN2 Cryostat Cooling System |  |  |  |  | 218.66 |  | 218.66
63 | [5 empty] | 103.48 |  | 103.48
65 | 612 - NB Water Cooling Systems | 9.38 | [5 empty] | 9.38
65 | 650 - Facility Systems Integration |  | 32.22 |  |  |  |  | 32.22
71 | 740 - Machine Assembly Planning and Oversight | 32.15 | [5 empty] | 32.15
72 |  |  |  | 50.21 |  |  |  | 50.21
73 | 730 - Test Cell & Basement Assembly Operations |  |  | 91.57 | 69.69 |  |  | 161.26
74 | 740 - Machine Assembly Planning and Oversight |  | 89.67 | 62.88 |  |  |  | 152.55
74 | 741 - Planning Prior to Machine Assembly | 131.68 | 149.89 |  |  |  |  | 281.57
74 | 742 - Construction Management |  |  | 114.78 | 116.09 | 457.26 | 380.03 | 1068.15
75 | 750 - Test Cell & Basement Assembly Operations |  |  |  | 153.55 | 1394.83 | 635 | 2183.38
76 |  |  |  |  | 79.16 | 141.68 |  | 220.85
81 | 810 - Project Management & Control | 445.94 | 850.77 | 751.63 | 693.83 | 549.98 | 126.31 | 3418.46
82 | 820 - Project Engineering | 518.9 | 1285.13 | 1036.81 | 877.76 | 408.47 | 102.47 | 4229.54
84 | 840 - Project Physics | 251.25 | 160.92 |  |  |  |  | 412.17
85 | [5 empty] | 558.84 | 664.1 | 1222.94
AA | PPPL Allocations | 60.67 | 265.92 | 314.33 | 320.75 | 166.89 |  | 1128.56
CC | Contingency | 0 | 0 | 1595.38 | 2801.05 | 5623.26 | 3436.27 | 13455.96
|  | 5942.28 | 13856.52 | 19811.85 | 22050.17 | 19181.47 | 5503.82 | 86346.12
| BA plus carryover |  |  | 19801 | 22100 | 19400 | 5100

## ECP14 ECP17 Reconciliation
NCSX FY05 ECP-21 reconciliation
wbs2 |  |  | ECP 14 | ECP 16 | change | description | ECP 18 | change | description | ECP 21 | ECP 24 | change | description
11 - In-Vessel Components |  | 111 - Limiters | 0.1 | 0.1 |  |  | 0.1 | 0 |  | 0.1 |  | 0 |  | 11 | 111 - Limiters | 0
| 12 - Vacuum Vessel Systems |  |  | 0 |  |  |  | 0 |  |  |  | 0
12 - Vacuum Vessel Systems |  | 121 - Vacuum Vessel Assembly | 7891.7 | 7906.3 | 14.6 | ECP 16 FY04 cost variance +14.6k | 8061.3 | 155 | .Increased Viola to 2 days /week oversight +$63k; Increased field weld joint full size sample =+$96k | 8061.3 | 8061.3 | 0 |  | 12 | 121 - Vacuum Vessel Assembly | 8065
12 - Vacuum Vessel Systems |  | 122 - Vacuum Vessel Thermal Insulation | 174.7 | 174.7 |  |  | 176.03 | 1.33 |  | 176.03 | 176.03 | 0 |  | 12 | 122 - Vacuum Vessel Thermal Insulation | 176
12 - Vacuum Vessel Systems |  | 123 - Vacuum Vessel Heating and Cooling Distrib | 375.7 | 375.7 |  |  | 373.37 | -2.33 |  | 373.37 | 373.37 | 0 |  | 12 | 123 - Vacuum Vessel Heating and Cooling Distrib | 373
12 - Vacuum Vessel Systems |  | 124 - Vacuum Vessel Supports | 62 | 62 |  |  | 97.63 | 35.63 | .Lateral supports +22k | 97.63 | 97.63 | 0 |  | 12 | 124 - Vacuum Vessel Supports | 98
12 - Vacuum Vessel Systems |  | 125 - Vacuum Vessel Local I&C | 27.3 | 27.3 |  |  | 29.04 | 1.74 |  | 29.04 | 29.04 | 0 |  | 12 | 125 - Vacuum Vessel Local I&C | 29
|  | subtotal | 8531.4 | 8546 | 14.6 |  | 8737.37 | 191.37 |  | 8737.37 | 8737.37 | 0
| 13 - Conventional Coils |  |  | 0 |  |  |  | 0 |  |  |  | 0
13 - Conventional Coils |  | 130 - Conventional Coil Design | 613.1 | 613.1 |  |  | 737.81 | 124.71 | Kalish re-estimate of new design | 737.81 | 849 | 111.19 | Completion of Prelim design and the re-estimate of final design tasks. | 13 | 130 - Conventional Coil Design | 849
13 - Conventional Coils |  | 131 - TF Coils | 1458.8 | 1458.8 |  |  | 1594.58 | 135.78 | Kalish re-estimate of new design | 1594.58 | 1594.58 | 0 |  | 13 | 131 - TF Coils | 1584
13 - Conventional Coils |  | 132 - PF Coils | 1777.3 | 1777.3 |  |  | 1870.43 | 93.13 | Kalish re-estimate | 1870.43 | 1870.43 | 0 |  | 13 | 132 - PF Coils | 1870
13 - Conventional Coils |  | 133 - External Trim Coils | 381.1 | 181.1 | -200 | ECP 16 simplification of trim coli sys -200k | 145.64 | -35.46 | Kalish re-estimate | 145.64 | 145.64 | 0 |  | 13 | 133 - External Trim Coils | 146
13 - Conventional Coils |  | 134 - Conventional Coil Local | 73.4 | 73.4 |  |  | 92.63 | 19.23 | Kalish re-estimate | 92.63 | 92.63 | 0 |  | 13 | 134 - Conventional Coil Local | 93
|  | subtotal | 4303.7 | 4103.7 | -200 |  | 4441.09 | 337.39 |  | 4441.09 | 4552.28 | 111.19
| 14 - Modular Coils |  |  | 0 |  |  |  | 0 |  |  |  | 0
14 - Modular Coils |  | 141 - Modular Coil Winding Form | 12788.6 | 12881.6 | 93 | ECP 16 FY04 cost variance +93 | 13180.68 | 299.08 | +$52k MCWF analysis, +85 EIO s/c,+54 JPP s/c,+79 title III MCWF fab | 13180.68 | 13180.68 | 0 |  | 14 | 141 - Modular Coil Winding Form | 13181
14 - Modular Coils |  | 142 - Modular Coil Windings and Assembly | 9438 | 9577 | 139 | ECP 16 FY04 cost variance +139. | 9614.03 | 37.03 | Chrzanowski/Meighan oversight of TRC +202k | 9853 | 9853 | 0 |  | 14 | 142 - Modular Coil Windings and Assembly | 9854
14 - Modular Coils |  | 143 - Modular Coil Local I&C | 121.2 | 121.2 |  |  | 120.42 | -0.78 |  | 120.42 | 120.42 | 0 |  | 14 | 143 - Modular Coil Local I&C | 120
14 - Modular Coils |  | 144 - Modular Coil Winding Facility & Fixtures | 2707.3 | 3214.3 | 507 | ECP 16 FY04 cost variance +507 | 3285.22 | 70.92 |  | 3285.22 | 3285.22 | 0 |  | 14 | 144 - Modular Coil Winding Facility & Fixtures | 3285
|  | subtotal | 25055.1 | 25794.1 | 739 |  | 26200.35 | 406.25 |  | 26439.32 | 26439.32 | 0
| 15 - Structures |  |  | 0 |  |  |  | 0 |  |  |  | 0
15 - Structures |  | 151 - Coil Support Structure | 1447.8 | 1447.8 |  |  | 1380.71 | -67.09 | Kalish re-estimate | 1380.71 | 1380.71 | 0 |  | 15 | 151 - Coil Support Structure | 1383
| 16 - Coil Services |  |  | 0 |  |  |  | 0 |  |  | 0 | 0
16 - Coil Services |  | 161 - LN2 Distribution | 337.5 | 337.5 |  |  | 338.11 | 0.61 |  | 338.11 | 338.11 | 0 |  | 16 | 161 - LN2 Distribution | 338
16 - Coil Services |  | 162 - Electrical Leads | 621.3 | 621.3 |  |  | 619.03 | -2.27 |  | 619.03 | 619.03 | 0 |  | 16 | 162 - Electrical Leads | 619
16 - Coil Services |  | 163 - Coil Protection System | 78.1 | 78.1 |  |  | 78.86 | 0.76 |  | 78.86 | 78.86 | 0 |  | 16 | 163 - Coil Protection System | 79
|  | subtotal | 1036.9 | 1036.9 |  |  | 1036 | -0.9 |  | 1036 | 1036 | 0
| 17 - Cryostat and Base Support Structure |  |  | 0 |  |  |  | 0 |  |  |  | 0
17 - Cryostat and Base Support Structure |  | 171 -Cryostat | 862.9 | 862.9 |  |  | 877.69 | 14.79 |  | 877.69 | 877.69 | 0 |  | 17 | 171 -Cryostat | 879
17 - Cryostat and Base Support Structure |  | 172 - Base Support Structure | 438.2 | 438.2 |  |  | 443.45 | 5.25 |  | 443.45 | 443.45 | 0 |  | 17 | 172 - Base Support Structure | 443
|  | subtotal | 1301.1 | 1301.1 |  |  | 1321.14 | 20.04 |  | 1321.14 | 1321.14 | 0
| 18 - Field Period Assembly |  |  | 0 |  |  |  | 0 |  |  |  | 0
18 - Field Period Assembly |  | 181 - Field Period Assembly Planning/Oversight | 1379.3 | 1379.3 |  |  | 1014.4 | -364.9 | Reduced Viola to .7 fte during FP assy.-$175k. $190 trabsferred to wbs185 | 1014.4 | 1014.4 | 0 |  | 18 | 181 - Field Period Assembly Planning/Oversight | 1014
18 - Field Period Assembly |  | 182 - TFTR Test Cell Area preparations | 92.9 | 92.9 |  |  | 1e-05 | -92.9 | part of FP assy | 1e-05 | 1e-05 | 0
18 - Field Period Assembly |  | 183 - Receive Inspect and Test Coils | 77.4 | 77.4 |  |  | 79.12 | 1.72 |  | 79.12 | 79.12 | 0 |  | 18 | 183 - Receive Inspect and Test Coils | 79
18 - Field Period Assembly |  | 184 - Receive Inspect and Test VV | 326.3 | 326.3 |  |  | 530.14 | 203.84 | +202k increased cost for stud instl, cooling tubes, magnetics instl, | 530.14 | 530.14 | 0 |  | 18 | 184 - Receive Inspect and Test VV | 532
18 - Field Period Assembly |  | 185 - Assemble Field Periods | 1509.4 | 1509.4 |  |  | 1818.56 | 309.16 | +$129 MC sub-assy, | 1818.56 | 1818.56 | 0 |  | 18 | 185 - Assemble Field Periods | 1819
18 - Field Period Assembly |  | 186 - Tooling Design and Fabrication | 1217.2 | 1217.2 |  |  | 1200.04 | -17.16 |  | 1200.04 | 1200.04 | 0 |  | 18 | 186 - Tooling Design and Fabrication | 1186
18 - Field Period Assembly |  | 187 - Measurement Systems | 463.2 | 463.2 |  |  | 475.83 | 12.63 |  | 475.83 | 475.83 | 0 |  | 18 | 187 - Measurement Systems | 476
|  | subtotal | 5065.7 | 5065.7 |  |  | 5118.09 | 52.39 |  | 5118.09 | 5118.09 | 0
| 19 - Stellarator Core Management and Integration |  |  | 0 |  |  |  | 0 |  |  |  | 0
19 - Stellarator Core Management and Integration |  | 191 - Stellarator Core Management & Oversight | 1083 | 1113 | 30 | ECP 16 FY04 cost variance +30 | 946.44 | -166.56 |  | 946.44 | 946.44 | 0 |  | 19 | 191 - Stellarator Core Management & Oversight | 946
19 - Stellarator Core Management and Integration |  | 192 - Stellarator Core Integration & Analysis | 1568.5 | 1568.5 | 0 |  | 1474.58 | -93.92 | Demo method for determining current center +88.Moved Brooks to WBS 82 -158 | 1474.58 | 1474.58 | 0 |  | 19 | 192 - Stellarator Core Integration & Analysis | 1475
|  | subtotal | 2651.5 | 2681.5 | 30 |  | 2421.02 | -260.48 |  | 2421.02 | 2421.02 | 0
|  | SUBTOTAL WBS 1 | 49393.3 | 49976.9 | 583.6 |  | 50655.87 | 678.97 |  | 50894.84 | 51005.93 | 111.19
21 - Fueling Systems | 21 - Fueling Systems |  | 140 | 80 | -60 | ECP 16 simplification offueling sys | 80.72 | 0.72 |  | 80.72 | 80.72 | 0 |  | 21 |  | 81
22 - Torus Vacuum Pumping Systems | 22 - Torus Vacuum Pumping Systems |  | 388.1 | 388.1 |  |  | 388.7 | 0.6 |  | 388.7 | 388.7 | 0 |  | 22 |  | 390
25 - Neutral Beam Injection System | 25 - Neutral Beam Injection System |  | 308.9 | 308.9 | 0 |  | 308.9 | 0 |  | 308.9 | 308.9 | 0 |  | 25 | 250 - Neutral Beam Injection System | 309
|  | SUBTOTAL WBS 2 | 837 | 777 | -60 |  | 778.32 | 1.32 |  | 778.32 | 778.32 | 0
31 - Magnetic Diagnostics | 31 - Magnetic Diagnostics |  | 455.6 | 455.6 |  |  | 413.8 | -41.8 | Deleted $41k for install of sensors and mag diag. Alreadyy incl in wbs 184 | 413.8 | 413.8 | 0 |  | 31 |  | 414
36 - Edge and Divertor Diagnostics | 36 - Edge and Divertor Diagnostics |  | 43.3 | 43.3 |  |  | 42.9 | -0.4 |  | 42.9 | 42.9 | 0 |  | 36 |  | 43
38 - Electron Beam (EB) Mapping | 38 - Electron Beam (EB) Mapping |  | 295.3 | 295.3 |  |  | 290.6 | -4.7 |  | 290.6 | 290.6 | 0 |  | 38 |  | 291
39 - Diagnostics Integration | 39 - Diagnostics Integration |  | 366.7 | 366.7 |  |  | 369.4 | 2.7 |  | 369.4 | 369.4 | 0 |  | 39 |  | 369
|  | SUBTOTAL WBS 3 | 1160.9 | 1160.9 |  |  | 1116.7 | -44.2 |  | 1116.7 | 1116.7 | 0
| 41 - AC Power |  |  | 0 |  |  |  | 0 |  |  |  | 0
41 - AC Power |  | 411 - Auxliary AC Power Systems | 471.1 | 471.1 |  |  | 439.83 | -31.27 | eliminated outlets on 2nd level | 439.83 | 439.83 | 0 |  | 41 | 411 - Auxliary AC Power Systems | 440
41 - AC Power |  | 412 - Experimental AC Power Systems | 42.7 | 42.7 |  |  | 45 | 2.3 |  | 45 | 45 | 0 |  | 41 | 412 - Experimental AC Power Systems | 45
| 43 - DC Systems |  |  | 0 |  |  |  | 0 |  |  |  | 0
43 - DC Systems |  | 431 - C-Site DC Systems | 523.6 | 523.6 |  |  | 445.5 | -78.1 |  | 445.5 | 445.5 | 0 |  | 43 | 431 - C-Site DC Systems | 446
43 - DC Systems |  | 432 - D-to-C Site DC Systems | 453.1 | 14 | -439.1 | ECP 16 reclassification to non MIE |  | -14 |  |  | 0 | 0
43 - DC Systems |  | 433 - D-Site DC Systems | 13.4 | 13.4 |  |  |  | -13.4 |  |  | 0 | 0
| 44 - Control and protection Systems |  |  | 0 |  |  |  | 0 |  |  | 0 | 0
44 - Control and protection Systems |  | 441 - Electrical Interlocks | 330.4 | 330.4 |  |  | 343.5 | 13.1 |  | 343.5 | 343.5 | 0 |  | 44 | 441 - Electrical Interlocks | 345
44 - Control and protection Systems |  | 442 - Kirk Key Interlocks | 90.2 | 90.2 |  |  | 77.8 | -12.4 |  | 77.8 | 77.8 | 0 |  | 44 | 442 - Kirk Key Interlocks | 78
44 - Control and protection Systems |  | 443 - Real Time Control Systems | 12.8 | 12.8 |  |  | 13.3 | 0.5 |  | 13.3 | 13.3 | 0 |  | 44 | 443 - Real Time Control Systems | 13
44 - Control and protection Systems |  | 444 - Instrument Systems | 349.1 | 349.1 |  |  | 294.2 | -54.9 |  | 294.2 | 294.2 | 0 |  | 44 | 444 - Instrument Systems | 294
44 - Control and protection Systems |  | 445 - Coil protection Systems | 366.9 | 366.9 |  |  | 485.9 | 119 | Increased scope from Raki | 485.9 | 485.9 | 0 |  | 44 | 445 - Coil protection Systems | 486
| 45 - Power System Design and Integration |  |  | 0 |  |  |  | 0 |  |  |  | 0
45 - Power System Design and Integration |  | 451 - System Design and Interfaces | 510 | 510 |  |  | 518.34 | 8.34 |  | 518.34 | 518.34 | 0 |  | 45 | 451 - System Design and Interfaces | 518
45 - Power System Design and Integration |  | 452 - Electrical Systems Support | 240.2 | 240.2 |  |  | 243.96 | 3.76 |  | 243.96 | 243.96 | 0 |  | 45 | 452 - Electrical Systems Support | 244
45 - Power System Design and Integration |  | 453 - System Testing (PTP's) | 302.4 | 302.4 |  |  | 305.49 | 3.09 |  | 305.49 | 305.49 | 0 |  | 45 | 453 - System Testing (PTP's) | 305
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0
46 - FCPC Building Modifications | 46 - FCPC Building Modifications |  | 1.3 | 1.3 | 0 |  | 1.3 | 0 |  | 1.3 | 1.3 | 0 |  | 46 | 460 | 1
|  | SUBTOTAL WBS 4 | 3707.2 | 3268.1 | -439.1 |  | 3214.12 | -53.98 |  | 3214.12 | 3214.12 | 0
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0
51 - TCP/IP Infrastructure Systems | 51 - TCP/IP Infrastructure Systems |  | 292.9 | 292.9 |  |  | 288.9 | -4 |  | 288.9 | 288.9 | 0 |  | 51 |  | 289
52 - Central Instrumentation & Control | 52 - Central Instrumentation & Control |  | 660.7 | 660.7 |  |  | 569.3 | -91.4 |  | 569.3 | 569.3 | 0 |  | 52 |  | 571
53 - Data Acquisition & Facility Computing | 53 - Data Acquisition & Facility Computing |  | 414.9 | 414.9 |  |  | 328.4 | -86.5 |  | 328.4 | 328.4 | 0 |  | 53 |  | 328
54 - Facility Timing & Synchronization | 54 - Facility Timing & Synchronization |  | 292 | 292 |  |  | 206.8 | -85.2 |  | 206.8 | 206.8 | 0 |  | 54 |  | 207
55 - Real Time Plasma & Power Supply Control Sys | 55 - Real Time Plasma & Power Supply Control Sys |  | 153.7 | 153.7 |  |  | 151.2 | -2.5 |  | 151.2 | 151.2 | 0 |  | 55 |  | 151
56 - Central Safety Interlock Systems | 56 - Central Safety Interlock Systems |  | 361.7 | 361.7 |  |  | 357.7 | -4 |  | 357.7 | 357.7 | 0 |  | 56 |  | 358
58 - Central I&C management and Integration | 58 - Central I&C management and Integration |  | 12.9 | 12.9 |  |  | 12.9 | 0 |  | 12.9 | 12.9 | 0 |  | 58 |  | 13
|  | SUBTOTAL WBS 5 | 2188.8 | 2188.8 |  |  | 1915.2 | -273.6 |  | 1915.2 | 1915.2 | 0
| 61 - Water Systems |  |  | 0 |  |  |  | 0 |  |  |  | 0
61 - Water Systems |  | 611 - C-Site Cooling System | 153.3 | 153.3 |  |  | 151.1 | -2.2 |  | 151.1 | 151.1 | 0 |  | 61 | 611 - C-Site Cooling System | 151
61 - Water Systems |  | 612 - NB Water Cooling Systems | 239.9 | -0.1 | -240 | ECP 16 not req'd for CD-4. |  | 0.1 |  |  | 0 | 0 |  | 61 | 613 - Vacuum Pumping System | 89
61 - Water Systems |  | 613 - Vacuum Pumping System | 100 | 100 |  |  | 89.4 | -10.6 |  | 89.4 | 89.4 | 0
61 - Water Systems |  | 614 - Bakeout Water System | 38.5 | 0 | -38.5 | ECP 16 not req'd for CD-4. |  | 0 |  |  | 0 | 0
| 62 - Cryogenic Systems |  |  | 0 |  |  |  | 0 |  |  |  | 0
62 - Cryogenic Systems |  | 621 - LN2-LHe Supply System | 224.9 | 224.9 |  |  | 220.9 | -4 |  | 220.9 | 220.9 | 0 |  | 62 | 621 - LN2-LHe Supply System | 221
62 - Cryogenic Systems |  | 622 - LN2 Coil Cooling Supply |  | 0 |  |  |  | 0 |  |  | 0 | 0 |  | 62 | 622 - LN2 Coil Cooling Supply
62 - Cryogenic Systems |  | 623 - GN2 Cryostat Cooling System | 222.5 | 222.5 |  |  | 218.7 | -3.8 |  | 218.7 | 218.7 | 0 |  | 62 | 623 - GN2 Cryostat Cooling System | 219
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0
63 - Utility Systems | 63 - Utility Systems |  | 122.7 | 122.7 |  |  | 103.5 | -19.2 |  | 103.5 | 103.5 | 0 |  | 63 |  | 103
| 65 - Facility Systems Integration |  |  | 0 |  |  |  | 0 |  |  |  | 0
65 - Facility Systems Integration |  | 612 - NB Water Cooling Systems | 9.4 | 9.4 |  |  | 9.4 | 0 |  | 9.4 | 9.4 | 0 |  | 65 | 612 - NB Water Cooling Systems | 9
65 - Facility Systems Integration |  | 650 - Facility Systems Integration | 32.2 | 32.2 | 0 |  | 32.2 | 0 |  | 32.2 | 32.2 | 0 |  | 65 | 650 - Facility Systems Integration | 32
|  | SUBTOTAL WBS 6 | 1143.4 | 864.9 | -278.5 |  | 825.2 | -39.7 |  | 825.2 | 825.2 | 0
71 - Shield Wall Seismic Modifications | 71 - Shield Wall Seismic Modifications |  | 32.2 | 32.2 |  |  | 32.2 | 0 |  | 32.2 | 32.2 | 0 |  | 71 | 740 - Machine Assembly Planning and Oversight | 32
72 - Control Room Refurbishment | 72 - Control Room Refurbishment |  | 48.8 | 48.8 |  |  | 50.2 | 1.4 |  | 50.2 | 50.2 | 0 |  | 72 | 720 | 50
73 - Platform Design & Fabrication | 73 - Platform Design & Fabrication |  | 161 | 161 |  |  | 161.3 | 0.3 |  | 161.3 | 161.3 | 0 |  | 73 | 730 - Test Cell & Basement Assembly Operations | 161
| 74 - Machine Assembly Planning and Oversight |  |  | 0 |  |  |  | 0 |  |  |  | 0
74 - Machine Assembly Planning and Oversight |  | 740 - Machine Assembly Planning and Oversight | 148 | 148 |  |  | 152.55 | 4.55 |  | 152.55 | 152.55 | 0 |  | 74 | 740 - Machine Assembly Planning and Oversight | 153
74 - Machine Assembly Planning and Oversight |  | 741 - Planning Prior to Machine Assembly | 281.6 | 281.6 |  |  | 281.57 | -0.03 |  | 281.57 | 281.57 | 0 |  | 74 | 741 - Planning Prior to Machine Assembly | 282
74 - Machine Assembly Planning and Oversight |  | 742 - Construction Management | 1194.2 | 1194.2 |  |  | 1068.15 | -126.05 |  | 1068.15 | 1068.15 | 0 |  | 74 | 742 - Construction Management | 1068
| 75 - Test Cell and Basement Assembly Operations |  |  | 0 |  |  |  | 0 |  |  | 0 | 0
75 - Test Cell and Basement Assembly Operations |  | 750 - Test Cell & Basement Assembly Operations | 2184.9 | 2184.9 |  |  | 2238.93 | 54.03 |  | 2238.93 | 2238.93 | 0 |  | 75 | 750 - Test Cell & Basement Assembly Operations | 2239
76 - Tooling Design & Fabrication | 76 - Tooling Design & Fabrication |  | 223.7 | 223.7 |  |  | 222.99 | -0.71 |  | 222.99 | 222.99 | 0 |  | 76 |  | 223
|  | SUBTOTAL WBS 7 | 4274.4 | 4274.4 |  |  | 4207.89 | -66.51 |  | 4207.89 | 4207.89 | 0
81 - Project Management and Control | 81 - Project Management and Control |  | 3556.8 | 3556.8 |  |  | 3450.278 | -106.522 | re-estimted out year needs. Cost share with res prep | 3450.278 | 3596 | 145.722 | Prior year scope retirement fore FY04 | 81 | 810 - Project Management & Control | 3596
82 - Project Engineering | 82 - Project Engineering |  | 4013.7 | 4207.5 | 193 | ECP 16 FY04 cost variance +193 | 4367.5 | 160 |  | 4367.5 | 4426 | 58.5 | New scope for FY05. Dimensional control coordinator. | 82 | 820 - Project Engineering | 4426
84 - Project Physics | 84 - Project Physics |  | 412.2 | 412.2 |  |  | 412.47 | 0.27 |  | 470.17 | 470.17 | 0 |  | 84 | 840 - Project Physics | 470
85 - Integrated Systems Testing | 85 - Integrated Systems Testing |  | 1220.1 | 1220.1 | 0 |  | 1220.68 | 0.58 |  | 1220.68 | 1220.68 | 0 |  | 85 |  | 1221
|  | SUBTOTAL WBS 8 | 9202.8 | 9396.6 | 193 |  | 9450.928 | 54.328 |  | 9508.628 | 9712.85 | 204.222
PPPL Allocations | PPPL Allocations |  | 983.3 | 983.3 |  |  | 1128.6 | 145.3 | Adjusted based upon FY04 allocation costs and estimated out year mapping | 1128.6 | 1128.6 | 0 |  | AA | PPPL Allocations | 1129
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Contingency | Contingency |  | 13454.9 | 13455 |  |  | 13052.89 | -402.11 |  | 12755.89 | 12440.478 | -315.412 |  | CC | Contingency | 12437
0
|  |  | 86346 | 86345.9 | -0.1 | 0 | 86345.718 | -0.18199 |  | 86345.388 | 86345.288 | 0.2 |  |  |  |  | 12437
86331