| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Mike Viola |  |  | Date: March 24, 2005 |  |
| ECP No: 027 |  | ECP Title: NCSX Vessel Port Manufacture – Material Change |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: Mike Viola, Paul Goranson, Brad Nelson, Jerry Levine, Judy Malsbury |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |  |  |  |  |
| Actions - Approve RFD-12-002 (but not the substitution of Haynes Alloy for Inconel) - Issue Contract Addendum to incorporate RFD-12-002 by April 24, 2005 - Update NCSX-CSPEC-121-02 to incorporate RFD-12-002 by April 24, 2005 - Prepare ECN (#4972 Assigned) and update impacted PDF drawings by April 24, 2005 |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Under Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Mike Viola | Date: March 24, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: MTM requested deviation due to long lead time for Schedule 40 pipe. Impacted WBS Elements: 121 Job 1250 Impacts of Change (Briefly Describe): MTM requested to: - Substitute schedule 10 pipe for specified schedule 40 [FOR 2-1/2 INCH PIPE ONLY] OR - Substitute Haynes Alloy C-276 for ASTM B705 / ASTM B444 / ASTM B443. Assessment of Other Options: None List Attachments, Impacted Documents, etc. - RFD-12-002 Description of Change: RLM (B. Nelson) dispositioned RFD-12-002 as follows: - Approved - substitution of sch 10 for the 2 1/2" sch 40 pipe is accepted. - Not Approved - the substitution of Haynes Alloy for Inconel is rejected. - Since this does not impact the design, the drawings do not need to be updated. - The CSPEC should be updated within 30 days to list this and other approved deviations (new Appendix B). |  |