| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Ron Strykowsky | Date: April 19, 2005 |
| ECP No: 029 | ECP Title: FY2005 Replanning Baseline |
| Required Reviewers |
| Required Reviewers for this ECP: WBS Managers, Project Engineers, NCSX QA, ES&H, NCSX Engineering Manager |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions (1) Revise cost and schedule baseline by April 30, 2005 to reflect updated baseline |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: April 19, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: DOE directed replanning to reflect revised annual funding guidance. Impacted WBS Elements: WBS Elements: 12, 13, 14, 15, 16, 17, 18, 19, 2, 3, 4, 5, 6, 7, & 8 Impacts of Change (Briefly Describe): At DOE direction, NCSX Project replanned to support a flat funding profile of $15.9 peak (FY2006-FY2008). As a result of this direction, two categories of cost and schedule impacts were noted: Project Stretch Out and Rate Adjustments Work scope stretched out; Overhead rates revised to reflect most recent PPPL and ORNL rates; Impact of escalation due to stretch out included; and First plasma revised to July 2009 with 5 months float. Re-Estimate of Work to Complete Based on Current Experience and Projections Reflected learning from final design of the vacuum vessel and modular coils as well as the experience from the modular coil R&D; Projected work to complete for the VVSA and MCWF based on production effort and experiences;and Re-evaluated contingency balance for the remaining work scope. Established revised basis of estimate: Assumed single shift/8 hour days except for the early Modular Coil winding effort; Made make-buy decision to fabricate TF coils at PPPL; and Reaffirmed the modular coil component fabrication will continue to be accomplished by industry Assessment of Other Options: Multiple shift fabrication and assembly considered but decision deferred. Make-buy decision for industry to fabricate the TF coils assessed to contain higher risk and potential cost and schedule impact. Make-buy decision on remaining modular coil components assessed and decision made that industry in best position to do this work. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: April 19, 2005 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. ECP-024 to ECP-029 Reconciliation Sheet Revised Resource Loaded Baseline Description of Change: the Table Below Summarizes the Cost Impact of this ECP: WBS Element Previous Baseline ($) Current Baseline ($) Stretchout ($) Re-Estimate ($) Total ($) 12 – Vacuum Vessel $8,737K $9,864K $119K $828K $947K 13 – Conventional Coils $4,552K $5,378K $226K $599K $825K 14 – Modular Coils $26,439K $28,993K $1,039K $1,515K $2,554K 15 - Structures $1,381K $1,413K $52K ($20K) $32K 16 – Coil Services $1,036K $1,146K $110K $110K 17 – Cryostat & Base Suppt Structure $1,321K $1,361K $40K $40K 18 – Field Period Assembly $5,118K $5,725K $561K $46K $607K 19 – Stellarator Core Mgmt & Integr $2,421K $2,752K $386K ($55K) $331K Subtotal WBS 1 – Stellarator Core $51,006K $56,452K $2,533K $2,913K $5,446K WBS 2 – Auxilliary Systems $778K $783K $27K ($22K) $5K WBS 3 – Diagnostic Systems $1,117K $1,143K $45K ($19K) $26K WBS 4 – Electrical Power Systems $3,214K $3,301K $170K ($83K) $87K WBS 5 – I&C Systems $1,915K $2,050K $130K $4K $134K WBS 6 – Facility Systems $825K $691K $34K ($168K) ($134K) WBS 7 Test Cell Prep & Machine Assy $4,208K $4,411K $173K $30K $203K 81 – Project Mgmt & Control $3,596K $4,509K $950K ($37K) $913K 82 – Project Engineering $4,426K $5,311K $563K $322K $885K 84 – Project Physics $470K $470K $0K 85 – Integrated Systems Testing $1,221K $1,189K $90K ($121K) (-$31K) Subtotal WBS 8 – Project Oversight & Suppt $9,713K $11,479K $1,603K $164K $1,766K PPPL Allocations $1,129K $1,577K $388K $60K $448K Contingency $12,441K $12,242K ($198K) ($198K) TOTALS $86,345K $94,129K $5,103K $2,681K $7,784K Of the $7,784K growth in the cost estimate, $5,103K (~66%) is due to strechout, rate changes, etc. The remaining $2,681K (~$34%) is due to re-estimating the work to complete based on experiences and projections to date. |