| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Bob Simmons | Date: April 20, 2005 |
| ECP No: 029 | ECP Title: Retirement of Risks for VVSA Forming Dies and Twisted Racetrack Assembly |
| Required Reviewers |
| Required Reviewers for this ECP: Paul Goranson, Dave Williamson, Brad Nelson, Jim Chrzanowski, Ron Strkowsky, Wayne Reiersen, Judy Malsbury |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Revise Cost Baseline by April 30, 2005 (Schedule Baseline revised in ECP-024) |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Under Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: April 20, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: Retirement of risks. Impacted WBS Elements: WBS 12 and WBS 14 Impacts of Change (Briefly Describe): WBS 12 – This change reflects the additional forming dies for the VVSA. Originally, the supplier had anticipated re-using the dies from the prototype effort, however design changes made between the fabrication of dies for the prototype casting and the final production VVSA, invalidated that assumption. ECP-024 (approved in early March, 2005) identified the schedule impact, but identified that the cost impact was still being assessed and negotiated. This ECP now captures the cost impact of $431K. This risk is now retired as the contract value has been adjusted to reflect these additional costs. WBS 14 – the Twisted Racetrack Coil Assembly proved to be an invaluable learning experience, but resulted in some unanticipated cost overruns of $400K. This activity was completed at the end of March, 2005, satisfying a Joule milestone, so the risk is now retired. Impact of Contingency – a drawdown of $831K from $12,441K to $11,610K. The TEC remains at $86,345K. Assessment of Other Options: None List Attachments, Impacted Documents, etc.: None |