## Stretchout calculation
NCSX Stretchout Impact analysis | [5 empty] | NCSX Stretchout Contingency Analysis
WBS 19 | [5 empty] | Management |  |  | Contingency
(old rates used) | Brad Nelson | added 10 months @ 30% coverage = 10/12*1726 *.3*$154$/h= |  |  | 66451 | WBS 191 | Stellarator core managemnt | 66451 | 10% | 6645.1
| Mike Cole | added 10 months @ 37% = 10/12*1726*.37*$154$/h= |  |  | 81956.2333 | WBS 192 | Stellarator core Integration | 81956.2333 | 10% | 8195.6233
[6 empty] | WBS 81 | Project Management | 817958.6047 | 17% | 139052.9628
WBS 81 | 14 month stretch | Strykowsky $$159.62$/h *1768*14/12 *90%$= |  |  | 296318.568 | WBS 82 | Project Engineering and Intrgration | 232495.652 | 17% | 39524.2608
(old rates used) |  | Neilson @ $250.53$/h *1768*14/12*85%= |  |  | 439245.898 |  |  | 1198861.49
|  | Pam Hampton @ $50.47$/h*2080*14/12 *40% |  |  | 48989.5467
|  | Lyon 12 months @10%@ 188.94$/h |  |  | 33404.592
WBS 82 | Wayne Reiersen @ 12 months @ 60%@ 179.34$/h |  |  |  | 186180.168
(old rates used) | Larry Dudek @ 12 months @ 10% @179.34 $/h= |  |  |  | 30954.084
| Cheryl Such @ 12 months @ 10% @89$/h= |  |  |  | 15361.4
1198861.49
WBS 13 TF fab oversight | 338 day atretchout of TF Fab effort
(old rates used) |  | Mike Kalish |  | 332 days * 6.64h/d*27%*179.78$/h | 107006.7819 | Field Oversight & Supervision
WBS 14 MC winding | Winding ops strecthout from 391 days to 663 days. added 272 days |  |  |  |  | WBS 131 TF fab oversight |  | 107006.7819 | 40% | 42802.7128
(old rates used) |  | Chrzanowski 86% |  |  |  | WBS 142 MC winding |  | 703276.3543 | 40% | 281310.5417
|  |  | 272days x 6.64(avg hrs/day)*86% *$179.78$/hr= |  | 279239.4737 | WBS 181 FP assy oversight |  | 441181.7821 | 24% | 105883.6277
|  | Raftopolous 50% | [5 empty] | 1251464.9183
|  |  | 272days x 6.64(avg hrs/day)*50% *$179.78$/hr= |  | 162348.5312
Meighan 86%
|  |  | 272days x 6.64(avg hrs/day)*86% *$116.55$/hr= |  | 181028.8166
|  | Title III Dave Williamson added 272days @ 29%*6.64 h/d * $154$/h= |  |  | 80659.5328
WBS 18 FP assy oversight | Health Physics support | added 14mos of HP support of FP assy in TFTR TC year @75% @$117.07$/h |  |  | 177556.1667
(old rates used) | Mike Viola filed supervision added 14 months @ 73% coverage @ $179.34$/h= |  |  |  | 263625.6154
1251464.9183
Overhead & Escalation
ALL WBS Elements-Rates differential. (old rates applied to new estimates delta to new rates)= |  |  |  |  | 1590290 | Labor and Overhead Rates (across all WBS elements) |  | 1590290 | 25% | 397572.5
WBS 8 Allocations added 12 months @ $187.9/yr unloaded = |  |  |  |  | 345000 | Direct Allocations (overhead) |  | 345000 | 10% | 34500
ALL WBS Elements-Escalation due to Annual BA limitations = |  |  |  |  | 399251 | Escalation |  | 399251 | 25% | 99812.75
[5 empty] | 2334541 |  |  | 2334541 | contingency
[7 empty] | Total = | 4784867.4083 | 24.14% | 1155300.0791
[7 empty] | Total = | 4784867.4083 | use 25% | 1196216.8521
[7 empty] | TOTAL IMPACT = | 5981084.2603
9569734.8165

## ecp29,ecp30,ecp31 reconcil
NCSX rebaseline reconciliation
wbs2 |  |  | ECP 14 | ECP 16 | change | description | ECP 18 | change | description | ECP 21 | ECP 29 | change | description | [6 empty] | WBS2 | DESC | ECP 30 (adjusted) | ECP 31 | increases ECP 30 - 31 | Changes | WBS2 | ACT ID | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | TOTAL
11 - In-Vessel Components |  | 111 - Limiters | 0.1 | 0.1 |  |  | 0.1 | 0 |  | 0.1 |  | 0 | [6 empty] | 11 - 11 - In-Vessel Components | 11 - 11 - In-Vessel Components | 111 - Limiters |  |  |  |  | 11 | 111 | 0.06 | [6 empty] | 0.06
| 12 - Vacuum Vessel Systems |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [13 empty] | 12 | 121 | 1217.44 | 1571.43 | 4076.16 | 1808.12 | 6.38 |  |  | 8679.52
12 - Vacuum Vessel Systems |  | 121 - Vacuum Vessel Assembly | 7891.7 | 7906.3 | 14.6 | ECP 16 FY04 cost variance +14.6k | 8061.3 | 155 | .Increased Viola to 2 days /week oversight +$63k; Increased field weld joint full size sample =+$96k | 8061.3 | 8492.3 | 431 | [6 empty] | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 121 - Vacuum Vessel Assembly |  | 8679.52 |  |  | 12 | 122 |  | 9.52 | 73.61 | 108.76 |  |  |  | 191.89
12 - Vacuum Vessel Systems |  | 122 - Vacuum Vessel Thermal Insulation | 174.7 | 174.7 |  |  | 176.03 | 1.33 |  | 176.03 | 176.03 | 0 | [6 empty] | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 122 - Vacuum Vessel Thermal Insulation |  | 191.89 |  |  | 12 | 123 |  | 46.14 | 302.56 | 187.27 |  |  |  | 535.98
12 - Vacuum Vessel Systems |  | 123 - Vacuum Vessel Heating and Cooling Distrib | 375.7 | 375.7 |  |  | 373.37 | -2.33 |  | 373.37 | 373.37 | 0 | [6 empty] | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 123 - Vacuum Vessel Heating and Cooling Distrib |  | 535.98 |  |  | 12 | 124 |  | 5.46 | 96.42 | 3.49 | 0.72 |  |  | 106.1
12 - Vacuum Vessel Systems |  | 124 - Vacuum Vessel Supports | 62 | 62 |  |  | 97.63 | 35.63 | .Lateral supports +22k | 97.63 | 97.63 | 0 | [6 empty] | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 124 - Vacuum Vessel Supports |  | 106.1 |  |  | 12 | 125 |  |  | 17.64 |  |  |  |  | 17.64
12 - Vacuum Vessel Systems |  | 125 - Vacuum Vessel Local I&C | 27.3 | 27.3 |  |  | 29.04 | 1.74 |  | 29.04 | 29.04 | 0 | [6 empty] | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 125 - Vacuum Vessel Local I&C |  | 17.64 |  |  | 13 | 130 | 91.66 | 333.93 | 411.81 |  |  |  |  | 837.4
|  | subtotal | 8531.4 | 8546 | 14.6 |  | 8737.37 | 191.37 |  | 8737.37 | 9168.37 | 431 | [9 empty] | 9495.2 | 9531.13 | 35.93 | -$137k full size weld sample; +$43k seals &5:5templates for VVSA;+$99k Engr contract admin;+$31 ORNL VVSA dsn support | 13 | 131 |  |  | 839.88 | 561.68 | 316.27 |  |  | 1717.83
| 13 - Conventional Coils |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [13 empty] | 13 | 132 |  |  |  |  | 360.59 | 1524.77 |  | 1885.36
13 - Conventional Coils |  | 130 - Conventional Coil Design | 613.1 | 613.1 |  |  | 737.81 | 124.71 | Kalish re-estimate of new design | 737.81 | 849 | 111.19 | Completion of Prelim design and the re-estimate of final design tasks. | [6 empty] | 13 - 13 - Conventional Coils | 130 - Conventional Coil Design |  | 837.4 |  |  | 13 | 133 |  |  |  |  | 257.67 |  |  | 257.67
13 - Conventional Coils |  | 131 - TF Coils | 1458.8 | 1458.8 |  |  | 1594.58 | 135.78 | Kalish re-estimate of new design | 1594.58 | 1594.58 | 0 | [7 empty] | 13 - 13 - Conventional Coils | 131 - TF Coils |  | 1717.83 |  |  | 13 | 134 |  |  |  |  | 70.62 | 21.25 |  | 91.87
13 - Conventional Coils |  | 132 - PF Coils | 1777.3 | 1777.3 |  |  | 1870.43 | 93.13 | Kalish re-estimate | 1870.43 | 1771 | -99.43 | [7 empty] | 13 - 13 - Conventional Coils | 132 - PF Coils |  | 1885.36 |  |  | 14 | 141 | 1128.23 | 3073.67 | 4107.01 | 4073.61 | 835.77 |  |  | 13218.27
13 - Conventional Coils |  | 133 - External Trim Coils | 381.1 | 181.1 | -200 | ECP 16 simplification of trim coli sys -200k | 145.64 | -35.46 | Kalish re-estimate | 145.64 | 245 | 99.36 | [7 empty] | 13 - 13 - Conventional Coils | 133 - External Trim Coils |  | 257.67 |  |  | 14 | 142 | 1028.98 | 1652.18 | 2870.35 | 3111.08 | 2533.09 | 335.95 |  | 11531.64
13 - Conventional Coils |  | 134 - Conventional Coil Local | 73.4 | 73.4 |  |  | 92.63 | 19.23 | Kalish re-estimate | 92.63 | 92.63 | 0 | [7 empty] | 13 - 13 - Conventional Coils | 134 - Conventional Coil Local |  | 91.87 |  |  | 14 | 143 |  |  | 19.35 | 33.44 | 33.17 |  |  | 85.96
|  | subtotal | 4303.7 | 4103.7 | -200 |  | 4441.09 | 337.39 |  | 4441.09 | 4552.21 | 111.12 | [9 empty] | 4790.13 | 4790.13 | 0 |  | 14 | 144 | 267.55 | 2598.22 | 389.4 |  |  |  |  | 3255.17
| 14 - Modular Coils |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [13 empty] | 15 | 151 |  | 34.61 |  | 186.87 | 1186.69 | 4.79 |  | 1412.96
14 - Modular Coils |  | 141 - Modular Coil Winding Form | 12788.6 | 12881.6 | 93 | ECP 16 FY04 cost variance +93 | 13180.68 | 299.08 | +$52k MCWF analysis, +85 EIO s/c,+54 JPP s/c,+79 title III MCWF fab | 13180.68 | 13180.68 | 0 | [7 empty] | 14 - 14 - Modular Coils | 141 - Modular Coil Winding Form |  | 13218.27 |  |  | 16 | 161 |  |  |  |  | 252.07 | 119.97 |  | 372.04
14 - Modular Coils |  | 142 - Modular Coil Windings and Assembly | 9438 | 9577 | 139 | ECP 16 FY04 cost variance +139. | 9614.03 | 37.03 | Chrzanowski/Meighan oversight of TRC +202k | 9853 | 10253 | 400 | [7 empty] | 14 - 14 - Modular Coils | 142 - Modular Coil Windings and Assembly |  | 11531.64 |  |  | 16 | 162 |  |  |  |  | 325.56 | 356.08 |  | 681.64
14 - Modular Coils |  | 143 - Modular Coil Local I&C | 121.2 | 121.2 |  |  | 120.42 | -0.78 |  | 120.42 | 120.42 | 0 | [7 empty] | 14 - 14 - Modular Coils | 143 - Modular Coil Local I&C |  | 85.96 |  |  | 16 | 163 |  |  |  |  | 86.3 |  |  | 86.3
14 - Modular Coils |  | 144 - Modular Coil Winding Facility & Fixtures | 2707.3 | 3214.3 | 507 | ECP 16 FY04 cost variance +507 | 3285.22 | 70.92 |  | 3285.22 | 3285.22 | 0 | [7 empty] | 14 - 14 - Modular Coils | 144 - Modular Coil Winding Facility & Fixtures |  | 3255.17 |  |  | 17 | 171 | 12.18 | 67.4 | 64.41 |  | 254.1 | 528.91 | 7.02 | 934.01
|  | subtotal | 25055.1 | 25794.1 | 739 |  | 26200.35 | 406.25 |  | 26439.32 | 26839.32 | 400 | [9 empty] | 27868.3 | 28091.04 | 222.74 | +$223k TRC and Final Winding design & analysis | 17 | 172 |  | 21.73 | 74.95 | 15.28 | 311.53 | 3.44 |  | 426.93
| 15 - Structures |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [13 empty] | 18 | 181 | 60.8 | 164.56 | 146.16 | 266.85 | 425.88 | 441.02 |  | 1505.26
15 - Structures |  | 151 - Coil Support Structure | 1447.8 | 1447.8 |  |  | 1380.71 | -67.09 | Kalish re-estimate | 1380.71 | 1380.71 | 0 | [7 empty] | 15 - 15 - Structures | 151 - Coil Support Structure | 1412.96 | 1412.96 | 0 |  | 18 | 185 |  |  |  | 200.83 | 1157.14 | 845.3 |  | 2203.28
| 16 - Coil Services |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 | [13 empty] | 18 | 186 |  |  | 758.11 | 396.33 | 54.74 | 10.47 |  | 1219.66
16 - Coil Services |  | 161 - LN2 Distribution | 337.5 | 337.5 |  |  | 338.11 | 0.61 |  | 338.11 | 338.11 | 0 | [7 empty] | 16 - 16 - Coil Services | 161 - LN2 Distribution |  | 372.04 |  |  | 18 | 187 |  | 197.99 | 184.4 | 85 | 11.25 | 11.34 | 11.79 | 501.77
16 - Coil Services |  | 162 - Electrical Leads | 621.3 | 621.3 |  |  | 619.03 | -2.27 |  | 619.03 | 619.03 | 0 | [7 empty] | 16 - 16 - Coil Services | 162 - Electrical Leads |  | 681.64 |  |  | 19 | 191 | 187.09 | 131.5 | 178.83 | 193.87 | 198.95 | 96.59 | 54.78 | 1041.61
16 - Coil Services |  | 163 - Coil Protection System | 78.1 | 78.1 |  |  | 78.86 | 0.76 |  | 78.86 | 78.86 | 0 | [7 empty] | 16 - 16 - Coil Services | 163 - Coil Protection System |  | 86.3 |  |  | 19 | 192 | 67.07 | 511.06 | 426.02 | 303.61 | 155.93 | 148.15 | 98.65 | 1710.49
|  | subtotal | 1036.9 | 1036.9 |  |  | 1036 | -0.9 |  | 1036 | 1036 | 0 | [9 empty] | 1139.98 | 1139.98 | 0 |  | 21 | [5 empty] | 51.65 | 34.89 |  | 86.54
| 17 - Cryostat and Base Support Structure |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [13 empty] | 22 |  | 63.67 |  |  |  | 123.31 | 225.58 |  | 412.55
17 - Cryostat and Base Support Structure |  | 171 -Cryostat | 862.9 | 862.9 |  |  | 877.69 | 14.79 |  | 877.69 | 877.69 | 0 | [7 empty] | 17 - 17 - Cryostat and Base Support Structure | 171 -Cryostat |  | 934.01 |  |  | 25 | 250 | 123 | 161.37 | [5 empty] | 284.37
17 - Cryostat and Base Support Structure |  | 172 - Base Support Structure | 438.2 | 438.2 |  |  | 443.45 | 5.25 |  | 443.45 | 443.45 | 0 | [7 empty] | 17 - 17 - Cryostat and Base Support Structure | 172 - Base Support Structure |  | 426.93 |  |  | 31 |  |  |  | 206.22 | 139.58 | 75.53 | 5.02 |  | 426.35
|  | 173-Spacer manipulator | [8 empty] | 0 | [8 empty] | 17 - 17 - Cryostat and Base Support Structure | 173 - Spacer Manipulator |  |  |  |  | 36 | [5 empty] | 5.92 | 40.03 |  | 45.96
|  | subtotal | 1301.1 | 1301.1 |  |  | 1321.14 | 20.04 |  | 1321.14 | 1321.14 | 0 | [9 empty] | 1360.94 | 1360.94 | 0 |  | 38 | [6 empty] | 310.09 |  | 310.09
| 18 - Field Period Assembly |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [13 empty] | 39 |  | 155.45 | 65 | 66.36 | 73.71 |  |  |  | 360.52
18 - Field Period Assembly |  | 181 - Field Period Assembly Planning/Oversight | 1379.3 | 1379.3 |  |  | 1014.4 | -364.9 | Reduced Viola to .7 fte during FP assy.-$175k. $190 trabsferred to wbs185 | 1014.4 | 1014.4 | 0 | [7 empty] | 18 - 18 - Field Period Assembly | 181 - Field Period Assembly Planning/Oversight |  | 1505.26 |  |  | 41 | 411 |  | 81.44 |  | 152.28 | 148.31 |  |  | 382.03
18 - Field Period Assembly |  | 182 - TFTR Test Cell Area preparations | 92.9 | 92.9 |  |  | 1e-05 | -92.9 | part of FP assy | 1e-05 | 1e-05 | 0 | [7 empty] | 18 - 18 - Field Period Assembly | 182 - TFTR Test Cell Area preparations |  |  |  |  | 41 | 412 |  |  |  |  | 18.44 | 29.7 |  | 48.14
18 - Field Period Assembly |  | 183 - Receive Inspect and Test Coils | 77.4 | 77.4 |  |  | 79.12 | 1.72 |  | 79.12 | 79.12 | 0 | [13 empty] | 43 | 431 |  |  | 232.56 | 5.1 | 216.28 |  |  | 453.94
18 - Field Period Assembly |  | 184 - Receive Inspect and Test VV | 326.3 | 326.3 |  |  | 530.14 | 203.84 | +202k increased cost for stud instl, cooling tubes, magnetics instl, | 530.14 | 530.14 | 0 | [13 empty] | 44 | 441 |  |  |  |  | 106.45 | 253.32 | 17.9 | 377.66
18 - Field Period Assembly |  | 185 - Assemble Field Periods | 1509.4 | 1509.4 |  |  | 1818.56 | 309.16 | +$129 MC sub-assy, | 1818.56 | 1818.56 | 0 | [7 empty] | 18 - 18 - Field Period Assembly | 185 - Assemble Field Periods |  | 2203.28 |  |  | 44 | 442 |  |  |  |  | 74.86 | 7.32 |  | 82.18
18 - Field Period Assembly |  | 186 - Tooling Design and Fabrication | 1217.2 | 1217.2 |  |  | 1200.04 | -17.16 |  | 1200.04 | 1200.04 | 0 | [7 empty] | 18 - 18 - Field Period Assembly | 186 - Tooling Design and Fabrication |  | 1219.66 |  |  | 44 | 443 |  |  |  |  | 11.26 | 3.01 |  | 14.27
18 - Field Period Assembly |  | 187 - Measurement Systems | 463.2 | 463.2 |  |  | 475.83 | 12.63 |  | 475.83 | 475.83 | 0 | [7 empty] | 18 - 18 - Field Period Assembly | 187 - Measurement Systems |  | 501.77 |  |  | 44 | 444 |  |  |  |  | 219.02 | 93.64 |  | 312.65
|  | subtotal | 5065.7 | 5065.7 |  |  | 5118.09 | 52.39 |  | 5118.09 | 5118.09 | 0 | [9 empty] | 5429.97 | 5429.97 | 0 |  | 44 | 445 |  | 1.05 |  | 61.03 | 382.57 | 77.45 |  | 522.1
| 19 - Stellarator Core Management and Integration |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [13 empty] | 45 | 451 | 112.34 | 29.89 | 155.93 | 33.61 | 105.02 | 83.55 |  | 520.33
19 - Stellarator Core Management and Integration |  | 191 - Stellarator Core Management & Oversight | 1083 | 1113 | 30 | ECP 16 FY04 cost variance +30 | 946.44 | -166.56 |  | 946.44 | 946.44 | 0 | [7 empty] | 19 - 19 - Stellarator Core Management and Integration | 191 - Stellarator Core Management & Oversight |  | 1041.61 |  |  | 45 | 452 |  |  |  |  | 119.12 | 142.62 |  | 261.74
19 - Stellarator Core Management and Integration |  | 192 - Stellarator Core Integration & Analysis | 1568.5 | 1568.5 | 0 |  | 1474.58 | -93.92 | Demo method for determining current center +88.Moved Brooks to WBS 82 -158 | 1474.58 | 1474.58 | 0 | [7 empty] | 19 - 19 - Stellarator Core Management and Integration | 192 - Stellarator Core Integration & Analysis |  | 1710.49 |  |  | 45 | 453 |  |  |  |  | 103.97 | 220.75 |  | 324.72
|  | subtotal | 2651.5 | 2681.5 | 30 |  | 2421.02 | -260.48 |  | 2421.02 | 2421.02 | 0 | [9 empty] | 2752 | 2752.1 | 0.1 |  | 46 | 460 | 1.3 | [6 empty] | 1.3
|  | SUBTOTAL WBS 1 | 49393.3 | 49976.9 | 583.6 |  | 50655.87 | 678.97 |  | 50894.84 | 51836.86 | 942.12 | [9 empty] | 54249.48 | 54508.25 | 258.77 |  | 51 |  | 11.9 | 16 |  |  |  | 282.69 |  | 310.59
[26 empty] | 52 | [5 empty] | 11.36 | 494.87 | 104.69 | 610.92
21 - Fueling Systems | 21 - Fueling Systems |  | 140 | 80 | -60 | ECP 16 simplification offueling sys | 80.72 | 0.72 |  | 80.72 | 80.72 | 0 | [7 empty] | 21 - 21 - Fueling Systems |  |  | 86.54 |  |  | 53 | [5 empty] | 12.07 | 318.95 | 20 | 351.01
22 - Torus Vacuum Pumping Systems | 22 - Torus Vacuum Pumping Systems |  | 388.1 | 388.1 |  |  | 388.7 | 0.6 |  | 388.7 | 388.7 | 0 | [7 empty] | 22 - 22 - Torus Vacuum Pumping Systems |  |  | 412.55 |  |  | 54 | [6 empty] | 220.96 |  | 220.96
25 - Neutral Beam Injection System | 25 - Neutral Beam Injection System |  | 308.9 | 308.9 | 0 |  | 308.9 | 0 |  | 308.9 | 308.9 | 0 | [7 empty] | 25 - 25 - Neutral Beam Injection System | 250 - Neutral Beam Injection System |  | 284.37 |  |  | 55 | [6 empty] | 161.65 |  | 161.65
|  | SUBTOTAL WBS 2 | 837 | 777 | -60 |  | 778.32 | 1.32 |  | 778.32 | 778.32 | 0 | [9 empty] | 783.46 | 783.46 | 0 |  | 56 | [6 empty] | 381.94 |  | 381.94
31 - Magnetic Diagnostics | 31 - Magnetic Diagnostics |  | 455.6 | 455.6 |  |  | 413.8 | -41.8 | Deleted $41k for install of sensors and mag diag. Alreadyy incl in wbs 184 | 413.8 | 413.8 | 0 | [7 empty] | 31 - 31 - Magnetic Diagnostics |  |  | 426.35 |  |  | 58 |  |  |  | 12.46 |  |  |  |  | 12.46
36 - Edge and Divertor Diagnostics | 36 - Edge and Divertor Diagnostics |  | 43.3 | 43.3 |  |  | 42.9 | -0.4 |  | 42.9 | 42.9 | 0 | [7 empty] | 36 - 36 - Edge and Divertor Diagnostics |  |  | 45.96 |  |  | 61 | 613 | [5 empty] | 94.51 |  | 94.51
38 - Electron Beam (EB) Mapping | 38 - Electron Beam (EB) Mapping |  | 295.3 | 295.3 |  |  | 290.6 | -4.7 |  | 290.6 | 290.6 | 0 | [7 empty] | 38 - 38 - Electron Beam (EB) Mapping |  |  | 310.09 |  |  | 62 | 621 |  |  |  |  | 15.89 | 217.16 |  | 233.04
39 - Diagnostics Integration | 39 - Diagnostics Integration |  | 366.7 | 366.7 |  |  | 369.4 | 2.7 |  | 369.4 | 369.4 | 0 | [7 empty] | 39 - 39 - Diagnostics Integration |  |  | 360.52 |  |  | 62 | 622
|  | SUBTOTAL WBS 3 | 1160.9 | 1160.9 |  |  | 1116.7 | -44.2 |  | 1116.7 | 1116.7 | 0 | [9 empty] | 1142.92 | 1142.92 | 0 |  | 62 | 623 |  |  |  |  | 27.34 | 202.88 |  | 230.22
| 41 - AC Power |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [13 empty] | 63 | [6 empty] | 109.3 |  | 109.3
41 - AC Power |  | 411 - Auxliary AC Power Systems | 471.1 | 471.1 |  |  | 439.83 | -31.27 | eliminated outlets on 2nd level | 439.83 | 439.83 | 0 | [7 empty] | 41 - 41 - AC Power | 411 - Auxliary AC Power Systems |  | 382.03 |  |  | 65 | 612 | 9.38 | [6 empty] | 9.38
41 - AC Power |  | 412 - Experimental AC Power Systems | 42.7 | 42.7 |  |  | 45 | 2.3 |  | 45 | 45 | 0 | [7 empty] | 41 - 41 - AC Power | 412 - Experimental AC Power Systems |  | 48.14 |  |  | 65 | 650 |  | 15 | [5 empty] | 15
| 43 - DC Systems |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [13 empty] | 71 | 740 | 32.15 | [6 empty] | 32.15
43 - DC Systems |  | 431 - C-Site DC Systems | 523.6 | 523.6 |  |  | 445.5 | -78.1 |  | 445.5 | 445.5 | 0 | [7 empty] | 43 - 43 - DC Systems | 431 - C-Site DC Systems |  | 453.94 |  |  | 72 | 720 |  |  | 47.59 |  |  |  |  | 47.59
43 - DC Systems |  | 432 - D-to-C Site DC Systems | 453.1 | 14 | -439.1 | ECP 16 reclassification to non MIE |  | -14 |  |  | 0 | 0 | [13 empty] | 73 | 730 |  |  | 69.87 | 20.1 | 74.45 |  |  | 164.42
43 - DC Systems |  | 433 - D-Site DC Systems | 13.4 | 13.4 |  |  |  | -13.4 |  |  | 0 | 0 | [13 empty] | 74 | 740 |  | 89.67 | 63.04 |  |  |  |  | 152.71
| 44 - Control and protection Systems |  |  | 0 |  |  |  | 0 |  |  | 0 | 0 | [13 empty] | 74 | 741 | 164 | 148.58 | [5 empty] | 312.58
44 - Control and protection Systems |  | 441 - Electrical Interlocks | 330.4 | 330.4 |  |  | 343.5 | 13.1 |  | 343.5 | 343.5 | 0 | [7 empty] | 44 - 44 - Control and protection Systems | 441 - Electrical Interlocks |  | 377.66 |  |  | 74 | 742 |  |  | 109.97 | 70.99 | 176.08 | 489.11 | 253.33 | 1099.47
44 - Control and protection Systems |  | 442 - Kirk Key Interlocks | 90.2 | 90.2 |  |  | 77.8 | -12.4 |  | 77.8 | 77.8 | 0 | [7 empty] | 44 - 44 - Control and protection Systems | 442 - Kirk Key Interlocks |  | 82.18 |  |  | 75 | 750 |  |  |  | 57.17 |  | 1623.78 | 684.6 | 2365.55
44 - Control and protection Systems |  | 443 - Real Time Control Systems | 12.8 | 12.8 |  |  | 13.3 | 0.5 |  | 13.3 | 13.3 | 0 | [7 empty] | 44 - 44 - Control and protection Systems | 443 - Real Time Control Systems |  | 14.27 |  |  | 76 | [6 empty] | 176.77 | 61.48 | 238.25
44 - Control and protection Systems |  | 444 - Instrument Systems | 349.1 | 349.1 |  |  | 294.2 | -54.9 |  | 294.2 | 294.2 | 0 | [7 empty] | 44 - 44 - Control and protection Systems | 444 - Instrument Systems |  | 312.65 |  |  | 81 | 810 | 445.94 | 961.12 | 803.59 | 756.15 | 732.59 | 612.89 | 196.53 | 4508.81
44 - Control and protection Systems |  | 445 - Coil protection Systems | 366.9 | 366.9 |  |  | 485.9 | 119 | Increased scope from Raki | 485.9 | 485.9 | 0 | [7 empty] | 44 - 44 - Control and protection Systems | 445 - Coil protection Systems |  | 522.1 |  |  | 82 | 820 | 518.9 | 1230.92 | 1193.56 | 1021.37 | 466.81 | 342.46 | 110.06 | 4884.08
| 45 - Power System Design and Integration |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [13 empty] | 84 | 840 | 251.25 | 218.68 | [5 empty] | 469.93
45 - Power System Design and Integration |  | 451 - System Design and Interfaces | 510 | 510 |  |  | 518.34 | 8.34 |  | 518.34 | 518.34 | 0 | [7 empty] | 45 - 45 - Power System Design and Integration | 451 - System Design and Interfaces |  | 520.33 |  |  | 85 | [6 empty] | 355.25 | 833.93 | 1189.18
45 - Power System Design and Integration |  | 452 - Electrical Systems Support | 240.2 | 240.2 |  |  | 243.96 | 3.76 |  | 243.96 | 243.96 | 0 | [7 empty] | 45 - 45 - Power System Design and Integration | 452 - Electrical Systems Support |  | 261.74 |  |  | AA | AAA | 112 | 260.69 | 350.85 | 340.47 | 340.08 | 172.79 |  | 1576.89
45 - Power System Design and Integration |  | 453 - System Testing (PTP's) | 302.4 | 302.4 |  |  | 305.49 | 3.09 |  | 305.49 | 305.49 | 0 | [7 empty] | 45 - 45 - Power System Design and Integration | 453 - System Testing (PTP's) |  | 324.72 |  |  | CC | CCC |  |  | 900 | 3840 | 3472 | 3041.61 | 1550.6 | 12804.21 | 12804
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0
46 - FCPC Building Modifications | 46 - FCPC Building Modifications |  | 1.3 | 1.3 | 0 |  | 1.3 | 0 |  | 1.3 | 1.3 | 0 | [7 empty] | 46 - 46 - FCPC Building Modifications | 460 |  | 1.3 |  |  |  | ECP -31 Plan | 6062.34 | 13698.81 | 19249.07 | 18107.65 | 15924.8 | 15274.57 | 4005.36 | 92322.55
|  | SUBTOTAL WBS 4 | 3707.2 | 3268.1 | -439.1 |  | 3214.12 | -53.98 |  | 3214.12 | 3214.12 | 0 | [9 empty] | 3301.06 | 3301.06 | 0 |  |  | ECP-30 Plan | 6062.34 | 13698.81 | 19100 | 18200 | 16000 | 15300 | 4000
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | [18 empty] | 57117.87 | 73042.67
51 - TCP/IP Infrastructure Systems | 51 - TCP/IP Infrastructure Systems |  | 292.9 | 292.9 |  |  | 288.9 | -4 |  | 288.9 | 288.9 | 0 | [7 empty] | 51 - 51 - TCP/IP Infrastructure Systems |  |  | 310.59 | [7 empty] | 57061.15 | 73061.15
52 - Central Instrumentation & Control | 52 - Central Instrumentation & Control |  | 660.7 | 660.7 |  |  | 569.3 | -91.4 |  | 569.3 | 569.3 | 0 | [7 empty] | 52 - 52 - Central Instrumentation & Control |  |  | 610.92
53 - Data Acquisition & Facility Computing | 53 - Data Acquisition & Facility Computing |  | 414.9 | 414.9 |  |  | 328.4 | -86.5 |  | 328.4 | 328.4 | 0 | [7 empty] | 53 - 53 - Data Acquisition & Facility Computing |  |  | 351.01
54 - Facility Timing & Synchronization | 54 - Facility Timing & Synchronization |  | 292 | 292 |  |  | 206.8 | -85.2 |  | 206.8 | 206.8 | 0 | [7 empty] | 54 - 54 - Facility Timing & Synchronization |  |  | 220.96
55 - Real Time Plasma & Power Supply Control Sys | 55 - Real Time Plasma & Power Supply Control Sys |  | 153.7 | 153.7 |  |  | 151.2 | -2.5 |  | 151.2 | 151.2 | 0 | [7 empty] | 55 - 55 - Real Time Plasma & Power Supply Control Sys |  |  | 161.65
56 - Central Safety Interlock Systems | 56 - Central Safety Interlock Systems |  | 361.7 | 361.7 |  |  | 357.7 | -4 |  | 357.7 | 357.7 | 0 | [7 empty] | 56 - 56 - Central Safety Interlock Systems |  |  | 381.94
58 - Central I&C management and Integration | 58 - Central I&C management and Integration |  | 12.9 | 12.9 |  |  | 12.9 | 0 |  | 12.9 | 12.9 | 0 | [7 empty] | 58 - 58 - Central I&C management and Integration |  |  | 12.46
|  | SUBTOTAL WBS 5 | 2188.8 | 2188.8 |  |  | 1915.2 | -273.6 |  | 1915.2 | 1915.2 | 0 | [9 empty] | 2049.53 | 2049.53 | 0
| 61 - Water Systems |  |  | 0 |  |  |  | 0 |  |  |  | 0
61 - Water Systems |  | 611 - C-Site Cooling System | 153.3 | 153.3 |  |  | 151.1 | -2.2 |  | 151.1 | 151.1 | 0 | [7 empty] | 61 - 61 - Water Systems | 611 - C-Site Cooling System |  | -
61 - Water Systems |  | 612 - NB Water Cooling Systems | 239.9 | -0.1 | -240 | ECP 16 not req'd for CD-4. |  | 0.1 |  |  | 0 | 0
61 - Water Systems |  | 613 - Vacuum Pumping System | 100 | 100 |  |  | 89.4 | -10.6 |  | 89.4 | 89.4 | 0 | [7 empty] | 61 - 61 - Water Systems | 613 - Vacuum Pumping System |  | 94.51
61 - Water Systems |  | 614 - Bakeout Water System | 38.5 | 0 | -38.5 | ECP 16 not req'd for CD-4. |  | 0 |  |  | 0 | 0
| 62 - Cryogenic Systems |  |  | 0 |  |  |  | 0 |  |  |  | 0
62 - Cryogenic Systems |  | 621 - LN2-LHe Supply System | 224.9 | 224.9 |  |  | 220.9 | -4 |  | 220.9 | 220.9 | 0 | [7 empty] | 62 - 62 - Cryogenic Systems | 621 - LN2-LHe Supply System |  | 233.04
62 - Cryogenic Systems |  | 622 - LN2 Coil Cooling Supply |  | 0 |  |  |  | 0 |  |  | 0 | 0 | [7 empty] | 62 - 62 - Cryogenic Systems | 622 - LN2 Coil Cooling Supply |  | 0
62 - Cryogenic Systems |  | 623 - GN2 Cryostat Cooling System | 222.5 | 222.5 |  |  | 218.7 | -3.8 |  | 218.7 | 218.7 | 0 | [7 empty] | 62 - 62 - Cryogenic Systems | 623 - GN2 Cryostat Cooling System |  | 230.22
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0
63 - Utility Systems | 63 - Utility Systems |  | 122.7 | 122.7 |  |  | 103.5 | -19.2 |  | 103.5 | 103.5 | 0 | [6 empty] | 63 - 63 - Utility Systems |  | 109.2996 |  | 109.3
| 65 - Facility Systems Integration |  |  | 0 |  |  |  | 0 |  |  |  | 0
65 - Facility Systems Integration |  | 612 - NB Water Cooling Systems | 9.4 | 9.4 |  |  | 9.4 | 0 |  | 9.4 | 9.4 | 0 | [7 empty] | 65 - 65 - Facility Systems Integration | 612 - NB Water Cooling Systems |  | 9.38
65 - Facility Systems Integration |  | 650 - Facility Systems Integration | 32.2 | 32.2 | 0 |  | 32.2 | 0 |  | 32.2 | 32.2 | 0 | [7 empty] | 65 - 65 - Facility Systems Integration | 650 - Facility Systems Integration |  | 15
|  | SUBTOTAL WBS 6 | 1143.4 | 864.9 | -278.5 |  | 825.2 | -39.7 |  | 825.2 | 825.2 | 0 | [9 empty] | 842 | 691.45 | -150.55 | -$151 C-site Water cooling system commissioning
71 - Shield Wall Seismic Modifications | 71 - Shield Wall Seismic Modifications |  | 32.2 | 32.2 |  |  | 32.2 | 0 |  | 32.2 | 32.2 | 0 | [7 empty] | 71 - 71 - Shield Wall Seismic Modifications | 740 - Machine Assembly Planning and Oversight |  | 32.15
72 - Control Room Refurbishment | 72 - Control Room Refurbishment |  | 48.8 | 48.8 |  |  | 50.2 | 1.4 |  | 50.2 | 50.2 | 0 | [7 empty] | 72 - 72 - Control Room Refurbishment | 720 |  | 47.59
73 - Platform Design & Fabrication | 73 - Platform Design & Fabrication |  | 161 | 161 |  |  | 161.3 | 0.3 |  | 161.3 | 161.3 | 0 | [7 empty] | 73 - 73 - Platform Design & Fabrication | 730 - Test Cell & Basement Assembly Operations |  | 164.42
| 74 - Machine Assembly Planning and Oversight |  |  | 0 |  |  |  | 0 |  |  |  | 0
74 - Machine Assembly Planning and Oversight |  | 740 - Machine Assembly Planning and Oversight | 148 | 148 |  |  | 152.55 | 4.55 |  | 152.55 | 152.55 | 0 | [7 empty] | 74 - 74 - Machine Assembly Planning and Oversight | 740 - Machine Assembly Planning and Oversight |  | 152.71
74 - Machine Assembly Planning and Oversight |  | 741 - Planning Prior to Machine Assembly | 281.6 | 281.6 |  |  | 281.57 | -0.03 |  | 281.57 | 281.57 | 0 | [7 empty] | 74 - 74 - Machine Assembly Planning and Oversight | 741 - Planning Prior to Machine Assembly |  | 312.58
74 - Machine Assembly Planning and Oversight |  | 742 - Construction Management | 1194.2 | 1194.2 |  |  | 1068.15 | -126.05 |  | 1068.15 | 1068.15 | 0 | [7 empty] | 74 - 74 - Machine Assembly Planning and Oversight | 742 - Construction Management |  | 1099.47
| 75 - Test Cell and Basement Assembly Operations |  |  | 0 |  |  |  | 0 |  |  | 0 | 0
75 - Test Cell and Basement Assembly Operations |  | 750 - Test Cell & Basement Assembly Operations | 2184.9 | 2184.9 |  |  | 2238.93 | 54.03 |  | 2238.93 | 2238.93 | 0 | [7 empty] | 75 - 75 - Test Cell and Basement Assembly Operations | 750 - Test Cell & Basement Assembly Operations |  | 2365.55
76 - Tooling Design & Fabrication | 76 - Tooling Design & Fabrication |  | 223.7 | 223.7 |  |  | 222.99 | -0.71 |  | 222.99 | 222.99 | 0 | [7 empty] | 76 - 76 - Tooling Design & Fabrication |  |  | 238.25
|  | SUBTOTAL WBS 7 | 4274.4 | 4274.4 |  |  | 4207.89 | -66.51 |  | 4207.89 | 4207.89 | 0 | [9 empty] | 4412.72 | 4412.72 | 0
81 - Project Management and Control | 81 - Project Management and Control |  | 3556.8 | 3556.8 |  |  | 3450.278 | -106.522 | re-estimted out year needs. Cost share with res prep | 3450.278 | 3596 | 145.722 | Prior year scope retirement fore FY04 | [6 empty] | 81 - 81 - Project Management and Control | 810 - Project Management & Control |  | 4508.81
82 - Project Engineering | 82 - Project Engineering |  | 4013.7 | 4207.5 | 193 | ECP 16 FY04 cost variance +193 | 4367.5 | 160 |  | 4367.5 | 4426 | 58.5 | New scope for FY05. Dimensional control coordinator. | [6 empty] | 82 - 82 - Project Engineering | 820 - Project Engineering |  | 4884.08
84 - Project Physics | 84 - Project Physics |  | 412.2 | 412.2 |  |  | 412.47 | 0.27 |  | 470.17 | 470.17 | 0 | [7 empty] | 84 - 84 - Project Physics | 840 - Project Physics |  | 469.93
85 - Integrated Systems Testing | 85 - Integrated Systems Testing |  | 1220.1 | 1220.1 | 0 |  | 1220.68 | 0.58 |  | 1220.68 | 1220.68 | 0 | [7 empty] | 85 - 85 - Integrated Systems Testing |  |  | 1189.18
|  | SUBTOTAL WBS 8 | 9202.8 | 9396.6 | 193 |  | 9450.928 | 54.328 |  | 9508.628 | 9712.85 | 204.222 | [9 empty] | 11160.2 | 11052 | -108.2 | +$50 Dimensional control coord in FY05; -$37k Research support in FY06; -$121 ISTP documentation req'd for CD-4
PPPL Allocations | PPPL Allocations |  | 983.3 | 983.3 |  |  | 1128.6 | 145.3 | Adjusted based upon FY04 allocation costs and estimated out year mapping | 1128.6 | 1128.6 | 0 | [7 empty] | AA - PPPL Allocations | PPPL Allocations | 1576.89 | 1576.89
|  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Contingency | Contingency |  | 13454.9 | 13455 |  |  | 13052.89 | -402.11 |  | 12755.89 | 11609.548 | -1146.342 | [7 empty] | CC - Contingency | Contingency | 12804.21 | 12804.21
0
[8 empty] | 0 | [13 empty] | 0
|  |  | 86346 | 86345.9 | -0.1 | 0 | 86345.718 | -0.18199 |  | 86345.388 | 86345.288 | -1.2506e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92322.47 | 92322.49 | 0.02
FY04 FY05 FY06 FY07 FY08 FY09
$23.7
$73.0
$57.1
41.2
$88.9
$92.3
$88.9