| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Ron Strykowsky |  |  | Date: April 21, 2005 |  |
| ECP No: 030 |  | ECP Title: DOE Directed FY2005 Rebaseline |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: WBS Managers, Project Engineers, NCSX QA, ES&H, NCSX Engineering Manager |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |  |  |  |  |
| Actions (1) Revise cost and schedule baseline by April 30, 2005 to reflect revised DOE annual funding guidance. |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Under Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Ron Strykowsky | Date: April 19, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: DOE directed rebaseline to reflect revised annual funding guidance. Impacted WBS Elements: WBS Elements: 12, 13, 14, 15, 16, 17, 18, 19, 2, 3, 4, 5, 6, 7, & 8. In addition, contingency adjusted to reflect added stretch-out costs. Impacts of Change (Briefly Describe): At DOE direction, NCSX Project rebaselined to support a flat funding profile of $15.9 peak (FY2006-FY2008). As a result of this direction, the following cost and schedule impacts were noted: - Project Stretch Out and Rate Adjustments - Work scope stretched out; - Overhead rates revised to reflect most recent PPPL and ORNL rates; - Impact of escalation due to stretch out included; - First plasma revised to July 2009 with 5 months schedule contingency; and - Re-evaluated contingency balance for the remaining work scope. Contingency balance is $12.8M, or 25% of work remaining from April 1, 2005. Summary of Level I baseline parameters: TEC = $92.3M Project completion date: July, 2009 Funding profile (BA) for remainder of the project: FY-06: $15,9M FY-07: $15.9M FY-08: $15.9M FY-09: $3.4M Assessment of Other Options: None |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |
| --- | --- | --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |  |  |
| Originator: Ron Strykowsky |  | Date: April 21, 2005 |  |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. - Revised Resource Loaded Baseline - Update PEP to reflect this data Description of Change: The Table Below Summarizes the Cost Impact of this ECP: WBS Element; Previous Baseline (ECP-029) ($); Current Baseline ($); Change Due to Stretchout ($). 12 – Vacuum Vessel; $9,168K; $9,439K; $271K. 13 – Conventional Coils; $4,552K; $4,779K; $226K. 14 – Modular Coils; $26,839K; $28,046K; $1,207K. 15 - Structures; $1,381K; $1,413K; $32K. 16 – Coil Services; $1,036K; $1,146K; $110K. 17 – Cryostat & Base Suppt Structure; $1,321K; $1,361K; $40K. 18 – Field Period Assembly; $5,118K; $5,424K; $306K. 19 – Stellarator Core Mgmt & Integr; $2,421K; $2,752K; $331K. Subtotal WBS 1 – Stellarator Core; $51,837K; $54,360K; $2,523K. WBS 2 – Auxilliary Systems; $778K; $783K; $5K. WBS 3 – Diagnostic Systems; $1,117K; $1,143K; $26K. WBS 4 – Electrical Power Systems; $3,214K; $3,301K; $87K. WBS 5 – I&C Systems; $1,915K; $2,050K; $134K. WBS 6 – Facility Systems; $825K; $842K; $17K. WBS 7 Test Cell Prep & Machine Assy; $4,208K; $4,411K; $203K. Subtotal WBS 8 – Project Oversight & Suppt; $10,841K; $12,633K; $1,791K. Subtotal; $74,736K; $79,523K; $4,787K. Contingency; $11,610K; $12,804K; $1,194K. TOTALS; $86,345K; $92.326K; $5,961K. Of this cost increase of $4,787K (before contingency): - Management (Period Dependent) - $1,186K - Field Oversight & Supervision (Task Dependent) - $1,225K - Overhead and Rates - $2,375K Overall contingency increased to 25% on the work remaining. |
| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |  |  |
| Originator: Ron Strykowsky | Date: April 21, 2005 |  |  |
| Continuation Sheet: The Table Below Summarizes the Schedule Impact of this ECP: |  |  |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Ron Strykowsky | Date: April 21, 2005 |
| Continuation Sheet: The Table Below Provides the Contingency Analysis: The Major Drivers of Contingency are: - WBS 12 (Vacuum Vessel) and 14 (Modular Coils) – maintain 10% on the balance of the VVSA and MCWF contracts - WBS 13 (Conventional Coils) – fabrication risk based upon preliminary estimate to complete – FDR scheduled in May 2005 - WBS 18 (Field Period Assembly) – estimate for field period assembly fixturing based upon initial supplier contacts – hardware design still in conceptual stage - WBS 18 (Field Period Assembly) and WBS 82 (Project Engineering) – dimensional control coordination and support - WBS 14 (Modular Coil) – modular coil assembly hardware (nuts, bolts, & shims) and MC winding operations |  |