| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Ron Strykowsky | Date: June 3, 2005 |
| ECP No: 031 | ECP Title: FY2005 DOE Directed Baseline Change Proposal |
| Required Reviewers |
| Required Reviewers for this ECP: WBS Managers, Project Engineers, NCSX QA, ES&H, NCSX Engineering Manager |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions (1) Adopt new baseline. |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Deputy Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: April 19, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: DOE directed rebaseline to reflect revised annual funding guidance. Impacted WBS Elements: WBS Elements: 12, 13, 14, 15, 16, 17, 18, 19, 2, 3, 4, 5, 6, 7, & 8. In addition, contingency adjusted to reflect added stretch-out costs. Impacts of Change (Briefly Describe): At DOE direction, NCSX Project rebaselined to support a flat funding profile of $15.9 peak (FY2006-FY2008). As a result of this direction, the project work is re-scheduled, resulting in a 14-month delay in the project end date (CD-4 milestone), to July, 2009. The impact on the total estimated cost (TEC) is a $6.1M increase, to $92.4M, attributed as follows: Management stretchout ($1.2M); Job oversight and support stretchout ($1.2M); PPPL allocations stretchout ($0.4M); Escalation $0.4M Rate increases driven by reduced overall funding at PPPL ($1.6M); Contingency associated with the above increases ($1.2M) Defense Contract Management Agency (DCMA) QC service ($0.075M) Summary of Level I baseline parameters: TEC = $92.4M (Increase of ~$6.1M) Project completion date: July, 2009 Budget contingency on work remaining from April 1, 2005: $12.8M (25%) Schedule contingency: 5 months Funding profile (BA in $M) for the project: FY-03 FY-04 FY-05 FY-06 FY-07 FY-08 FY-09 TEC CD-3 Baseline 7..9 15.9 15.9 22.1 19.4 5.1 86.3 New Baseline (This ECP) 7.9 15.9 17.5 15.9 15.9 15.9 3.4 92.4 Assessment of Other Options: None. Directed Change. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: April 21, 2005 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. Revised Resource Loaded Baseline Update PEP to reflect this data Description of Change: The Table Below Summarizes the Cost Impact of this ECP: WBS Element Previous Baseline (ECP-030) ($) Current Baseline ($) Change ($) 12 – Vacuum Vessel $9,204K $9,531K $327K 13 – Conventional Coils $4,552K $4,790K $238K 14 – Modular Coils $27,062K $28,091K $1,029K 15 - Structures $1,381K $1,413K $32K 16 – Coil Services $1,036K $1,140K $104K 17 – Cryostat & Base Suppt Structure $1,321K $1,361K $40K 18 – Field Period Assembly $5,118K $5,430K $312K 19 – Stellarator Core Mgmt & Integr $2,421K $2,752K $331K Subtotal WBS 1 – Stellarator Core $52,096K $54,508K $2,412K WBS 2 – Auxilliary Systems $778K $783K $5K WBS 3 – Diagnostic Systems $1,117K $1,143K $26K WBS 4 – Electrical Power Systems $3,214K $3,301K $87K WBS 5 – I&C Systems $1,915K $2,050K $134K WBS 6 – Facility Systems $674K $691K $17K WBS 7 Test Cell Prep & Machine Assy $4,208K $4,413K $205K Subtotal WBS 8 – Project Oversight & Suppt $9,605K $11,052K $1,447K Subtotal $73,607K $77,941K $4,334K PPPL Allocations $1,129K $1,577K $448K Contingency $11,610K $12,804K $1,194K DCMA 75k 75k TOTALS $86,345K $92,401K $6,056K Overall contingency $12,804K 25% on the work remaining. |
| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: April 21, 2005 |
| Continuation Sheet: The Table Below Summarizes the Schedule Impact of this ECP: |