| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Phil Heitzenroeder | Date: July 7, 2005 |
| ECP No: 033 Rev 1 | ECP Title: MCWF Technical Requirements Revision |
| Required Reviewers |
| Required Reviewers for this ECP: Dave Williamson, Wayne Reiersen, Brad Nelson, Ron Strykowsky, Judy Malsbury, Frank Malinowski, Jerry Levine, Larry Sutton, Bob Simmons |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Revise MCWF CSPEC (NCSX-CSPEC-141-03) by July 15th. Revise MCWF SOW (NCSX-SOW-141-02) by July 15th. Incorporate ECN-4994 changes by June 15, 2005 (completed under Rev 0 of this ECP) Issue Approved RFD-14-003 by June 15, 2005 (completed under Rev 0 of this ECP) Issue contract modification to EIO by July 15th specifying NCSX-CSPEC-141-03-Rev. 8 Update cost and schedule baseline by July 15th. |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Deputy Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Phil Heitzenroeder | Date: July 7, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: Revision 0 - Clarifications of technical requirements, clarification of delivery requirements in SOW, revision of several drawings to reflect redesigned lead block, and approval of a Request for Deviation on material testing. This ECP was approved in mid-June as a Class 3 ECP since no impact on the cost or schedule baselines. However, subsequent discussions with EIO revealed additional concerns and revisions needed. Accordingly, this Revision 1 incorporates the results of the discussions with EIO. Revision 1 - this revision incorporates the following major changes (attached version of CSPEC and SOW include all the revisions): PPPL added a requirement to heat treat each MCWF casting to ensure adequate stress relief PPPL clarified surface finish requirements and weld repair requirements. Other miscellaneous changes to CSPEC made. Impacted WBS Elements: WBS 141 Impacts of Change (Briefly Describe): Revision 0 - This ECP dealt entirely with technical changes to requirements that had no impact on performance, cost, or schedule. Revision 1: There are not cost or schedule impacts associated with the change in surface finish and weld repair requirements. These changes are more clarifications and agreements reached with EIO on clarifications. Cost impact to add the requirement of heat treating each MCWF casting is $28.8K and should not impact EIO delivery schedule. Heat treatment was already a requirement to develop the strength required. What is added is a final, lower temperature stress relieving cycle under heat treatment to relax the residual stress in the weld repair area. It is this additional requirement that resulted in a cost increase. Net impact is a required drawdown of contingency of $28.8K from $12,804K to $12, 775.2K Assessment of Other Options: None |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Phil Heitzenroeder | Date: July 7, 2005 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. CSPEC (NCSX-CSPEC-141-03-08) – Currently in signature cycle SOW (NCSX-SOW-141-02-04) – approved ECN-4994 impacting drawings SE141-114, SE141-115, and SE141-116 RFD-14-003 Description of Change: Changes to CSPEC: Added ASTM A751-01, “Standard Test Methods, Practices, and Terminology for Chemical Analysis of Steel Products,” to Section 2.1.1. This ASTM Spec is used to define the casting chemistry determination method used by MetalTek (and standard industry practice). Revised Section 3.1.1.1: Added note about alloy composition ranges – this note cautioning that although the alloy is based on that developed for the prototype, it differs inasmuch as the range of chemistry is now specified. This was requested by EIO, presumably as a note to their personnel. Clarifies that Table 3-1 is for the casting chemistry. Table 3-2 was added which gives the chemical constituents of the weld wire. Table 3-1: The % Si was changed from 0.5% to 0.7% max per EIO’s request. Previous requirement of 0.5% was deemed to be to restrictive. The acceptability of this change was confirmed by a June 1st e-mail from Dick Reed: “Phil, There should be no problem with the higher Si (0.7%) spec. Dick”; Revised Table 3-3: Changed yield from 34 ksi (234.4 MPa) to 30 ksi (206.8 Mpa). This refers to RT yield. Was 29ksi for for prototype and was subsequently increased. However, the higher 34 ksi value was found to be difficult to achieve consistently with actual attached specimens that received representative thermal processing ; Revised Section 3.1.1.4 to change surface finish requirements. Relaxed finish requirements to <250 microinch in non-critical areas. This is anticipated to possibly provide some schedule relief. The visual examination requirements of Section 3.1.1.6.1 were revised to eliminate the need to do a higher level of visual examination in the foundry of areas which will then be machined in subsequent steps. This change removed unnecessarily restrictive language that could be misinterpreted – does not result in any change to the level of inspection required; Revised Section 3.2.3.1 to clarify stress relieving processes. Stress relieving is now specified for all castings as a final operation after all weld “upgrades” have been completed. This will reduce the risk of distortions due to residual stresses in welds and the risk that machining rates will be impacted by non-uniformity of metal properties that could occur without stress relieving; Revised Sections 3.2.3.2.2.2 and 3.2.3.2.2.3 concerning weld repair to address weld repairs due to machining errors – this was not foreseen in the original spec; |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Phil Heitzenroeder | Date: July 7, 2005 |
| Continuation Sheet: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) Changes to CSPEC (continued): In Section 4.2.1, the requirements for chemical analysis was clarified ; we want to know analysis of material for each ladle rather than a single average value, since we cannot be sure of how the material from the three ladles will mix. Consequently, we now clearly say analysis of the material for each ladle is required. Revised Section 4.2.2: Deleted the requirement for both transverse and longitudinal test specimens and clarified test specimen details. It was deemed impractical and meaningless to get longitudinal and transverse measurements since the data indicates that the material is not directionally sensitive; To make sure that it is absolutely clear that we expect yield strength, E, ultimate strength, elongation, and Charpy V-notch results from all three zones, the statement : “…for the three zones specified in Section 4.2.2 for each casting…” was added to Sections 4.2.2.1, 4.2.2.2, and 4.2.2.3. This was added for emphasis – the vendor missed this in pouring C1 casting; Section 4.2.2.4 has been revised to clarify the quantity requirements, their origin, and the need to engrave or stamp so that their location is preserved for the additional test material to be supplied with each casting and for each zone;. Revised Section 4.2.2.5: Clarified wording for weld filler properties requirements; and Revised Table 6-1 and Table 6-2 to reflect latest approved models and drawings and approved RFDs. Changes to SOW: Revision 3 - Section 5.4.3 revised to clarify the clarify dimensional inspection file format and contents. Revision 4 – Section 5.5 revised to clarify retention requirements of CAD/CAM files. Changes to Drawings (per ECN-4994): Drawings SE141-114, SE141-115, and SE141-116 were revised due to the redesign of the lead blocks. As a result it was necessary to change the slot length from 6.38-in to 7.5-in and the slot width from 1.5-in to 1.5625-in. The location and dimensions of four tee base tapped holes w/ spotface were also changed to conform to the new design. The mounting pad dimensioning scheme was revised, resulting in a slight change in the pad height for the Type-A and –B winding forms. Approval of RFD-14-003 Section 4.2.2 required that material be tested in the transverse and longitudinal directions. This is performed when testing wrought materials, but is typically not performed in cast materials as it offers no significant information. The primary reason is that in cast materials, the grain structure is equiaxed, uniform, and has no directionality. This deviation was approved and the commitment was made to delete this requirement from the CSPEC (Rev 8). |