| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Phil Heitzenroeder | Date: June 9, 2005 |
| ECP No: 033 | ECP Title: MCWF Technical Requirements Revision |
| Required Reviewers |
| Required Reviewers for this ECP: Dave Williamson, Wayne Reiersen, Brad Nelson, Ron Strykowsky, Judy Malsbury, Frank Malinowski, Jerry Levine, Larry Sutton, Bob Simmons |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Revise MCWF CSPEC (NCSX-CSPEC-141-03) – will be Revision 8 by June 15, 2005 Revise MCWF SOW (NCSX-SOW-141-02) – will be Revision 3 by June 15, 2005 Incorporate ECN-4994 changes by June 15, 2005 Issue Approved RFD-14-003 by June 15, 2005 |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Deputy Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Phil Heitzenroeder | Date: June 9, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: Clarifications of technical requirements, clarification of delivery requirements in SOW, revision of several drawings to reflect redesigned lead block, and approval of a Request for Deviation on material testing. Impacted WBS Elements: WBS 141 Impacts of Change (Briefly Describe): See details on the following page. Assessment of Other Options: None |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Phil Heitzenroeder | Date: June 9, 2005 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. CSPEC (NCSX-CSPEC-141-03) - Draft A (dated June 10th) SOW (NCSX-SOW-141-02) – Draft A (dated June 10th) ECN-4994 impacting drawings SE141-114, SE141-115, and SE141-116 RFD-14-003 Description of Change: Changes to CSPEC: In Section 3.1.1.1, a sentence was added cautioning that although the alloy is based on that developed for the prototype, it differs inasmuch as the range of chemistry is now specified. This was requested by EIO, presumably as a note to their personnel. Table 3-2 was added which gives the chemical constituents of the weld wire. These data are from the Metrode product sheets. Table 3-1: The % Si was changed from 0.5 to 0.7% max per EIO’s request. The acceptability of this change was confirmed by a June 1st e-mail from Dick Reed: “Phil, There should be no problem with the higher Si (0.7%) spec. Dick” The visual examination requirements of Section 3.1.1.6.1 were revised to eliminate the need to do a higher level of visual examination in the foundry of areas which will then be machined in subsequent steps. The visual examination is now in two distinct steps: one in the foundry and one in the machine shop. For the cast surfaces, Level III is now specified. For machined surfaces, Level II is now specified. It should be noted that machined surfaces are also required to meet a 125 micro-inch surface finish requirement in Section 3.1.1.4, but the visual examination takes into account casting imperfections that are not covered by the machining finish. (We may want to re-examine if this secondary visual examination is needed after we have some experience with it.) In Section 3.2.3.2.3: Iterative weld repairs -i.e., more than 2 at the same location) are now addressed. This was discussed with J. Edwards during our May meeting, and he is in agreement. In Section 4.2.1, the requirements for chemical analysis was clarified ; we want to know analysis of material for each ladle rather than a single average value, since we cannot be sure of how the material from the three ladles will mix. Consequently, we now clearly say analysis of the material for each ladle is required. To make sure that it is absolutely clear that we expect yield strength, E, ultimate strength, elongation, and Charpy V-notch results from all three zones, the statement : “…for the three zones specified in Section 4.2.2 for each casting…” was added to Sections 4.2.2.1, 4.2.2.2, and 4.2.2.3. Section 4.2.2.4 has been revised to clarify the quantity requirements, their origin, and the need to engrave or stamp so that their location is preserved for the additional test material to be supplied with each casting and for each zone. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Phil Heitzenroeder | Date: June 9, 2005 |
| Continuation Sheet: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) Changes to CSPEC (continued): The verification requirements for the weld filler material properties were re-worded to clarify their needs. They refer back to the new Table 3.2, since our intention is to see how consistent the chemical composition of the weld wire and material properties. If experience shows that it is reasonable to assess the weld wire properties from its chemistry, we may want to re-assess the need for properties testing of each lot of filler wire. Section 4.2.2 was revised to delete the requirement to test the material in the transverse and longitudinal directions. (See RFD-14-003). Changes to SOW: Section 5.4.3 revised to clarify the to clarify dimensional inspection file format and contents. Changes to Drawings (per ECN-4994): Drawings SE141-114, SE141-115, and SE141-116 were revised due to the redesign of the lead blocks. As a result it was necessary to change the slot length from 6.38-in to 7.5-in and the slot width from 1.5-in to 1.5625-in. The location and dimensions of four tee base tapped holes w/ spotface were also changed to conform to the new design. The mounting pad dimensioning scheme was revised, resulting in a slight change in the pad height for the Type-A and –B winding forms. Approval of RFD-14-003 Section 4.2.2 required that material be tested in the transverse and longitudinal directions. This is performed when testing wrought materials, but is typically not performed in cast materials as it offers no significant information. The primary reason is that in cast materials, the grain structure is equiaxed, uniform, and has no directionality. This deviation was approved and the commitment was made to delete this requirement from the CSPEC. |