| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Bob Simmons |  |  | Date: July 7, 2005 |  |
| ECP No: 034 |  | ECP Title: VV Trinos Flange |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: P. Goranson, M. Viola, B. Nelson, R. Strykowsky, W. Reiersen, J. Levine, J. Malsbury, F. Malinowski |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |  |  |  |  |
| Actions (1) Adjust Cost/Schedule Baseline Documentation by July 30th. |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Deputy Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: Bob Simmons | Date: July 7, 2005 |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: The project has authorized the VVSA supplier to purchase Trinos Flanges for the ports. The originally specified MDC flanges, which have already been purchased, will be shipped to PPPL and will be available for fabrication of the removable port extensions during the operations phase of the project. This change is made to reduce the risk of field errors due to high magnetic permeability in the flanges. This is projected at a cost increase of ~$39K. This change does not require a change to any technical requirements. In parallel, the Control Rooms Wall Refurbishment task has now been determined to be a GPP activity consistent with PPPL’s cost accounting standards. This will free up ~$39.5K (what was in the NCSX job) to pay for this cost increase in the VV for the procurement of the Trinos Flanges. Impacted WBS Elements: WBS 12 and WBS 75. Impacts of Change (Briefly Describe): Net result will be zero, but funds will be transferred from WBS 75 to WBS 12. Assessment of Other Options: Other material flanges evaluated, but none will meet the magnetic permeability requirements as closely as do the Trinos flanges. List Attachments, Impacted Documents, etc. (1) Budget Reconciliation Sheet (ECP-031 – ECP-033 and ECP-034) |  |