## ECP31 ECP33-34Reconciliation
| NCSX rebaseline reconciliation | [15 empty] | FIRST PLASMA July 2009
wbs2 |  |  | ECP 14 | ECP 16 | change | description | ECP 18 | change | description | ECP 21 | change | description |  | WBS2 | DESC | ECP031 | ECP-033 & ECP -034 | Changes
11 - In-Vessel Components |  | 111 - Limiters | 0.1 | 0.1 |  |  | 0.1 | 0 |  | 0.1 | 0 |  | 11 - 11 - In-Vessel Components | 11 - 11 - In-Vessel Components | 111 - Limiters | 0 | 0
| 12 - Vacuum Vessel Systems |  |  | 0 |  |  |  | 0 |  |  | 0
12 - Vacuum Vessel Systems |  | 121 - Vacuum Vessel Assembly | 7891.7 | 7906.3 | 14.6 | ECP 16 FY04 cost variance +14.6k | 8061.3 | 155 | .Increased Viola to 2 days /week oversight +$63k; Increased field weld joint full size sample =+$96k | 8061.3 | 769.7 |  | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 121 - Vacuum Vessel Assembly | 8792 | 8831 | 39 | Trinos Flanges (ECP-034)
12 - Vacuum Vessel Systems |  | 122 - Vacuum Vessel Thermal Insulation | 174.7 | 174.7 |  |  | 176.03 | 1.33 |  | 176.03 | 19.97 |  | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 122 - Vacuum Vessel Thermal Insulation | 196 | 196 | 0
12 - Vacuum Vessel Systems |  | 123 - Vacuum Vessel Heating and Cooling Distrib | 375.7 | 375.7 |  |  | 373.37 | -2.33 |  | 373.37 | 194.63 |  | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 123 - Vacuum Vessel Heating and Cooling Distrib | 568 | 568 | 0
12 - Vacuum Vessel Systems |  | 124 - Vacuum Vessel Supports | 62 | 62 |  |  | 97.63 | 35.63 | .Lateral supports +22k | 97.63 | 13.37 |  | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 124 - Vacuum Vessel Supports | 111 | 111 | 0
12 - Vacuum Vessel Systems |  | 125 - Vacuum Vessel Local I&C | 27.3 | 27.3 |  |  | 29.04 | 1.74 |  | 29.04 | -11.04 |  | 12 - 12 - Vacuum Vessel Systems | 12 - 12 - Vacuum Vessel Systems | 125 - Vacuum Vessel Local I&C | 18 | 18 | 0
|  | subtotal | 8531.4 | 8546 | 14.6 |  | 8737.37 | 191.37 |  | 8737.37 | 986.63 |  |  |  |  | 9685 | 9724 | 39
| 13 - Conventional Coils |  |  | 0 |  |  |  | 0 |  |  | 0
13 - Conventional Coils |  | 130 - Conventional Coil Design | 613.1 | 613.1 |  |  | 737.81 | 124.71 | Kalish re-estimate of new design | 737.81 | 129.19 | Completion of Prelim design and the re-estimate of final design tasks. |  | 13 - 13 - Conventional Coils | 130 - Conventional Coil Design | 867 | 867 | 0
13 - Conventional Coils |  | 131 - TF Coils | 1458.8 | 1458.8 |  |  | 1594.58 | 135.78 | Kalish re-estimate of new design | 1594.58 | 680.42 |  |  | 13 - 13 - Conventional Coils | 131 - TF Coils | 2275 | 2275 | 0
13 - Conventional Coils |  | 132 - PF Coils | 1777.3 | 1777.3 |  |  | 1870.43 | 93.13 | Kalish re-estimate | 1870.43 | 14.57 |  |  | 13 - 13 - Conventional Coils | 132 - PF Coils | 1885 | 1885 | 0
13 - Conventional Coils |  | 133 - External Trim Coils | 381.1 | 181.1 | -200 | ECP 16 simplification of trim coli sys -200k | 145.64 | -35.46 | Kalish re-estimate | 145.64 | 112.36 |  |  | 13 - 13 - Conventional Coils | 133 - External Trim Coils | 258 | 258 | 0
13 - Conventional Coils |  | 134 - Conventional Coil Local | 73.4 | 73.4 |  |  | 92.63 | 19.23 | Kalish re-estimate | 92.63 | -0.63 |  |  | 13 - 13 - Conventional Coils | 134 - Conventional Coil Local | 92 | 92 | 0
|  | subtotal | 4303.7 | 4103.7 | -200 |  | 4441.09 | 337.39 |  | 4441.09 | 935.91 |  |  |  |  | 5377 | 5377 | 0
| 14 - Modular Coils |  |  | 0 |  |  |  | 0 |  |  | 0
14 - Modular Coils |  | 141 - Modular Coil Winding Form | 12788.6 | 12881.6 | 93 | ECP 16 FY04 cost variance +93 | 13180.68 | 299.08 | +$52k MCWF analysis, +85 EIO s/c,+54 JPP s/c,+79 title III MCWF fab | 13180.68 | 730.22 |  |  | 14 - 14 - Modular Coils | 141 - Modular Coil Winding Form | 13873 | 13910.9 | 37.9 | Addl Heat Treatment (ECP-033)
14 - Modular Coils |  | 142 - Modular Coil Windings and Assembly | 9438 | 9577 | 139 | ECP 16 FY04 cost variance +139. | 9614.03 | 37.03 | Chrzanowski/Meighan oversight of TRC +202k | 9853 | 1829 |  |  | 14 - 14 - Modular Coils | 142 - Modular Coil Windings and Assembly | 11682 | 11682 | 0
14 - Modular Coils |  | 143 - Modular Coil Local I&C | 121.2 | 121.2 |  |  | 120.42 | -0.78 |  | 120.42 | -34.42 |  |  | 14 - 14 - Modular Coils | 143 - Modular Coil Local I&C | 86 | 86 | 0
14 - Modular Coils |  | 144 - Modular Coil Winding Facility & Fixtures | 2707.3 | 3214.3 | 507 | ECP 16 FY04 cost variance +507 | 3285.22 | 70.92 |  | 3285.22 | 67.78 |  |  | 14 - 14 - Modular Coils | 144 - Modular Coil Winding Facility & Fixtures | 3353 | 3353 | 0
|  | subtotal | 25055.1 | 25794.1 | 739 |  | 26200.35 | 406.25 |  | 26439.32 | 2592.58 |  |  |  |  | 28994 | 29031.9 | 37.9
| 15 - Structures |  |  | 0 |  |  |  | 0 |  |  | 0
15 - Structures |  | 151 - Coil Support Structure | 1447.8 | 1447.8 |  |  | 1380.71 | -67.09 | Kalish re-estimate | 1380.71 | 32.29 |  |  | 15 - 15 - Structures | 151 - Coil Support Structure | 1413 | 1413 | 0
| 16 - Coil Services |  |  | 0 |  |  |  | 0 |  |  | 0 | [5 empty] | 0 | 0
16 - Coil Services |  | 161 - LN2 Distribution | 337.5 | 337.5 |  |  | 338.11 | 0.61 |  | 338.11 | 35.89 |  |  | 16 - 16 - Coil Services | 161 - LN2 Distribution | 374 | 374 | 0
16 - Coil Services |  | 162 - Electrical Leads | 621.3 | 621.3 |  |  | 619.03 | -2.27 |  | 619.03 | 66.97 |  |  | 16 - 16 - Coil Services | 162 - Electrical Leads | 686 | 686 | 0
16 - Coil Services |  | 163 - Coil Protection System | 78.1 | 78.1 |  |  | 78.86 | 0.76 |  | 78.86 | 7.14 |  |  | 16 - 16 - Coil Services | 163 - Coil Protection System | 86 | 86 | 0
|  | subtotal | 1036.9 | 1036.9 |  |  | 1036 | -0.9 |  | 1036 | 110 |  |  |  |  | 1146 | 1146 | 0
| 17 - Cryostat and Base Support Structure |  |  | 0 |  |  |  | 0 |  |  | 0
17 - Cryostat and Base Support Structure |  | 171 -Cryostat | 862.9 | 862.9 |  |  | 877.69 | 14.79 |  | 877.69 | 56.31 |  |  | 17 - 17 - Cryostat and Base Support Structure | 171 -Cryostat | 934 | 934 | 0
17 - Cryostat and Base Support Structure |  | 172 - Base Support Structure | 438.2 | 438.2 |  |  | 443.45 | 5.25 |  | 443.45 | -16.45 |  |  | 17 - 17 - Cryostat and Base Support Structure | 172 - Base Support Structure | 427 | 427 | 0
|  | 173-Spacer manipulator | [11 empty] | 17 - 17 - Cryostat and Base Support Structure | 173 - Spacer Manipulator | 0 | 0 | 0
|  | subtotal | 1301.1 | 1301.1 |  |  | 1321.14 | 20.04 |  | 1321.14 | 39.86 |  |  |  |  | 1361 | 1361 | 0
| 18 - Field Period Assembly |  |  | 0 |  |  |  | 0 |  |  | 0
18 - Field Period Assembly |  | 181 - Field Period Assembly Planning/Oversight | 1379.3 | 1379.3 |  |  | 1014.4 | -364.9 | Reduced Viola to .7 fte during FP assy.-$175k. $190 trabsferred to wbs185 | 1014.4 | 490.6 |  |  | 18 - 18 - Field Period Assembly | 181 - Field Period Assembly Planning/Oversight | 1505 | 1505 | 0
18 - Field Period Assembly |  | 182 - TFTR Test Cell Area preparations | 92.9 | 92.9 |  |  | 1e-05 | -92.9 | part of FP assy | 1e-05 | 35 |  |  | 18 - 18 - Field Period Assembly | 182 - TFTR Test Cell Area preparations | 35 | 35 | 0
18 - Field Period Assembly |  | 183 - Receive Inspect and Test Coils | 77.4 | 77.4 |  |  | 79.12 | 1.72 |  | 79.12 | -79.12 |  |  |  |  | 0 | 0 | 0
18 - Field Period Assembly |  | 184 - Receive Inspect and Test VV | 326.3 | 326.3 |  |  | 530.14 | 203.84 | +202k increased cost for stud instl, cooling tubes, magnetics instl, | 530.14 | -530.14 |  |  |  |  | 0 | 0 | 0
18 - Field Period Assembly |  | 185 - Assemble Field Periods | 1509.4 | 1509.4 |  |  | 1818.56 | 309.16 | +$129 MC sub-assy, | 1818.56 | 316.44 |  |  | 18 - 18 - Field Period Assembly | 185 - Assemble Field Periods | 2135 | 2135 | 0
18 - Field Period Assembly |  | 186 - Tooling Design and Fabrication | 1217.2 | 1217.2 |  |  | 1200.04 | -17.16 |  | 1200.04 | 337.96 |  |  | 18 - 18 - Field Period Assembly | 186 - Tooling Design and Fabrication | 1538 | 1538 | 0
18 - Field Period Assembly |  | 187 - Measurement Systems | 463.2 | 463.2 |  |  | 475.83 | 12.63 |  | 475.83 | 36.17 |  |  | 18 - 18 - Field Period Assembly | 187 - Measurement Systems | 512 | 512 | 0
|  | subtotal | 5065.7 | 5065.7 |  |  | 5118.09 | 52.39 |  | 5118.09 | 606.91 |  |  |  |  | 5725 | 5725 | 0
| 19 - Stellarator Core Management and Integration |  |  | 0 |  |  |  | 0 |  |  | 0
19 - Stellarator Core Management and Integration |  | 191 - Stellarator Core Management & Oversight | 1083 | 1113 | 30 | ECP 16 FY04 cost variance +30 | 946.44 | -166.56 |  | 946.44 | 95.56 |  |  | 19 - 19 - Stellarator Core Management and Integration | 191 - Stellarator Core Management & Oversight | 1042 | 1042 | 0
19 - Stellarator Core Management and Integration |  | 192 - Stellarator Core Integration & Analysis | 1568.5 | 1568.5 | 0 |  | 1474.58 | -93.92 | Demo method for determining current center +88.Moved Brooks to WBS 82 -158 | 1474.58 | 235.42 |  |  | 19 - 19 - Stellarator Core Management and Integration | 192 - Stellarator Core Integration & Analysis | 1710 | 1710 | 0
|  | subtotal | 2651.5 | 2681.5 | 30 |  | 2421.02 | -260.48 |  | 2421.02 | 330.98 |  |  |  |  | 2752 | 2752 | 0
|  | SUBTOTAL WBS 1 | 49393.3 | 49976.9 | 583.6 |  | 50655.87 | 678.97 |  | 50894.84 | 5635.16 |  |  |  |  | 56453 | 56529.9 | 76.9
21 - Fueling Systems | 21 - Fueling Systems |  | 140 | 80 | -60 | ECP 16 simplification offueling sys | 80.72 | 0.72 |  | 80.72 | 6.28 |  |  | 21 - 21 - Fueling Systems |  | 87 | 87 | 0
22 - Torus Vacuum Pumping Systems | 22 - Torus Vacuum Pumping Systems |  | 388.1 | 388.1 |  |  | 388.7 | 0.6 |  | 388.7 | 24.3 |  |  | 22 - 22 - Torus Vacuum Pumping Systems |  | 413 | 413 | 0
25 - Neutral Beam Injection System | 25 - Neutral Beam Injection System |  | 308.9 | 308.9 | 0 |  | 308.9 | 0 |  | 308.9 | -24.9 |  |  | 25 - 25 - Neutral Beam Injection System | 250 - Neutral Beam Injection System | 284 | 284 | 0
|  | SUBTOTAL WBS 2 | 837 | 777 | -60 |  | 778.32 | 1.32 |  | 778.32 | 5.68 |  |  |  |  | 784 | 784 | 0
31 - Magnetic Diagnostics | 31 - Magnetic Diagnostics |  | 455.6 | 455.6 |  |  | 413.8 | -41.8 | Deleted $41k for install of sensors and mag diag. Alreadyy incl in wbs 184 | 413.8 | 12.2 |  |  | 31 - 31 - Magnetic Diagnostics |  | 426 | 426 | 0
36 - Edge and Divertor Diagnostics | 36 - Edge and Divertor Diagnostics |  | 43.3 | 43.3 |  |  | 42.9 | -0.4 |  | 42.9 | 3.1 |  |  | 36 - 36 - Edge and Divertor Diagnostics |  | 46 | 46 | 0
38 - Electron Beam (EB) Mapping | 38 - Electron Beam (EB) Mapping |  | 295.3 | 295.3 |  |  | 290.6 | -4.7 |  | 290.6 | 19.4 |  |  | 38 - 38 - Electron Beam (EB) Mapping |  | 310 | 310 | 0
39 - Diagnostics Integration | 39 - Diagnostics Integration |  | 366.7 | 366.7 |  |  | 369.4 | 2.7 |  | 369.4 | -8.4 |  |  | 39 - 39 - Diagnostics Integration |  | 361 | 361 | 0
|  | SUBTOTAL WBS 3 | 1160.9 | 1160.9 |  |  | 1116.7 | -44.2 |  | 1116.7 | 26.3 |  |  |  |  | 1143 | 1143 | 0
| 41 - AC Power |  |  | 0 |  |  |  | 0 |  |  | 0
41 - AC Power |  | 411 - Auxliary AC Power Systems | 471.1 | 471.1 |  |  | 439.83 | -31.27 | eliminated outlets on 2nd level | 439.83 | -57.83 |  |  | 41 - 41 - AC Power | 411 - Auxliary AC Power Systems | 382 | 382 | 0
41 - AC Power |  | 412 - Experimental AC Power Systems | 42.7 | 42.7 |  |  | 45 | 2.3 |  | 45 | 3 |  |  | 41 - 41 - AC Power | 412 - Experimental AC Power Systems | 48 | 48 | 0
| 43 - DC Systems |  |  | 0 |  |  |  | 0 |  |  | 0
43 - DC Systems |  | 431 - C-Site DC Systems | 523.6 | 523.6 |  |  | 445.5 | -78.1 |  | 445.5 | 8.5 |  |  | 43 - 43 - DC Systems | 431 - C-Site DC Systems | 454 | 454 | 0
43 - DC Systems |  | 432 - D-to-C Site DC Systems | 453.1 | 14 | -439.1 | ECP 16 reclassification to non MIE |  | -14 |  |  | 0 |  |  |  |  | 0 | 0 | 0
43 - DC Systems |  | 433 - D-Site DC Systems | 13.4 | 13.4 |  |  |  | -13.4 |  |  | 0 |  |  |  |  | 0 | 0 | 0
| 44 - Control and protection Systems |  |  | 0 |  |  |  | 0 |  |  | 0 | [5 empty] | 0
44 - Control and protection Systems |  | 441 - Electrical Interlocks | 330.4 | 330.4 |  |  | 343.5 | 13.1 |  | 343.5 | 34.5 |  |  | 44 - 44 - Control and protection Systems | 441 - Electrical Interlocks | 378 | 378 | 0
44 - Control and protection Systems |  | 442 - Kirk Key Interlocks | 90.2 | 90.2 |  |  | 77.8 | -12.4 |  | 77.8 | 4.2 |  |  | 44 - 44 - Control and protection Systems | 442 - Kirk Key Interlocks | 82 | 82 | 0
44 - Control and protection Systems |  | 443 - Real Time Control Systems | 12.8 | 12.8 |  |  | 13.3 | 0.5 |  | 13.3 | 0.7 |  |  | 44 - 44 - Control and protection Systems | 443 - Real Time Control Systems | 14 | 14 | 0
44 - Control and protection Systems |  | 444 - Instrument Systems | 349.1 | 349.1 |  |  | 294.2 | -54.9 |  | 294.2 | 18.8 |  |  | 44 - 44 - Control and protection Systems | 444 - Instrument Systems | 313 | 313 | 0
44 - Control and protection Systems |  | 445 - Coil protection Systems | 366.9 | 366.9 |  |  | 485.9 | 119 | Increased scope from Raki | 485.9 | 36.1 |  |  | 44 - 44 - Control and protection Systems | 445 - Coil protection Systems | 522 | 522 | 0
| 45 - Power System Design and Integration |  |  | 0 |  |  |  | 0 |  |  | 0
45 - Power System Design and Integration |  | 451 - System Design and Interfaces | 510 | 510 |  |  | 518.34 | 8.34 |  | 518.34 | 1.66 |  |  | 45 - 45 - Power System Design and Integration | 451 - System Design and Interfaces | 520 | 520 | 0
45 - Power System Design and Integration |  | 452 - Electrical Systems Support | 240.2 | 240.2 |  |  | 243.96 | 3.76 |  | 243.96 | 18.04 |  |  | 45 - 45 - Power System Design and Integration | 452 - Electrical Systems Support | 262 | 262 | 0
45 - Power System Design and Integration |  | 453 - System Testing (PTP's) | 302.4 | 302.4 |  |  | 305.49 | 3.09 |  | 305.49 | 19.51 |  |  | 45 - 45 - Power System Design and Integration | 453 - System Testing (PTP's) | 325 | 325 | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
46 - FCPC Building Modifications | 46 - FCPC Building Modifications |  | 1.3 | 1.3 | 0 |  | 1.3 | 0 |  | 1.3 | -0.3 |  |  | 46 - 46 - FCPC Building Modifications | 460 | 1 | 1 | 0
|  | SUBTOTAL WBS 4 | 3707.2 | 3268.1 | -439.1 |  | 3214.12 | -53.98 |  | 3214.12 | 86.88 |  |  |  |  | 3301 | 3301 | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
51 - TCP/IP Infrastructure Systems | 51 - TCP/IP Infrastructure Systems |  | 292.9 | 292.9 |  |  | 288.9 | -4 |  | 288.9 | 22.1 |  |  | 51 - 51 - TCP/IP Infrastructure Systems |  | 311 | 311 | 0
52 - Central Instrumentation & Control | 52 - Central Instrumentation & Control |  | 660.7 | 660.7 |  |  | 569.3 | -91.4 |  | 569.3 | 41.7 |  |  | 52 - 52 - Central Instrumentation & Control |  | 611 | 611 | 0
53 - Data Acquisition & Facility Computing | 53 - Data Acquisition & Facility Computing |  | 414.9 | 414.9 |  |  | 328.4 | -86.5 |  | 328.4 | 22.6 |  |  | 53 - 53 - Data Acquisition & Facility Computing |  | 351 | 351 | 0
54 - Facility Timing & Synchronization | 54 - Facility Timing & Synchronization |  | 292 | 292 |  |  | 206.8 | -85.2 |  | 206.8 | 14.2 |  |  | 54 - 54 - Facility Timing & Synchronization |  | 221 | 221 | 0
55 - Real Time Plasma & Power Supply Control Sys | 55 - Real Time Plasma & Power Supply Control Sys |  | 153.7 | 153.7 |  |  | 151.2 | -2.5 |  | 151.2 | 10.8 |  |  | 55 - 55 - Real Time Plasma & Power Supply Control Sys |  | 162 | 162 | 0
56 - Central Safety Interlock Systems | 56 - Central Safety Interlock Systems |  | 361.7 | 361.7 |  |  | 357.7 | -4 |  | 357.7 | 24.3 |  |  | 56 - 56 - Central Safety Interlock Systems |  | 382 | 382 | 0
58 - Central I&C management and Integration | 58 - Central I&C management and Integration |  | 12.9 | 12.9 |  |  | 12.9 | 0 |  | 12.9 | -0.9 |  |  | 58 - 58 - Central I&C management and Integration |  | 12 | 12 | 0
|  | SUBTOTAL WBS 5 | 2188.8 | 2188.8 |  |  | 1915.2 | -273.6 |  | 1915.2 | 134.8 |  |  |  |  | 2050 | 2050 | 0
| 61 - Water Systems |  |  | 0 |  |  |  | 0 |  |  | 0
61 - Water Systems |  | 611 - C-Site Cooling System | 153.3 | 153.3 |  |  | 151.1 | -2.2 |  | 151.1 | -151.1 |  |  | 61 - 61 - Water Systems | 611 - C-Site Cooling System | 0 | 0 | 0
61 - Water Systems |  | 612 - NB Water Cooling Systems | 239.9 | -0.1 | -240 | ECP 16 not req'd for CD-4. |  | 0.1 |  |  | 0 |  |  |  |  | 0 | 0 | 0
61 - Water Systems |  | 613 - Vacuum Pumping System | 100 | 100 |  |  | 89.4 | -10.6 |  | 89.4 | 5.6 |  |  | 61 - 61 - Water Systems | 613 - Vacuum Pumping System | 95 | 95 | 0
61 - Water Systems |  | 614 - Bakeout Water System | 38.5 | 0 | -38.5 | ECP 16 not req'd for CD-4. |  | 0 |  |  | 0 |  |  |  |  | 0 | 0 | 0
| 62 - Cryogenic Systems |  |  | 0 |  |  |  | 0 |  |  | 0
62 - Cryogenic Systems |  | 621 - LN2-LHe Supply System | 224.9 | 224.9 |  |  | 220.9 | -4 |  | 220.9 | 12.1 |  |  | 62 - 62 - Cryogenic Systems | 621 - LN2-LHe Supply System | 233 | 233 | 0
62 - Cryogenic Systems |  | 622 - LN2 Coil Cooling Supply |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 62 - 62 - Cryogenic Systems | 622 - LN2 Coil Cooling Supply | 0 | 0 | 0
62 - Cryogenic Systems |  | 623 - GN2 Cryostat Cooling System | 222.5 | 222.5 |  |  | 218.7 | -3.8 |  | 218.7 | 11.3 |  |  | 62 - 62 - Cryogenic Systems | 623 - GN2 Cryostat Cooling System | 230 | 230 | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
63 - Utility Systems | 63 - Utility Systems |  | 122.7 | 122.7 |  |  | 103.5 | -19.2 |  | 103.5 | 5.5 |  | 63 - 63 - Utility Systems |  | 109.2996 | 109 | 109 | 0
| 65 - Facility Systems Integration |  |  | 0 |  |  |  | 0 |  |  | 0
65 - Facility Systems Integration |  | 612 - NB Water Cooling Systems | 9.4 | 9.4 |  |  | 9.4 | 0 |  | 9.4 | -0.4 |  |  | 65 - 65 - Facility Systems Integration | 612 - NB Water Cooling Systems | 9 | 9 | 0
65 - Facility Systems Integration |  | 650 - Facility Systems Integration | 32.2 | 32.2 | 0 |  | 32.2 | 0 |  | 32.2 | -17.2 |  |  | 65 - 65 - Facility Systems Integration | 650 - Facility Systems Integration | 15 | 15 | 0
|  | SUBTOTAL WBS 6 | 1143.4 | 864.9 | -278.5 |  | 825.2 | -39.7 |  | 825.2 | -134.2 |  |  |  |  | 691 | 691 | 0
71 - Shield Wall Seismic Modifications | 71 - Shield Wall Seismic Modifications |  | 32.2 | 32.2 |  |  | 32.2 | 0 |  | 32.2 | -0.2 |  |  | 71 - 71 - Shield Wall Seismic Modifications | 740 - Machine Assembly Planning and Oversight | 32 | 32 | 0
72 - Control Room Refurbishment | 72 - Control Room Refurbishment |  | 48.8 | 48.8 |  |  | 50.2 | 1.4 |  | 50.2 | -41.7 |  |  | 72 - 72 - Control Room Refurbishment | 720 | 48 | 8.5 | -39.5 | Control Room Walls - GPP (ECP-034)
73 - Platform Design & Fabrication | 73 - Platform Design & Fabrication |  | 161 | 161 |  |  | 161.3 | 0.3 |  | 161.3 | 0.7 |  |  | 73 - 73 - Platform Design & Fabrication | 730 - Test Cell & Basement Assembly Operations | 162 | 162 | 0
| 74 - Machine Assembly Planning and Oversight |  |  | 0 |  |  |  | 0 |  |  | 0 | [6 empty] | 0
74 - Machine Assembly Planning and Oversight |  | 740 - Machine Assembly Planning and Oversight | 148 | 148 |  |  | 152.55 | 4.55 |  | 152.55 | 0.45 |  |  | 74 - 74 - Machine Assembly Planning and Oversight | 740 - Machine Assembly Planning and Oversight | 153 | 153 | 0
74 - Machine Assembly Planning and Oversight |  | 741 - Planning Prior to Machine Assembly | 281.6 | 281.6 |  |  | 281.57 | -0.03 |  | 281.57 | 31.43 |  |  | 74 - 74 - Machine Assembly Planning and Oversight | 741 - Planning Prior to Machine Assembly | 313 | 313 | 0
74 - Machine Assembly Planning and Oversight |  | 742 - Construction Management | 1194.2 | 1194.2 |  |  | 1068.15 | -126.05 |  | 1068.15 | 30.85 |  |  | 74 - 74 - Machine Assembly Planning and Oversight | 742 - Construction Management | 1099 | 1099 | 0
| 75 - Test Cell and Basement Assembly Operations |  |  | 0 |  |  |  | 0 |  |  | 0 | [5 empty] | 0 | 0
75 - Test Cell and Basement Assembly Operations |  | 750 - Test Cell & Basement Assembly Operations | 2184.9 | 2184.9 |  |  | 2238.93 | 54.03 |  | 2238.93 | 127.07 |  |  | 75 - 75 - Test Cell and Basement Assembly Operations | 750 - Test Cell & Basement Assembly Operations | 2366 | 2366 | 0
76 - Tooling Design & Fabrication | 76 - Tooling Design & Fabrication |  | 223.7 | 223.7 |  |  | 222.99 | -0.71 |  | 222.99 | 15.01 |  |  | 76 - 76 - Tooling Design & Fabrication |  | 238 | 238 | 0
|  | SUBTOTAL WBS 7 | 4274.4 | 4274.4 |  |  | 4207.89 | -66.51 |  | 4207.89 | 163.61 |  |  |  |  | 4411 | 4371.5 | -39.5
81 - Project Management and Control | 81 - Project Management and Control |  | 3556.8 | 3556.8 |  |  | 3450.278 | -106.522 | re-estimted out year needs. Cost share with res prep | 3450.278 | 1058.722 | Prior year scope retirement fore FY04 |  | 81 - 81 - Project Management and Control | 810 - Project Management & Control | 4509 | 4509 | 0
82 - Project Engineering | 82 - Project Engineering |  | 4013.7 | 4207.5 | 193 | ECP 16 FY04 cost variance +193 | 4367.5 | 160 |  | 4367.5 | 943.5 | New scope for FY05. Dimensional control coordinator. |  | 82 - 82 - Project Engineering | 820 - Project Engineering | 5311 | 5311 | 0
84 - Project Physics | 84 - Project Physics |  | 412.2 | 412.2 |  |  | 412.47 | 0.27 |  | 470.17 | -0.17 |  |  | 84 - 84 - Project Physics | 840 - Project Physics | 470 | 470 | 0
85 - Integrated Systems Testing | 85 - Integrated Systems Testing |  | 1220.1 | 1220.1 | 0 |  | 1220.68 | 0.58 |  | 1220.68 | -31.68 |  |  | 85 - 85 - Integrated Systems Testing |  | 1189 | 1189 | 0
|  | SUBTOTAL WBS 8 | 9202.8 | 9396.6 | 193 |  | 9450.928 | 54.328 |  | 9508.628 | 1970.372 |  |  |  |  | 11479 | 11479 | 0
PPPL Allocations | PPPL Allocations |  | 983.3 | 983.3 |  |  | 1128.6 | 145.3 | Adjusted based upon FY04 allocation costs and estimated out year mapping | 1128.6 | 448.4 |  |  | AA - PPPL Allocations | PPPL Allocations | 1577 | 1577 | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
Contingency | Contingency |  | 13454.9 | 13455 |  |  | 13052.89 | -402.11 |  | 12755.89 | -551.29 |  |  | CC - Contingency | Contingency | 12242 | 12204.6 | 37.4 | Contingency Drawdown
0
|  |  | 86346 | 86345.9 | -0.1 | 0 | 86345.718 | -0.18199 |  | 86345.388 | 7785.912 |  |  |  |  | 94131 | 94131 | 0
$23.7
$73.0
$57.1
41.2
$88.9
$94.1