| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Bob Simmons | Date: August 3, 2005 |
| ECP No: 035 | ECP Title: Changes to MCWF Technical Requirements |
| Required Reviewers |
| Required Reviewers for this ECP: Dave Williamson, Phil Heitzenroeder, Brad Nelson, Wayne Reiersen, Judy Malsbury, Frank Malinowski, Tom Brown, Jerry Levine, Ron Strykowsky |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions (1) Update drawings per ECN#5009 by August 10th (2) Update Specification (NCSX-CSPEC-141-03) by August 10th (3) Obtain confirmation/quote from supplier by August 20th (4) Determine cost and schedule impact of adding holes by August 20th (5) Process/Disposition MetalTek Corrective Action Request #1323 by August 20th |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Deputy Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-035 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: August 3, 2005 |
| Overview of Change Type of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Description and Reasons for Changes: Poloidal Break Insulator Re-Design - The original design of the bolt insulators consisted of thick, counterbored G-11 “washers”. When MTM machined them from G-11 rod, they cracked due to the fact that the glass plies are now laid up in a stacked fashion rather than in the “jellyroll” fashion as it was when purchased many years ago. PPPL has had similar experience on other projects and concurs with this being a manufacturability issue. Neither PPPL nor MTM has been able to find sources of the jellyroll type layup. Consequently, PPPL proposed that instead of individual insulating washers at each of the 7 bolts, a flat plate that covers the entire surface be used in which 7 holes are provided for the bolts. The glass in this configuration will be in flatwise compression, virtually eliminating the likelihood of cracking. MTM agrees with this design change and notes that they have sufficient material on hand to accomplish this. Re-Definition of O-Ring Groove Extent in Machining Models - There are several locations on the winding form where NCSX and EIO agree that the o-ring groove does not (or, in some cases cannot) be machined. In a few areas, the base of the “T” is too shallow to permit the groove to be machined, and in the lead block area the block would cover the groove, making it inaccessible. Consequently, NCSX agreed to prepare revised machining drawings which indicate these areas where no o-ring will be needed to clarify the requirements. Elimination of Lead Block Attachment Tapped Holes - MTM noted that, due to geometry, they cannot fit a 90 degree head in to drill and tap the two holes on each side of each “T” which were provided to attach the lead blocks. After consideration of several options, NCSX chose to delete these holes from the machining requirement, and instead just require that MTM locate and scribe (or otherwise clearly mark) the center of each tapped hole. PPPL will weld threaded stainless steel bushings on site to perform the function of the tapped holes that were previously shown. Addition of (4) Holes in the Shell of All Three MCWF Types for Coolant Lines - Four clearance holes are being added through the shells of the winding forms in the vicinity of the poloidal break to permit routing of the nitrogen coolant lines. These are new additions; they will be drilled at PPPL. Impact of Change in Chemistry Requirements – MetalTek provided a corrective action #1323 dated July 27, 2005, identified an issue in measuring phosphorus and sulfur levels. While this Corrective Action Request will be dispositioned separately, the proposed changes (from 0.015% to 0.04%) for both phosphorus and sulfur in the modified CF 8M material used for these castings sets the requirement at the same level used for standard CF 8M and so is deemed acceptable. Table 3-1 of the CSPEC will be revised accordingly. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-035 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Bob Simmons | Date: August 3, 2005 |
| Continuation Sheet Impacted WBS Elements: WBS 14 (Job 1403) Impacts of Change (Briefly Describe): Items (1) – (3) and (5) are not anticipated to have any cost or schedule impacts if direction is provided to vendor this week (Week ending August 6th). Item (4) will have a cost impact of approximately $14,400 (exact cost impact to be identified within two weeks – by August 20th. Drawdown of contingency will be addressed in ECP-036, currently being processed. Assessment of Other Options: None List Attachments, Impacted Documents, etc. Draft of Specification NCSX-CSPEC-141-03-09-dA RFD-14-004 ECN#5009 MetalTek Correctivie Action #1323 dated July 27, 2005 |