| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Bob Simmons |  |  | Date: August 3, 2005 |  |
| ECP No: 036 |  | ECP Title: Risk Retirement and Identification |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: Paul Goranson, Brad Nelson, Dave Williamson, Mike Cole, Wayne Reiersen, H. Neilson, Judy Malsbury, Frank Malinowski, Jerry Levine, Ron Strykowsky |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |  |  |  |  |
| Actions - Incorporate Risk Retirement items (#1) into the July Baseline by August 5th. - Incorporate new risk identification item (#2) into the August Baseline by August 31st. |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Deputy Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-036 |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: | Date: |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Description and Reasons for Change: Summary: Approval of this ECP will require a drawdown of contingency of $797K from $12,767K in ECP-033 to $11969K (~25% of remaining work scope). - Risk Retirement Items - WBS 121 - Cancellation of Field Weld R&D (-$63.9) - WBS 121 - Drawdown on Undistributed Budget to correct data entry error reflected in ECP-031 (-$114K) - WBS 142 – Closeout of TRC job (+$305K) - WBS 142 - Reassignment of task from WBS 144 (+$28K)( 1409-130 & 135 Coil Test Stand cryostat desing and fabrication) - WBS 142 – Additional work for dimensional control lacing test now closed out (+$14K) - WBS 142 – Additional work on design and fabrication of the TRC clamp now closed out (+$13K) - WBS 142 – Reassignment of mod coil local instrumentation and control activities from WBS 143 (+$86K) (MC I&C Procurement and Installation) - WBS 143 - Reassignment of mod coil local instrumentation and control activities to WBS 142 (-$86K) MC I&C Procurement and Installation) - WBS 144 – Closeout of Modular Coil Winding Facility job (+$230K) - WBS 144 - Reassignment of task to WBS 142 (-$28K) )( 1409-130 & 135 Coil Test Stand cryostat desing and fabrication) - WBS 144 – Closeout of Coil Test Stand job (+$406K) - WBS 192 – Reduction in estimate for current center demonstration activities (-$14K) - New Risk Identification Items - WBS 141 - ECP-035 identified the need to bore 4 holes/casting to accommodate N2 cooling lines. This work will be accomplished on the completed casting after it is received at PPPL and will be done by PPPL labor (+$14.4K) Impacted WBS Elements: WBS 121 (-$171K), WBS 141 ($14.4K), WBS 142 (+$446K), WBS 143 (-$86K), WBS 144 (+$608K). and WBS 192 (-$14K) Assessment of Other Options: None. No other offsets identified at this time. |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-036 |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: | Date: |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. - Budget Reconciliation Sheet - Revised Cost and Schedule Bar Charts for July 2005 Summary of Cost Impacts: WBS Element; Previous Baseline (ECP-033 & ECP-034) ($); Current Baseline ($); Change ($). 12 – Vacuum Vessel; $9,571K; $9,400K; ($171K). 13 – Conventional Coils; $4,790K; $4,790K; -. 14 – Modular Coils; $28,131K; $29,114K; +$983K. 15 - Structures; $1,413K; $1,413K; -. 16 – Coil Services; $1,140K; $1,140K; -. 17 – Cryostat & Base Suppt Structure; $1,361K; $1,361K; -. 18 – Field Period Assembly; $5,430K; $5,430K; -. 19 – Stellarator Core Mgmt & Integr; $2,752K; $2,738K; -$14K. Subtotal WBS 1 – Stellarator Core; $54,588K; $55,385K; +$797K. WBS 2 – Auxilliary Systems; $783K; $783K; -. WBS 3 – Diagnostic Systems; $1,143K; $1,143K; -. WBS 4 – Electrical Power Systems; $3,301K; $3,301K; -. WBS 5 – I&C Systems; $2,050K; $2,050K; -. WBS 6 – Facility Systems; $691K; $691K; -. WBS 7 Test Cell Prep & Machine Assy; $4,473K; $4,473K; -. WBS 8 – Project Oversight & Suppt; $11,053K; $11,053K; -. Subtotal; $77,982K; $78,779K; +$797K. PPPL Allocations; $1,577K; $1,577K; -. Contingency; $12,767K; $11,969K; -$797K. DCMA; 75k; 75k. TOTALS; $92,401K; $92,401K; -. Remaining contingency ($11,969K) is ~ XX%. |