| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Bob Simmons |  |  | Date: August 3, 2005 |  |
| ECP No: 036 |  | ECP Title: Risk Retirement and Identification |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: Paul Goranson, Brad Nelson, Dave Williamson, Mike Cole, Wayne Reiersen, H. Neilson, Judy Malsbury, Frank Malinowski, Jerry Levine, Ron Strykowsky |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |  |  |  |  |
| Actions - Incorporate Risk Retirement items (#1) into the July Baseline by August 5th. - Incorporate new risk identification item (#2) into the August Baseline by August 31st. |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Deputy Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-036 |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: | Date: |
| Overview of Change Type of of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Description and Reasons for Change: Summary: Approval of this ECP will require a drawdown of contingency of $797K from $12,767K in ECP-033 to $11969K (~25% of remaining work scope). Hutch’s comments: 1. Do we really need to document budget shifts at the 3-digit level that are all within WBS 14 (d., g., h., j.)? If so, at least list them under a different heading, like “Re-allocation of budget” or something. 2.No reasons are given justifying the budget requests. Please provide same before the CCB meeting, otherwise we are not ready for the CCB. 3.I question why we are covering the cost of holes but not the lacing or the mods to the lead blocks. Why not just overhaul the winding estimate all at once, looking for offsets. We can discuss at the CCB meeting. - Risk Retirement Items - WBS 121 - Cancellation of Field Weld R&D (-$57.3K) - WBS 121 - Drawdown on Undistributed Budget to correct data entry error reflected in ECP-031 (-$114K) - WBS 142 – Closeout of TRC job (+$305K) - WBS 142 - Reassignment of task from WBS 144 (+$28K) ( 1409-130 & 135 Coil Test Stand Cryostat Design and Fabrication) - WBS 142 – Additional work for dimensional control lacing test now closed out (+$14K) - WBS 142 – Additional work on design and fabrication of the TRC clamp now closed out (+$13K) - WBS 142 – Reassignment of mod coil local instrumentation and control activities from WBS 143 (+$86K) (MC I&C Procurement and Installation) - WBS 143 - Reassignment of mod coil local instrumentation and control activities to WBS 142 (-$86K) (MC I&C Procurement and Installation) - WBS 144 – Closeout of Modular Coil Winding Facility job (+$230K) - WBS 144 - Reassignment of task to WBS 142 (-$28K) ( 1409-130 & 135 Coil Test Stand Cryostat Design and Fabrication) - WBS 144 – Closeout of Coil Test Stand job (+$406K) - WBS 192 – Reduction in estimate for current center demonstration activities (-$14K) - New Risk Identification Items - WBS 141 - ECP-035 identified the need to bore 4 holes/casting to accommodate N2 cooling lines. This work will be accomplished on the completed casting after it is received at PPPL and will be done by PPPL labor (+$14.4K) Impacted WBS Elements: WBS 121 (-$171K), WBS 141 ($14.4K), WBS 142 (+$446K), WBS 143 (-$86K), WBS 144 (+$608K). and WBS 192 (-$14K) Assessment of Other Options: None. No other offsets identified at this time. |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-036 |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |  |
| Originator: | Date: |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) Assessment of Other Options: None. No other offsets identified at this time. List Attachments, Impacted Documents, etc. - Budget Reconciliation Sheet - Revised Cost and Schedule Bar Charts for July 2005 Summary of Cost Impacts: WBS Element; Previous Baseline (ECP-033 & ECP-034) ($); Current Baseline ($); Change ($). 12 – Vacuum Vessel; $9,571K; $9,400K; ($171K). 13 – Conventional Coils; $4,790K; $4,790K; -. 14 – Modular Coils; $28,131K; $29,114K; +$983K. 15 - Structures; $1,413K; $1,413K; -. 16 – Coil Services; $1,140K; $1,140K; -. 17 – Cryostat & Base Suppt Structure; $1,361K; $1,361K; -. 18 – Field Period Assembly; $5,430K; $5,430K; -. 19 – Stellarator Core Mgmt & Integr; $2,752K; $2,738K; -$14K. Subtotal WBS 1 – Stellarator Core; $54,588K; $55,385K; +$797K. WBS 2 – Auxilliary Systems; $783K; $783K; -. WBS 3 – Diagnostic Systems; $1,143K; $1,143K; -. WBS 4 – Electrical Power Systems; $3,301K; $3,301K; -. WBS 5 – I&C Systems; $2,050K; $2,050K; -. WBS 6 – Facility Systems; $691K; $691K; -. WBS 7 Test Cell Prep & Machine Assy; $4,473K; $4,473K; -. WBS 8 – Project Oversight & Suppt; $11,053K; $11,053K; -. Subtotal; $77,982K; $78,779K; +$797K. PPPL Allocations; $1,577K; $1,577K; -. Contingency; $12,767K; $11,969K; -$797K. DCMA; 75k; 75k. TOTALS; $92,401K; $92,401K; -. Remaining contingency ($11,969K) is ~ 25%. |