| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Ron Strykowsky | Date: August 5, 2005 |
| ECP No: 036 | ECP Title: Risk Retirement, Budget Reallocation, Correction of Data Error, and New Work |
| Required Reviewers |
| Required Reviewers for this ECP: Paul Goranson, Brad Nelson, Dave Williamson, Mike Cole, Wayne Reiersen, H. Neilson, Judy Malsbury, Frank Malinowski, Jerry Levine, Ron Strykowsky |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Incorporate Risk Retirement items (#1) into the July Baseline by August 5th. Incorporate new risk identification item (#2) into the August Baseline by August 31st. |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Deputy Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-036 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: August 5, 2005 |
| Overview of Change Type of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL Description and Reasons for Change: Summary: Approval of this ECP will require a drawdown of contingency of $797.1K from $12,767K in ECP-033 to $11969K (~25% of remaining work scope). Risk Retirement Items (+$896.7K) WBS 12 (-$57.3K) – Closeout of Job 1206 – VV Field Weld Joint R&D. R&D completed to date provides sufficient data. Work now completed and risk retired. WBS 14 – (+$954K) Closeout of Job 1410 - TRC Fabrication (+$318K) – Contributors to the overrun included; rework of the final clamps, unanticipated labor to install ground wrap, dimensional control interaction in winding side A, chill plate installation longer that anticipated, and as a result of initial trials the process for installing the outer epoxy shell was changed. Now completed and risk retired. Closeout of Job 1412 – Complete Winding Facility (+$230K). Contributors to this overrun include modifications and punch list changes to the facility hardware and components due to experienced gained in winding the TRC. Work now completed and risk retired. Closeout of Job 1409 – Modular Coil Test Stand (+$406K). Design and testing of the system more extensive than anticipated due to; electrical isolation problems at cold temperatures, single phase cryogenic operation requirements, and addressing OSHA and IH requirements relative to ventilation. The later required HVAC mods. Work now completed and risk retired. Reallocation of Budgets Within 3-Digit WBS Elements ($0K) Reassignment of Coil Test Stand Cryostat Design and Fabrication Task between three-digit WBS elements within WBS 14. Reassignment of mod coil local instrumentation and control procurement and installation activities between three-digit WBS elements within WBS 14. Reallocation of budget ($14k) from WBS 19 Job 1901 - Reduction in estimate for current center demonstration activities to WBS 14 Job 1415 – Dimensional Control Testing for lacing concept demo. New Work (+$14.4K) WBS 14 (+$14.4K) - ECP-035 identified the need to bore 4 holes/casting to accommodate N2 cooling lines. This work will be accomplished on the completed casting after it is received at PPPL and will be done by PPPL labor. Correction of Data Entry Error (-$114K) WBS 12 - Drawdown on Undistributed Budget to correct data entry error reflected in ECP-031 (-$114K) |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-036 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: August 5, 2005 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) Assessment of Other Options: None. No other offsets identified at this time. List Attachments, Impacted Documents, etc. Budget Reconciliation Sheet Revised Cost and Schedule Bar Charts for July 2005 Summary of Cost Impacts: WBS Element Previous Baseline (ECP-033 & ECP-034) ($) Current Baseline ($) Change ($) 12 – Vacuum Vessel $9,571K $9,400K ($171K) 13 – Conventional Coils $4,790K $4,790K - 14 – Modular Coils $28,131K $29,114K +$983K 15 - Structures $1,413K $1,413K - 16 – Coil Services $1,140K $1,140K - 17 – Cryostat & Base Suppt Structure $1,361K $1,361K - 18 – Field Period Assembly $5,430K $5,430K - 19 – Stellarator Core Mgmt & Integration $2,752K $2,738K -$14K Subtotal WBS 1 – Stellarator Core $54,588K $55,385K +$797K WBS 2 – Auxiliary Systems $783K $783K - WBS 3 – Diagnostic Systems $1,143K $1,143K - WBS 4 – Electrical Power Systems $3,301K $3,301K - WBS 5 – I&C Systems $2,050K $2,050K - WBS 6 – Facility Systems $691K $691K - WBS 7 Test Cell Prep & Machine Assembly $4,473K $4,473K - WBS 8 – Project Oversight & Support $11,053K $11,053K - Subtotal $77,982K $78,779K +$797K PPPL Allocations $1,577K $1,577K - Contingency $12,767K $11,969K -$797K DCMA 75k 75k TOTALS $92,401K $92,401K - Remaining contingency ($11,969K) is ~ 25%. |