| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Ron Strykowsky | Date: October 25, 2005 |
| ECP No: 039 | ECP Title: Performance Measurement Baseline (PMB) Update – October 2005 |
| Required Reviewers |
| Required Reviewers for this ECP: Paul Goranson, Brad Nelson, Dave Williamson, Mike Cole, Wayne Reiersen, H. Neilson, Judy Malsbury, Frank Malinowski, Jerry Levine, Ron Strykowsky |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Update PMB by October 31st. Revise GRD by November 22nd. |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Deputy Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-039 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: October 25, 2005 |
| Overview of Change Type of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL Description and Reasons for Change: Summary: Approval of this ECP will require a drawdown of contingency of $2,357K from $11,969K in ECP-036 to $9,612K (~21.6% of remaining work scope). This ECP is a combination of estimate growth based on completed work, replanned work, and retirement of unrecoverable cost variances (work activity completed). This ECP does not cover the total estimate growth in the modular and TF coil winding operations, but provides budget to fully cover estimated costs through the third quarter and fourth quarter, respectively, of FY-06. At that time, the need for additional contingency to cover completion of those operations will be re-evaluated based on actual costs to date and reductions resulting from the project’s process improvement efforts. This ECP does not impact Level 1 milestones but one non-critical Level 2 milestone is re-scheduled. The breakdown of proposed changes is as follows: Proposed PMB Updates (+$764K) WBS 12 – Vacuum Vessel (+$106K) WBS 121 – Vacuum Vessel Final Design (+$204K) – redesign of insulation scheme and cooling tubes. WBS 122 and 123 – VV Non-VVSA Procurements (-$98K) – less expensive tubes and insulation due to redesign. WBS 13 – Conventional Coils (-$188K) WBS 131 - TF Coil Fabrication (+$432K) – replanned effort for facility, material, and winding operations. WBS 132 – PF Coil Design & Fabrication (-$466K) – revised plan to use existing NSTX PF1a coil for central solenoid, instead of new coils. WBS 133 – Trim Coils Design and Fabrication (-$154K) – simplified design of trim coils. WBS 14 – Modular Coils (+$1,227K) WBS 142 – Modular Coils Type A & B Final Design (+$520K) – replanned effort to reflect Type C experiences. WBS 142 – Modular Coil Winding (-$17K) – increased effort for ground wrap, interlacing, and shift differential offset by supervision and oversight effort reduction due to shortened schedule. WBS 142 – Mod Coil Winding Supplies (+$655K) – revised estimate to reflect experiences gained in the procurement of Type C1 shims and high strength bolts . WBS 142 – Modular Coil Final Design (+$69K) – revised estimate of oversight (Title III) of contract based on experience gained on C1 casting. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-039 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: October 25, 2005 |
| Overview of Change WBS 18 – Field Period Assembly (-$90K) WBS 183 – Field Period Assembly (-$40K) – eliminated requirement to bakeout field period assembly to 350°C. WBS 183 – Field Period Assembly Tooling & Constructability (-$50K) – re-planning eliminated need for second set of assembly fixtures. WBS 3 – Diagnostics (-$42K) WBS 31 – Magnetic Diagnostics (+$62K) – Redesign of saddle loops and termination box. WBS 38 – E-Beam Mapping (-$104) – simplified application of e-beam mapping scheme. WBS 5 – Plasma Control Systems (-$100K) – simplified plasma control system design. WBS 81 – Project Management (-$54K) – re-planned FY2006-09 effort to match project needs. WBS 82 – Dimensional Control (+$84K) – dimensional control planning for assembly operations. Various WBS Elements – Rescheduling and Rate Changes (-$180K) Unrecoverable Cost Variances – tasks completed (+$1,593K) WBS 13 – Conventional Coils (+$246K) WBS 131 – TF Design (+$97K) – unanticipated iterations on the TF design. WBS 131 – TF Coil fabrication Preparations (+$149K) – unanticipated additional effort to finalize the design, increased material costs, and additional effort to debug electrical system. WBS 14 – Modular Coils (+1,044K) WBS 142 – Modular Coil Final Design (+$409K) – increased effort on the MCWF C Final Design to reflect experiences gained in the Twisted Racetrack Coil winding. WBS 144 – Completion of Coil Test Facility (+$150K) – additional efforts required to debug cryogenic systems and to incorporate design safeguards into the facility. WBS 141 – Fabrication of First Casting as Part of R&D Contract (+$137K) – additional costs associated with the fabrication of the first production casting. WBS 142 – Modular Coil Final Design (+$110K) – additional Title III efforts to work with vendor to address technical requirements and schedule. Other Miscellaneous (+$23.8K) – TRC winding prep, etc. WBS 17 – Cryostat & Base Support Structure Design (+$178K) – underestimate of design and engineering effort needed. WBS 4 –Power Systems (+$68K) – revised estimate for the design effort. WBS 7 - Test Cell Preparations (+$129K) – additional efforts to restore/refurbish house power to ensure its availability for the NCSX test cell. Various WBS Elements – unrecoverable cost variances for work now completed (-$72K) Level 2 Milestone, “Vacuum Vessel Sectors Delivered” re-scheduled from May, 2006 to Sept. 2006. Leaves ample free float (at least 6 months) and better matches project needs. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-039 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: October 25, 2005 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) Assessment of Other Options: None. No other offsets identified at this time. List Attachments, Impacted Documents, etc. Budget Reconciliation Sheet Revised Cost and Schedule Bar Charts for October 2005 Summary of Cost Impacts: WBS Element Previous Baseline (ECP-036) ($) Current Baseline (ECP-039) ($) Change ($) 12 – Vacuum Vessel $9,400K $9,439K +$39K 13 – Conventional Coils $4,790K $4,831K +$41K 14 – Modular Coils $29,114K $31,356K +$2,242K 15 - Structures $1,413K $1,386K -$27K 16 – Coil Services $1,140K $1,135K -$5K 17 – Cryostat & Base Suppt Structure $1,361K $1,533K +$172K 18 – Field Period Assembly $5,430K $5,281K -$149K 19 – Stellarator Core Mgmt & Integration $2,738K $2,767K +$29K Subtotal WBS 1 – Stellarator Core $55,385K $55,728K +$2,343K WBS 2 – Auxiliary Systems $783K $791K +$8K WBS 3 – Diagnostic Systems $1,143K $1,149K +$6K WBS 4 – Electrical Power Systems $3,301K $3,305K +$4K WBS 5 – I&C Systems $2,050K $1,874K -$176K WBS 6 – Facility Systems $691K $679K -$13K WBS 7 Test Cell Prep & Machine Assembly $4,473K $4,555K +$182K WBS 8 – Project Oversight & Support $11,053K $11,025K -$28K Subtotal $78,779K $78,779K +$797K PPPL Allocations $1,577K $1,608K +$32K Contingency $11,969K $9,612K -$2,357K DCMA 75k 75k - TOTALS $92,401K $92,401K - Remaining contingency ($9,612K) is ~ 21.6% of remaining work. One Level 2 Milestone, “Vacuum Vessel Sectors Delivered” re-scheduled from May, 2006 to Sept. 2006. Leaves ample free float (at least 6 months) and better matches project needs. |

|  | Current Baseline (ECP-036) ($K) |  | Unrecoverable Cost Variances ($K) |  | ETC Updates & Design Changes ($K) |  | Total Budget Change ($K) |  | Proposed PMB (ECP-039) ($K) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 Stellarator Core Systems | 55,386 |  | 1,385 |  | 957 |  | 2,342 |  | 57,728 |
| 12 - Vacuum Vessel Systems | 9,400 |  | (68) |  | 107 |  | 39 |  | 9,439 |
| 13 - Conventional Coils | 4,790 |  | 246 |  | (205) |  | 41 |  | 4,831 |
| 14 - Modular Coils | 29,114 |  | 1,044 |  | 1,198 |  | 2,242 |  | 31,356 |
| 15 - Structures | 1,413 |  | (1) |  | (26) |  | (27) |  | 1,386 |
| 16 - Coil Services | 1,140 |  |  |  | (5) |  | (5) |  | 1,135 |
| 17 - Cryostat and Base Support Struct | 1,361 |  | 178 |  | (6) |  | 172 |  | 1,533 |
| 18 - Field Period Assembly | 5,430 |  | (23) |  | (126) |  | (149) |  | 5,281 |
| 19 - Stellarator Core Mgt & Integr | 2,738 |  | 9 |  | 20 |  | 29 |  | 2,767 |
| 2 Heating, Fueling & Vac Sys | 783 |  |  |  | 8 |  | 8 |  | 791 |
| 3 Diagnostics | 1,143 |  | 18 |  | (12) |  | 6 |  | 1,149 |
| 4 Electrical Power Sys | 3,301 |  | 68 |  | (64) |  | 4 |  | 3,305 |
| 5 Central I&C Sys | 2,050 |  | (7) |  | (169) |  | (176) |  | 1,874 |
| 6 Facility Sys | 691 |  |  |  | (13) |  | (13) |  | 678 |
| 7 Test Cell Prep & MachAssy | 4,373 |  | 129 |  | 54 |  | 183 |  | 4,556 |
| 8 Project Oversight & Support | 12,630 |  | 1 |  | 3 |  | 4 |  | 12,634 |
| Subtotal PMB | 80,357 |  | 1,593 |  | 764 |  | 2,357 |  | 82,714 |
| Contingency | 11,969 |  | (1,593) |  | (764) |  | (2,357) |  | 9,612 |
| TEC = | 92,326 |  |  |  |  |  |  |  | 92,326 |
| DCMA | 75 |  |  |  |  |  |  |  | 75 |
| TOTALS - TPC | 92,401 |  |  |  |  |  |  |  | 92,401 |
|  |  |  |  |  |  |  | BCWR |  | 44,400 |
|  |  |  |  |  |  |  | Contingency Balance |  | 9,612 |
|  |  |  |  |  |  |  |  |  | 21.6% |