| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Ron Strykowsky |  |  | Date: December 16, 2005 |  |
| ECP No: 041 |  | ECP Title: PMB Update – December 2005 |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: M.Viola, B. Nelson, W. Reiersen, J. Levine, J. Malsbury, L. Dudek, P. Goranson |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |  |  |  |  |
| Actions Update PMB by December 22, 2005 |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Deputy Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) ECP-041 |  |
| Originator: Ron Strykowsky | Date: December 16, 2005 |
| Overview of Change Type of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: Revised forecast delivery dates of the VVSA (now 3/27/2006, 5/15/2006, and 6/16/2006) have been provided by Major Tool (see weekly report of period from 12/08/2005 through 12/14/2005). It is important that the scheduling of activities related VVSA delivery be coordinated with the forecast delivery dates. The purpose of this ECP is to revise the PMB accordingly. The proposed change to the PMB reflects the revised VVSA delivery schedule. Impacted WBS Elements: WBS 12 & WBS 18 Impacts of Change (Briefly Describe): No technical or cost impact. There is no impact on Level II milestones or the critical path. However, the delayed delivery of the VV sectors impact dependent Field Period Assembly tasks, which are also re-scheduled in this revised PMB. Does this Change Impact Material Already Procured or Parts/Assemblies Already Assembled/Manufactured using this Material: Yes No If “Yes”, what is the recommended disposition of this material/part/assembly? Assessment of Other Options: None List Attachments, Impacted Documents, etc.: - Updated PMB Barcharts - MTM Monthly Status Report Dated Dec 14th, 2005 Description of Change: Reschedules Job 1250 (VVSA Contract) and Job 1810 (Station 1 Field Period Assembly) – see pages 5, 6, and 34 on the attached bar charts. There is sufficient float to accommodate these proposed changes. |  |