| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Ron Strykowsky | Date: March 22, 2006 |
| ECP No: 043 | ECP Title: March 2006 PMB Update |
| Required Reviewers |
| Required Reviewers for this ECP: Dave Williamson, Brad Nelson, Larry Sutton, Wayne Reiersen, Jerry Levine, Judy Malsbury, Jim Chrzanowski, Hutch Neilson, Phil Heitzenroeder |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Update PMB by March 31, 2006 |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Deputy Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) ECP-043 |
| Originator: Ron Strykowsky | Date: March 22, 2006 |
| Overview of Change Type of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason and Description of the Proposed Change: MCWF Modification #11 incorporated technical requirements changes in the MCWF fabrication work as approved by ECP-038, resulting in a price increase of $356.09K (due to both the technical changes, the decision by the NCSX Project to have MTM purchase replacement bolts, and an extension to the MCWF delivery schedule by 15 weeks - interim delivery dates revised and final delivery date extended from September 15th, 2006 to December 29th, 2006). ECP-038 only addressed the technical changes. MCWF Modification #12 reflected the renegotiated a revised delivery schedule (replaced the revised schedule in Amendment #11) and provided delivery price incentives for the MCWF contract. In addition, the technical changes (i.e., relaxation of tolerances) reflected in ECP-042 were also part of this amendment. The project schedule was revised to incorporate a delivery schedule that is more conservative than the contract schedule (see discussion that follows). This ECP requests and additional $535.88 of budget to cover the amount that EIO would earn if the remaining MCWFs are delivered according to the Project schedule. Impacted WBS Elements: 14, 18 Impacts of Change (Briefly Describe): Approval of this ECP will require a reduction in contingency by $892K from $9,612K to $8,720K. The Level II Milestone, “Last MCWF Delivered” is re-scheduled from June 2007 to September 2007. Accommodating this change in the schedule required the field period assembly plan to incorporate some parallel operations as well as employ 2 shift operations on the last field period final assembly. Schedule contingency remains unchanged at 5 months. Does this Change Impact Material Already Procured or Parts/Assemblies Already Assembled/Manufactured using this Material: Yes No If “Yes”, what is the recommended disposition of this material/part/assembly? There are two impacts: Casting C-3 comes under the incentive program implemented by Amendment #12; and Castings C-1 through C-3 will need hardware modifications (i.e., replacement of bolts). |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-043 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: March 22, 2006 |
| Discussion of Schedule and Potential Additional Cost Risk: Amendment 12 to the EIO contract laid out a planned delivery of MCWF's for which EIO and MTM have committed to. Their incentive payments are tied to these dates. However, PPPL has determined that EIO's delivery schedule still contains schedule risks. Required learning curves improvements during MTM machining operations, while showing signs of improvement, have not yet been realized. In recognition of these risks PPPL has established a more likely delivery schedule that calls for winding form delivery every 4.8 weeks vs. the 4 week interval that EIO has promised. The project thinks it prudent to adopt this more conservative schedule as one that is more likely to be achieved. As such the projected incentives covered in this ECP are based on this more conservative schedule. The project recognizes an additional cost risk exists should EIO deliver on their new contract dates. Should EIO/MTM adhere to their contract schedule, there are possible additional cost risks of approximately $710K, albeit with an improved schedule performance. However, per mutual agreement between DOE and PPPL the additional risk for DOE has been capped at $410k; cost risks above that ceiling will be absorbed by Princeton University. List Attachments, Impacted Documents, etc. Revised Bar Charts showing updated PMP. Reconciliation of Former PMB (ECP-039) and this ECP-043. MCWF Amendment #12 Projected Delivery Dates and Payment Schedule |