| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Ron Strykowsky | Date: March 20, 2006 |
| ECP No: 043 | ECP Title: March 2006 PMB Update |
| Required Reviewers |
| Required Reviewers for this ECP: Dave Williamson, Brad Nelson, Larry Sutton, Wayne Reiersen, Jerry Levine, Judy Malsbury, Jim Chrzanowski, Hutch Neilson, Phil Heitzenroeder |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Update PMB by March 31, 2006 |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Deputy Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) ECP-043 |
| Originator: Ron Strykowsky | Date: March 20, 2006 |
| Overview of Change Type of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: This ECP incorporates: The cost and schedule impacts of MCWF Modification #11 which incorporated technical requirements changes in the MCWF fabrication work, resulting in a price increase of $356.09K and an extension to the MCWF delivery schedule by 15 weeks (interim delivery dates revised and final delivery date extended from September 15th, 2006 to December 29th, 2006). The technical changes were approved with ECP-042. MCWF Modification #12 that further revises the delivery schedule and provides delivery price incentives for the MCWF contract. The project schedule is revised to incorporate a delivery schedule that is more conservative than the contract schedule. This ECP requests $535.88 of budget to cover the amount that EIO would earn if the remaining MCWFs are delivered according to the Project schedule. Impacted WBS Elements: 14, 18 Impacts of Change (Briefly Describe): Approval of this ECP will require a reduction in contingency by $892K from $9,612K to $8,720K. The Level II Milestone, “Last MCWF Delivered” is re-scheduled from June 2007 to September 2007. Accommodating this change in the schedule required the field period assembly plan to incorporate some parallel operations as well as employ 2 shift operations on the last field period final assembly. Schedule contingency remains unchanged at 5 months. Does this Change Impact Material Already Procured or Parts/Assemblies Already Assembled/Manufactured using this Material: Yes No If “Yes”, what is the recommended disposition of this material/part/assembly? Use “as is” – this ECP impacts all casting deliveries following C-3 (e.g., 15 remaining castings). Assessment of Other Options: . Amendment 12 to the EIO contract lays out a planned delivery of MCWF's for which EIO and MTM has committed to. Their incentive payments are tied to these dates. However, PPPL has determined that EIO's delivery schedule still contains schedule risks. Required learning curves improvements during MTM machining operations, while showing signs of improvement, have not yet been realized. In recognition of these risks PPPL has established a more likely delivery schedule that calls for winding form delivery every 4.8 weeks vs. the 4 week interval that EIO has promised. The project thinks it prudent to adopt this more conservative schedule as one that is more likely to be achieved. As such the projected incentives covered in this ECP are based on this more conservative schedule. The project recognizes an additional cost risk exists should EIO deliver on their new contract dates. Per mutual agreement between DOE and PPPL the additional risk for DOE has been capped at $364k. Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. Revised Bar Charts showing updated PMP. Reconciliation of Former PMB (ECP-039) and this ECP-043. MCWF Amendment #12 Projected Delivery Dates and Payment Schedule Description of Change: ECP-042 summarized the technical changes to improve machining and inspection times as a result of technical meetings held at MTM the week of January 3, 2006. This ECP only reflects the revised cost and schedule impacts associated with the re-negotiated delivery schedule, as amended by the Project. |