| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Ron Strykowsky | Date: March 20, 2006 |
| ECP No: 043 | ECP Title: March 2006 PMB Update |
| Required Reviewers |
| Required Reviewers for this ECP: Dave Williamson, Brad Nelson, Larry Sutton, Wayne Reiersen, Jerry Levine, Judy Malsbury, Jim Chrzanowski, Hutch Neilson, Phil Heitzenroeder |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Update PMB by March 31, 2006 |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Deputy Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) ECP-043 |
| Originator: Ron Strykowsky | Date: March 20, 2006 |
| Overview of Change Type of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL Is this really a technical change? (Check all that Apply) Reason for Change: This ECP incorporates: The cost and schedule impacts of MCWF Modification #11 which incorporated technical requirements changes in the MCWF fabrication work, resulting in a price increase of $???K and an extension to the MCWF delivery schedule by 15 weeks (interim delivery dates revised and final delivery date extended from September 15th, 2006 to December 29th, 2006). The technical changes were approved with ECP-042. MCWF Modification #12 that further revises the delivery schedule and provides delivery price incentives for the MCWF contract. The project schedule is revised to incorporate a delivery schedule that is more conservative than the contract schedule. This ECP requests $538.9K of budget to cover the amount that EIO would earn if the remaining MCWFs are delivered according to the project schedule. FYI: the agreement is that DOE picks up all the risk except for the last $300K. Impacted WBS Elements: 14, 18 Impacts of Change (Briefly Describe): Approval of this ECP will require a reduction in contingency by $892K from $9,612K to $8,720K. The Level II Milestone, “XXXX” is re-scheduled from date A to date B. Briefly describe the modification to the field period assembly plan. Schedule contingency remains unchanged at 5 months. Does this Change Impact Material Already Procured or Parts/Assemblies Already Assembled/Manufactured using this Material: Yes No Why “Yes”? If “Yes”, what is the recommended disposition of this material/part/assembly? Use “as is” – this ECP impacts all casting deliveries following C-3 (e.g., 15 remaining castings). Assessment of Other Options: . This is not an answer. Explain what happens if EIO delivers according to the contract schedule and why you are not drawing down contingency to cover that full amount. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-043 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: March 20, 2006 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. Revised Bar Charts showing updated PMP. Reconciliation of Former PMB (ECP-039) and this ECP-043. MCWF Amendment #12 Projected Delivery Dates and Payment Schedule Description of Change: ECP-042 summarized the technical changes to improve machining and inspection times as a result of technical meetings held at MTM the week of January 3, 2006. Out of scope. This was already covered in ECP-042. Are there any technical changes with this ECP? |