| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Ron Strykowsky | Date: June 8, 2006 |
| ECP No: 045 | ECP Title: May 2006 PMB Update |
| Required Reviewers |
| Required Reviewers for this ECP: Hutch Neilson, Wayne Reiersen, Brad Nelson, Larry Dudek, Mike Williams |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Update PMB by June 9, 2006 |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Deputy Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-045 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: June 8, 2006 |
| Overview of Change Type of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: Office of Science mid-year review assessment of cost to date plus updates of the estimate to complete. These proposed changes were presented and positively reviewed at the May, 2006 Lehman review. Impacted WBS Elements: ALL WBS Elements Impacts of Change (Briefly Describe): Re-align the project PMB (BCWS) by recognizing; The additional cost incurred for retired risk ($510k); Re-evaluated scope requirements including estimates for future scope (net +$39k); and Realigning the project schedule consistent with estimated cost to complete. This change requires the drawdown of $549k of contingency from $8,720k to $8,171k. It should be noted that while the Project expects a credit for FY2006 end-of-year rate changes, this has not been taken into account in this ECP. This change does not impact Level I or II milestones. The project total float has increased from 5 to 6 month as a result of schedule optimizations. Much of the cost increases documented in this ECP were offset by non-CD-4 scope reductions primarily in the I&C and electrical power systems. To ensure that the required safeguards and vigilance to the CD-4 deliverables is met the project has drafted a "Safe startup and Control" plan. This plan depicts those controls, actions, documents, sub-system procedures, ES&H requirements necessary to meet the CD-4 requirements for the Stellarator Acceptance Testing and Magnetic Configuration Studies phase of the NCSX Project. Does this Change Impact Material Already Procured or Parts/Assemblies Already Assembled/Manufactured using this Material: Yes No |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-045 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: June 8, 2006 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. 1) Detailed resource loaded schedule 2) ECP-43 vs ECP-45 budget comparison table 3) Safe Startup and Control Plan 4) Retired risk white paper Description of Change: WBS Total Change Unrecoverable Cost Variances Estimate to Complete Change |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-045 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: June 8, 2006 |
| Continuation Sheet: Description of Change: WBS Total Change Unrecoverable Cost Variances Estimate to Complete Change |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-045 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: June 8, 2006 |
| Continuation Sheet: Description of Change: WBS Total Change Unrecoverable Cost Variances Estimate to Complete Change |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-045 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: June 8, 2006 |
| Continuation Sheet: Description of Change: WBS Total Change Unrecoverable Cost Variances Estimate to Complete Change |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) ECP-045 |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) |
| Originator: Ron Strykowsky | Date: June 8, 2006 |
| Continuation Sheet: Description of Change: WBS Total Change Unrecoverable Cost Variances Estimate to Complete Change |