## ECP-Estimate increases
Estimate updates
WBS | Cost increment | Description
12 | 81.7 | vac vessel hardware cost for cooling tube clamps and saddles. (Job1204)
| -22.4 | VVSA final assy dwgs moved to WBS 18.
59.3
13 | -22.1 | misc replanning and estimating
14 | 53.6 | Ancillary mod coil hardware designs (ie shear plate test and design, clamp modifications, fiber optic strain gage qualification. (Job 1403 & 1416)
| 88.1 | Modified clamp hardware, strain gages, data acquisition controllers, and thermocouples. (Job 1408)
| 258.8 | Additional MCWF vendor incentives consistent with EIO's faster delivery rate. Increase ORNL title III. (Job 1411)
| 63.1 | 3rd winding fixture (Job 1460)
| 329.1 | Modular coil winding operations including ORNL Title III ($22), fully fund estimates through February ($73), and additional punch list task for coil completion ($234). (Job 1451 & 1459)
| 161.9 | Modular coil interface design tasks. Test bladder concept and design, bolt reaming concept and design, shear plate/shim testing and design, insulation over wings, and 3 point positioning H/W test and design. (Job 1421)
954.6
15 | -42.1 | Reduced coil structure procurement oversight. (Job 1550)
16 | 11.2 | misc replanning and estimating
17 | -287.8 | Re-estimated cryostat design and procurement based upon simpler design concept. (Job 1701 & 1751
18 | 8 | Field period assembly fixture design and fabrication . (Job1803 & 1805)
| 315.2 | Field period assembly specifications and assembly drawings. (Job 1806)
| 94.9 | Reduced health physics req'd coverage (-$80), reduced metrology supervision support (-$45). Increased cost for field period fixture installation ($27) and ORNL title III during assembly ($193). (Job1802)
| 227.2 | increased station 1,2&3 estimates including pre-fit of modular coils. (Job 1810)
645.3
19 | -151.1 | Reduced LOE support of general stellarator core management. Re-allocated to WBS 14 and 18.
Estimate updates
WBS | Cost increment | Description
2 | 2.3 | misc replanning and estimating
3 | 33.75 | Increased general diagnostic integration support req'd in FY07
4 | 47.25 | misc replanning and estimating
5 | 1.8 | misc replanning and estimating
6 | 1.2 | misc replanning and estimating
7 | -569 | Reduced support crew coverage and supervision as a result of tightening the final machine assembly schedule. (Job 7401 & 7501)
| 35.7 | misc replanning and estimating (Job 7503)
-533.3
8 | 131.5 | Re-estiamted req'd engineering management & system engineering support (Job 8202)
| 14.4 | Re-estimated Design integration,system analysis and dimensional control coordination. (Jobs 8203, 8204, & 8205)
| 6.5 | misc replanning and estimating
152.4
872.7
| 1246.5 | -1246.9

## ECP-cost variances
Unrecoverable Cost Variances
WBS | Cost increment | Description
12 | 126.4 | Vacuum vessel sectors delivered on schedule. Work scope completed. Cost overrun attributed to dispositioning NCR's and resolving fabrication issues. (Job 1250 closed)
12 | -30 | Vacuum vessel final design complete. Job 1203 closed
13 | 32 | TF coil final design completed. Job 1301 closed.
18 | 12 | Health physics oversight of fabrication activities in the TFTR test cell. Required coverage higher than planned.
8 | 233.4 | Project management and engineering management and integration LOE support during FY06.Major increases seen in systems engineering to support integrated modeling and analysis.
373.8

## Job detail
WBS | JOB | FY2003 | FY2004 | FY2005 | FY2006 | FY2007 | FY2008 | FY2009 | ECP-52 | ECP-50 | delta | bcwr
12 | Job: 1201 - Vacuum Vessel Prelim Dsn-**CLOSED** | 424.4 | [6 empty] | 424.4 | 424.4 | 0 | 0 | 6487.3
12 | Job: 1202 - Vacuum Vessel R&D | 793 | 998.2 | -21 |  |  |  |  | 1770.2 | 1770.2 | 0 | 0
12 | Job: 1206 - VV Field Weld Joint R&D-**CLOSED** |  | 3.4 | 12.2 |  |  |  |  | 15.6 | 15.6 | 0 | 0
12 | Job: 1203 - Vacuum Vessel Final Dsn-**CLOSED** |  | 628.3 | 299.8 | 289.8 |  |  |  | 1217.9 | 1270.3 | -52.4 | 0
12 | Job:1204-VV Sys Procurements (non VVSA)-DUDEK |  |  |  | 187.5 | 253.2 | 244.5 |  | 685.2 | 603.5 | 81.7 | 497.7
12 | Job: 1250 - Vacuum Vessel Fabrication--**CLOSED** |  | 36.9 | 3416.1 | 2355.6 |  |  |  | 5808.6 | 5681.6 | 127 | 0
13 | Job: 1301 - TF Design-KALISH**CLOSED** | 91.7 | 333.9 | 494.1 | 50.9 |  |  |  | 970.6 | 965.8 | 4.8 | 0
13 | Job: 1350 TF Coil Fab Prep-CHRZANOWSKI**CLOSED** |  |  | 346.1 | 200.9 |  |  |  | 547 | 560.3 | -13.3 | 0
13 | Job: 1351 - TF Coil Fabr Supplies-KALISH |  |  | 179.9 | 281.2 | 8.9 |  |  | 470 | 469.6 | 0.4 | 8.9
13 | Job: 1361 - TF Fabrication-KALISH |  |  | 9.9 | 642.5 | 1145 | 247.9 |  | 2045.3 | 2017.9 | 27.4 | 1392.9 | 3159.1
13 | Job: 1302 - PF Design -KALISH |  |  | -13.7 | 7.3 | 138.4 |  |  | 132 | 132 | 0 | 138.4
13 | Job: 1352 - PF Coil Procurement-KALISH |  |  |  |  | 276.4 | 511.7 |  | 788.1 | 794.6 | -6.5 | 788.1
13 | Job: 1354 - Trim Coil Design &Procurement-KALISH | [5 empty] | 106.1 |  | 106.1 | 103.4 | 2.7 | 106.1
13 | Job: 1303 -Central Solenoid Support Dsn-DAHLGREN |  |  |  | 106.4 |  |  |  | 106.4 | 116.9 | -10.5 | 0
13 | Job: 1353 - CS Structure Procurement-DAHLGREN |  |  |  |  | 32.5 | 90.1 |  | 122.6 | 120.9 | 1.7 | 122.6
13 | Job: 1355 - WBS 13 I&C Proc & | [5 empty] | 93.4 |  | 93.4 | 91.2 | 2.2 | 93.4
14 | Job: 1401 - Mod Coil Prel.Dsn**CLOSED** | 303 |  | 1 |  |  |  |  | 304 | 304 | 0 | 0
14 | Job: 1402 - Mod.Coil Analyses**CLOSED** | 239.1 | [6 empty] | 239.1 | 239.1 | 0 | 0
14 | Job:1404-MCWF R&D & 1st Prod Casting**CLOSED** | 586 | 1625.8 | 331.6 |  |  |  |  | 2543.4 | 2543.5 | -0.1 | 0
14 | Job: 1413 -MCWF Fracture Analysis-**CLOSED** |  |  | 28.2 | -0.3 |  |  |  | 27.9 | 27.8 | 0.1 | 0
14 | Job: 1405-Mod Coil Winding R&D Prep-**CLOSED** | 168.1 | [6 empty] | 168.1 | 168.1 | 0 | 0
14 | Job: 1407 -Mod Coil Winding Facility-**CLOSED** | 267.6 | 2236.3 | 42.2 | 25.4 |  |  |  | 2571.5 | 2571.4 | 0.1 | 0
14 | Job: 1412 - Complete Winding Facilities-*CLOSED* |  |  | 537.4 | 3.6 |  |  |  | 541 | 541 | 0 | 0
14 | Job: 1406 - Mod. Coil Winding | 831.1 | 1266.5 | 149 | 17 |  |  |  | 2263.6 | 2263.6 | 0 | 0
14 | Job: 1410 MC Twisted Racetrack Fabr-**CLOSED** |  |  | 1050.2 | -0.2 |  |  |  | 1050 | 1050 | 0 | 0
14 | Job: 1409 - Coil Test Stand-GETTELFINGER*CLOSED* |  | 363.8 | 552.1 | -90 |  |  |  | 825.9 | 825.9 | 0 | 0
14 | Job: 1414 Coil Testing-Gettelfinger**CLOSED** |  |  | 132.1 | 542.8 |  |  |  | 674.9 | 674.8 | 0.1 | 0
14 | Job: 1415 Dim Cntrl Testing-RAFTOPOLOUS*CLOSED** |  |  | 23.9 |  |  |  |  | 23.9 | 23.9 | 0 | 0
14 | Job: 1419-Winding Fac. Mods-CHRZANOWSKI*CLOSED* |  |  | 48 | 7.2 |  |  |  | 55.2 | 55.2 | 0 | 0
14 | Job: 1403 - Modular Coil Final Design-WILLIAMSON |  | 1773.9 | 1139 | 397.7 |  |  |  | 3310.6 | 3496.6 | -186 | 0
14 | Job: 1416-Mod Coil Type A&B Final Dsn-WILLIAMSON |  | 6.5 | 76.6 | 388.3 | 214.4 |  |  | 685.8 | 446.2 | 239.6 | 214.4
14 | Job:1408-Mod Coil Winding Supplies-CHRZANOWSKI | 29.8 | 2.5 | 529.6 | 1083.4 | 303.4 | 4.2 |  | 1952.9 | 1864.8 | 88.1 | 307.6
14 | Job: 1411-MCWF Fabrication S005242-HEITZENROEDER |  | 20.4 | 3905.9 | 4153.3 | 1766.2 |  |  | 9845.8 | 9587 | 258.8 | 1766.2
14 | Job:1460 3rd Winding Fixture-CHRZANOWSKI |  |  |  |  | 63.1 |  |  | 63.1 |  | 63.1 | 63.1 | 4118.4
14 | Job: 1451 - Mod Coil Winding-CHRZANOWSKI |  |  | 134.4 | 2178.7 | 3218.5 | 462.3 |  | 5993.9 | 6087.6 | 329.1 | 3680.8
| Job: 1459 - Mod Coil Fabr.Punch List-CHRZANOWSKI |  |  |  | 48.3 | 330.8 | 43.7 |  | 422.8 |  |  | 374.5
14 | Job: 1421-Mod Coil Interface Design-WILLIAMSON |  |  | 70.4 | -15.3 | 324.7 |  |  | 379.8 | 916.9 | -537.1 | 324.7
14 | Job: 1431 - Mod. Coil Interface Hardware-DUDEK |  |  |  |  | 699 |  |  | 699 |  | 699 | 699
18 | Job: 1804-Metrology Hardware-RAFTOPOULOS |  | 198 | 239.6 | 111.4 | 15.3 | 11.7 | 11.5 | 587.5 | 585.9 | 1.6 | 38.5 | 4321.1
18 | Job: 1801-Field Period Assly -CHRZANOWSKI (ORNL) | 60.8 |  |  | 3.9 |  |  |  | 64.7 | 64.7 | 0 | 0
18 | Job: 1803- FP Assy Toolg/Constructability-BROWN |  |  | 461.4 | 366.4 | 342.4 |  |  | 1170.2 | 1372.4 | -202.2 | 342.4
18 | Job: 1805 -FP Assy H/W&Fixture |  |  |  | 13.1 | 197.1 |  |  | 210.2 |  | 210.2 | 197.1
18 | Jpb: 1806 - FP Assembly specs & dwgs |  |  |  |  | 304.8 | 10.4 |  | 315.2 |  | 315.2 | 315.2
18 | Job: 1802 - FP Assy Oversight&Support-VIOLA |  | 164.6 | 203.2 | 308.8 | 661.7 | 276.1 |  | 1614.4 | 1507.5 | 106.9 | 937.8
18 | Job:1810 - Field Period Assembly-VIOLA |  |  |  | 127.5 | 1157.4 | 1332.7 |  | 2617.6 | 2390.4 | 227.2 | 2490.1
dcma | dcma |  | 75 | [5 empty] | 75 | 75 | 0 | 0
15 | Job: 1501 - Coil Structures Design- DAHLGREN |  | 34.6 | 45.4 | 18.8 | 119.1 |  |  | 217.9 | 217.1 | 0.8 | 119.1
15 | Job:1550 - Coil Structures Procurement -DAHLGREN |  |  |  |  | 489.7 | 642.8 |  | 1132.5 | 1175.4 | -42.9 | 1132.5
16 | Job: 1601 - Coil Services Design-WILLIAMSON |  |  |  | 2.8 | 171 | 956.9 | 17.9 | 1148.6 | 1137.8 | 10.8 | 1145.8
17 | Job:1701-Cryost&Base Sprt Strct Dsn-GETTLEFINGER | 12.2 | 65.7 | 244.2 | 103.2 | 56.5 | 124 |  | 605.8 | 730.4 | -124.6 | 180.5
17 | Job: 1751 - Cryostat Procurement | [5 empty] | 322 | 55.3 | 377.3 | 540.5 | -163.2 | 377.3
17 | Job: 1752 - Base Support Structure Procurement |  |  |  |  | 2.7 | 228.5 |  | 231.2 | 230.9 | 0.3 | 231.2
19 | Job: 1901 - Stellarator Core Mngtt&Integr-NELSON | 254.2 | 640.7 | 557.5 | 554.3 | 208.3 | 251.5 | 153.7 | 2620.2 | 2771.3 | -151.1 | 613.5
2 | Job: 2001-VPS Gas& Cond Sys Oversight-BLANCHARD | 63.7 |  |  | -0.8 |  |  |  | 62.9 | 62.9 | 0 | 0 | 4138.5
2 | Job: 2101 - Fueling Systems | [5 empty] | 61.2 |  | 61.2 | 60.1 | 1.1 | 61.2
2 | Job: 2201 - Vacuum Pumping Systems | [5 empty] | 77.2 |  | 77.2 | 76.1 | 1.1 | 77.2
2 | Job: 2501 - Neutral Beam Refurbishment-STEVENSON | 123 | 161.4 |  | 0.7 |  |  |  | 285.1 | 285 | 0.1 | 0
3 | Job: 3101 Magnetic Diagnostics |  |  | 117.2 | 269.9 | 112.9 | 21.6 | 0.1 | 521.7 | 518.5 | 3.2 | 134.6
3 | Job: 3601 - Edge and Divertor | [5 empty] | 9.4 |  | 9.4 | 9.4 | 0 | 9.4
3 | Job: 3801 - Electron Beam Mapping | [5 empty] | 29.6 |  | 29.6 | 29.6 | 0 | 29.6
3 | Job: 3901 - Diagnostics sys Integration-JOHNSON | 155.5 | 65 | 54.4 | 70.5 | 30 |  |  | 375.4 | 345.3 | 30.1 | 30
4 | Job: 4101 - AC Power-RAMAKRISHNAN |  | 81.4 | 10.6 | 15.9 |  | 256.1 |  | 364 | 357.4 | 6.6 | 256.1
4 | Job: 4301 - DC Systems-RAMAKRISHNAN |  |  | 212 | 169.8 |  | 347.4 |  | 729.2 | 726.1 | 3.1 | 347.4
4 | Job: 4401 - Control & Protection-RAMAKRISHNAN |  | 1.1 | 55.5 | 25.8 |  | 757 | 173.2 | 1012.6 | 989 | 23.6 | 930.2
4 | Job: 4501 - Power Sys Dsn & Integr-RAMAKRISHNAN | 112.3 | 29.9 | -10.5 | 16.2 |  | 928.1 |  | 1076 | 1062.5 | 13.5 | 928.1
4 | Job: 4601 - FCPC Bldg Mods-RAMAKRISHNAN | 1.3 | [6 empty] | 1.3 | 1.3 | 0 | 0
5 | Job: 5101 - TCP/IP Infrastructure Systems | [5 empty] | 150.8 |  | 150.8 | 150.8 | 0 | 150.8
5 | 5201 - I&C Systems | [5 empty] | 122.9 | 15.9 | 138.8 | 138.1 | 0.7 | 138.8
5 | 5301 - Data Acquisition | [5 empty] | 150.1 |  | 150.1 | 149.8 | 0.3 | 150.1
5 | Job: 5401 - Facility Timing & | [5 empty] | 82.2 |  | 82.2 | 82.2 | 0 | 82.2
5 | 5501 - Real Time Control System | [5 empty] | 85.9 | 8.1 | 94 | 93.6 | 0.4 | 94
5 | Job: 5601 - Central Safety Interlock Systems | [5 empty] | 129.4 |  | 129.4 | 129.4 | 0 | 129.4
5 | Job: 5801 -Central I&C Integr | 11.9 | 16 | 5.5 | 12.3 |  | 12.5 |  | 58.2 | 57.8 | 0.4 | 12.5
6 | Job:6101 - Water Systems | [5 empty] | 13.8 |  | 13.8 | 13.8 | 0 | 13.8
6 | Job: 6163 - Facility Systems Support FY04 |  | 15 | [5 empty] | 15 | 15 | 0 | 0
6 | Job: 6201 - Cryogenic Systems | [5 empty] | 456.2 |  | 456.2 | 455 | 1.2 | 456.2
6 | Job: 6301 - Utility Systems | [5 empty] | 106.9 |  | 106.9 | 106.9 | 0 | 106.9
6 | Job: 6501 - Facility Systems Integration-DUDEK | 9.4 | [6 empty] | 9.4 | 9.4 | 0 | 0
7 | Job: 7101 - Shield Wall Modif | 32.2 |  |  | 0.5 |  |  |  | 32.7 | 32.6 | 0.1 | 0 | 2892.3
7 | Job: 7301 - Platform Design & |  |  | 70.1 | 4.5 |  | 39.3 |  | 113.9 | 112.9 | 1 | 39.3
7 | Job: 7401 - TC Prep & Mach Assy Planning-PERRY | 164 | 238.2 | 396.5 | 32.4 | 34.5 | 424.6 | 261 | 1551.2 | 1773 | -221.8 | 720.1
7 | 7501 - Construction Support Crew | [5 empty] | 284.2 | 304.8 | 589 | 936.2 | -347.2 | 589
7 | 7503 - Machine Assembly | [5 empty] | 800.4 | 505.8 | 1306.2 | 1272 | 34.2 | 1306.2
7 | Job: 7601 - Tooling Design & Fabrication | [5 empty] | 180.6 | 57.1 | 237.7 | 237.6 | 0.1 | 237.7
8 | Job: 8101 - Project Management & Control-NEILSON | 387.3 | 873.1 | 693.1 | 601.6 | 640.9 | 554.5 | 84.5 | 3835 | 3868.1 | -33.1 | 1279.9 | 4609.1
8 | Job: 8102 - NCSX MIE Management ORNL-LYON | 58.6 | 88 | 108.4 | 175 | 65.8 | 36.7 |  | 532.5 | 531.4 | 1.1 | 102.5
8 | Job: 8202 - Engr Mgmt & Sys Eng Support-REIERSEN | 295.5 | 669.6 | 650.3 | 665.6 | 500.1 | 246 | 62.8 | 3089.9 | 2918.4 | 171.5 | 808.9
8 | Job: 8203 - Design Integration-BROWN | 178.8 | 372.6 | 135 | 166.2 | 183.6 |  |  | 1036.2 | 1019.8 | 16.4 | 183.6
8 | Job: 8204 - Systems Analysis-BROOKS | 44.6 | 188.8 | 265.6 | 471.5 | 245.6 |  |  | 1216.1 | 901.2 | 314.9 | 245.6
8 | Job: 8205 - Dimensional Control Coordination |  |  | 89.5 | 149.3 | 30.8 | 31.6 |  | 301.2 | 487.1 | -185.9 | 62.4
8 | Job: 8401 - Project Physcis-ZARNSTORFF | 210.3 | 113.8 |  | 0.5 |  |  |  | 324.6 | 324.6 | 0 | 0
8 | Job: 8402 - Project Physics MIE ORNL-LYON | 41 | 104.9 |  | 0.6 |  |  |  | 146.5 | 146.5 | 0 | 0
8 | Job: 8501 - Integrated Systems Testing | [5 empty] | 224.3 | 589.2 | 813.5 | 807.4 | 6.1 | 813.5
8 | Job: 8998 - Allocations | 112 | 260.7 | 406.8 | 424.8 | 331.5 | 167.7 |  | 1703.5 | 1608.4 | 95.1 | 499.2
Contingency | FY06 CV plus future Contingency |  |  |  | 1398 | 2022 | 3075 | 132 | 6627 | 7873.9 | -1246.9
[11 empty] | 0 | 29725.8
|  | 6062.4 | 13754.5 | 18486.3 | 19143 | 16698.2 | 15823.7 | 2432.9 | 92401 | 92401 | 0
85774
[8 empty] | Free balance contingency = | 5229 | 17.59%
[8 empty] | BCWR = | 29725.8
54.327
[10 empty] | bcws | p
[10 empty] | 1.325 | 0
[10 empty] | 1.325 | 0
[10 empty] | 1.325 | 0
[10 empty] | 1.325 | 0
[10 empty] | 1.325 | 0
[10 empty] | 1.325 | 0
[10 empty] | 1.325 | 0
[10 empty] | 1.325 | 0
[10 empty] | 1.325 | 0
[10 empty] | 1.325 | 0
[10 empty] | 1.325 | 0
[10 empty] | 1.325 | 0