| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |  |  |  |
| --- | --- | --- | --- | --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |  |  |  |  |
| Originator: Bob Simmons |  |  | Date: October 15, 2007 |  |
| ECP No: 058 |  | ECP Title: Update of VV Requirement Documents |  |  |
| Required Reviewers |  |  |  |  |
| Required Reviewers for this ECP: J.L. Anderson, H. Neilson, P. Heitzenroeder, P. Goranson, R. Ramakrishnan, P. Sichta, M. Viola, L. Dudek, C. Phelps, J. Malsbery, J. Levine, M. Zarnstorff, F. Malinowski |  |  |  |  |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |  |  |  |  |
| Actions - Update NCSX-BSPEC-12 (Vacuum Vessel SRD) by 10/22/2007 - Update NCSX-CSPEC-185-01 (Station 1 Field Period Assembly) by 10/22/2007 - Update NCSX-PRL-012-003 (Product Requirements List for the Vacuum Vessel System Thermocouples) by 10/22/2007 |  |  |  |  |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |  |  |  |  |
| Change Level | Approving Official |  | Approval? | Signature |
| 3 | NCSX Project Manager |  | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager |  | Yes No |  |
| 2 | NCSX Federal Project Director |  | Yes No |  |
| 1 | Associate Director OFES |  | Yes No |  |
| 0 | Deputy Secretary of Energy |  | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) ECP- 058 |  |
| Originator: Bob Simmons | Date: October 15, 2007 |
| Overview of Change Type of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: - BSPEC – incorrectly identifies in Section 3.3.2 (Electrical Grounding) a non-existent “NCSX Grounding Specification for Personnel and Equipment Safety” => should refer to PPPL ESHD-5008 (PPPL Environment, Safety, and Health Directives "Safety Manual”) - Station 1 FPA CSPEC - Clarify pressure range and pressure flow requirements. - PRL – clarify electrical isolation requirements Impacted WBS Elements: WBS 12 & WBS 18 Impacts of Change (Briefly Describe): - BSPEC -Correct SRD to reflect proper electrical safety requirement. - CSPEC - Original requirements would have necessitated purchase of expensive components and test equipment, when original requirement was only to check for blockages. These revised requirements will satisfy that need. - PRL – clarify electrical isolation requirements for future procurements of thermocouples. Does this Change Impact Material Already Procured or Parts/Assemblies Already Assembled/Manufactured using this Material: Yes No If “Yes”, what is the recommended disposition of this material/part/assembly? “Use as is” – thermocouples as per revised NCR-3719 (Rev 1). Assessment of Other Options: None – original disposition to NCR of “return to vendor” determined to be incorrect. |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |  |
| --- | --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) ECP- 058 |  |
| Originator: Bob Simmons | Date: October 15, 2007 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. - Updated NCSX-BSPEC-12 -01-dA - NCSX-CSPEC-185-01-02-dF - Updated PRL-12-003-01-dA Description of Change: - BSPEC – revise Section 3.3.2 (Electrical Grounding) to replace in subparagrahs a. & b. the reference to the “NCSX Grounding Specification for Personnel and Equipment Safety” with “PPPL ESHD-5008 (PPPL Environment, Safety, and Health Directives "Safety Manual” ), Chapter 4 (Isolation of Hazards), Section 4.15 (Grounding).” - Station 1 FPA CSPEC - Pressure range and Pressure-Flow Requirements: Change CSPEC 185-01-01, paragraph 4.2.1.1 to read: - “The heating/cooling system shall be leaked checked with helium gas at 300 psigin accordance with ENG-014.” - “The region around the compression fittings shall be checked with a helium leak detector tuned to 1 x 10-5 torr-l/s. Acceptance criteria shall be no detectable leaks.” - PRL – Revise Section 2.1 (Item Definition) to add CSPEC electrical isolation requirement of “>1.5 MOhms at a minimum of 500V” and Section 2.2 (Characteristics) to read: “Similar to type XCIB-E, Style 4 (Ungrounded) |  |