| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| COVER PAGE (TO BE COMPLETED BY SYSTEMS ENGINEERING SUPPORT MANAGER) |
| Originator: Bob Simmons | Date: October 29, 2007 |
| ECP No: 058 | ECP Title: Update of VV & Station 1 FPA Requirement Documents |
| Required Reviewers |
| Required Reviewers for this ECP: J.L. Anderson, H. Neilson, P. Heitzenroeder, P. Goranson, R. Ramakrishnan, P. Sichta, M. Viola, L. Dudek, C. Phelps, J. Malsbery, J. Levine, M. Zarnstorff, F. Malinowski, W. Reiersen, B. Nelson |
| ECP Approval Level Expedited ECP? Yes No Change Level: Approving Official: |
| Actions Prepare NCSX-specific Grounding CSPEC by 12/1/2007 Update the NCSX-BSPEC-12 (Vacuum Vessel SRD) by 12/1/2007 Update NCSX-CSPEC-185-01 (Station 1 Field Period Assembly) by 11/15/2007 Updated NCSX-prl-12-002 (Product Requirements List for the Vacuum Vessel Heater Tapes) by 10/22/2007 Update NCSX-PRL-012-003 (Product Requirements List for the Vacuum Vessel System Thermocouples) by 10/22/2007 Updated NCSX-PRL-012-004 (Product Requirements List for the Thermal Insulation) by 10/24/2007 |
| APPROVALS (TO BE COMPLETED BY APPROVING OFFICIALS) |
| Change Level | Approving Official | Approval? | Signature |
| 3 | NCSX Project Manager | Yes No |  |
| 3a (Expedited ECP) | NCSX Engineering Manager | Yes No |  |
| 2 | NCSX Federal Project Director | Yes No |  |
| 1 | Associate Director OFES | Yes No |  |
| 0 | Deputy Secretary of Energy | Yes No |  |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) ECP- 058 |
| Originator: Bob Simmons | Date: October 29, 2007 |
| Overview of Change Type of ECP: EXPEDITED STANDARD Type of Change: TECHNICAL COST SCHEDULE EDITORIAL (Check all that Apply) Reason for Change: BSPEC – incorrectly identifies in Section 3.3.2 (Electrical Grounding) a nonexistent “NCSX Grounding Specification for Personnel and Equipment Safety” => need to develop this specification for the NCSX Project. Station 1 FPA CSPEC - Clarify pressure range and pressure flow requirements. PRLs for Heat Tapes and Thermocouples – clarify electrical isolation requirements as specified in the Station 1 FPA CSPEC. Impacted WBS Elements: WBS 12 & WBS 18 Impacts of Change (Briefly Describe): Prepare new NCSX Grounding Specification for Personnel and Equipment Safety VV BSPEC -Correct SRD to reflect proper electrical safety requirement. FPA CSPEC - Original requirements would have necessitated purchase of expensive components and test equipment, when original requirement was only to check for blockages. These revised requirements will satisfy that need. PRLs for Heater Tapes and Thermocouples – clarify electrical isolation requirements for future procurements. PRL for Thermal Insulation – replace obsolete “aerogel” silica with “Pyrogel 6671” Does this Change Impact Material Already Procured or Parts/Assemblies Already Assembled/Manufactured using this Material: Yes No If “Yes”, what is the recommended disposition of this material/part/assembly? “Use as is” – thermocouples as per revised NCR-3719 (Rev 1). Assessment of Other Options: None – original disposition to NCR of “return to vendor” determined to be incorrect. |

| NATIONAL COMPACT STELLARATOR PROJECT Engineering Change Proposal (ECP) |
| --- |
| PART I (TO BE COMPLETED BY ORIGINATOR) ECP- 058 |
| Originator: Bob Simmons | Date: October 29, 2007 |
| Detailed Description of the Change: (Use Continuation Sheets and/or Attach Information/Sketches, As Needed) List Attachments, Impacted Documents, etc. None. Description of Change: Prepare new NCSX CSPEC (NCSX-CSPEC-41-01-00) to reflect specific NCSX Project grounding requirements VV BSPEC – revise Section 3.3.2 (Electrical Grounding) to replace in subparagrahs a., b., & c. the reference to the “NCSX Grounding Specification for Personnel and Equipment Safety” with the specific CSPEC reference developed above in step #1. Station 1 FPA CSPEC - Pressure range and Pressure-Flow Requirements: Change CSPEC 185-01-01, paragraph 4.2.1.1 to read: “The heating/cooling system shall be leaked checked with helium gas at 300 psigin accordance with ENG-014.” “The region around the compression fittings shall be checked with a helium leak detector tuned to 1 x 10-5 torr-l/s. Acceptance criteria shall be no detectable leaks.” PRLs PRL-12-002 (Heater Tapes) – Revise Section 2.3.3 (Heater Construction) to add CSPEC electrical isolation requirement of “>1.5 MOhms at a minimum of 500V”. PRL-12-003 (Thermocouples) - Revise Section 2.1 (Item Definition) to add CSPEC electrical isolation requirement of “>1.5 MOhms at a minimum of 500V” and Section 2.2 (Characteristics) to read: “Similar to type XCIB-E, Style 4 (Ungrounded) PRL-12-004 (Thermal Insulation) – Revise Section 1.2.1(Insulation Material) – deleted “aerogel” & replaced with “Pyrogel 6671” - Substitution of insulation material since original no longer made |